## Staff Schedule
Trafford Park Line - K1011 |  |  |  |  | COST
Staff Monitor / CRF Feeder Sheet
Month Reporting; March 2019
Cost Head | [5 empty] | LOR | [47 empty] | Cost to Date |  | Costed To Date | Cost to Completion |  |  | Estimated Final Cost | Previous EFC | Movement | time axis 2017-04-01 to 2021-02-01
| Designation | Name | Start Date | End Date |  | VOLKERRAIL
[6 empty] | AGENCY | [47 empty] | Qty | Rate |  | Qty | Rate | Forecast | [8 empty] | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | bar: 2017-04-01 to 2021-02-01
| TRAFFORD PARK LINE | [54 empty] | 0 | 0
[56 empty] | 0 | 0 |  |  | 0 | 0
| Cost to Date (upto April 2017) | [52 empty] | 1 |  | 0 | 0 |  |  | 0 | 5774532.31 | bar: 2017-04-01
[54 empty] | 0 |  | 0 |  |  |  | 0 | 0
| DIRECTORS | [52 empty] | 0 |  | 0 |  |  |  | 0 | 0
DIR | Commercial Director | Sean Fogarty | Commenced | 2020-04-01 |  | LOR |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [10 empty] | 4.6 |  | 0 | 2.6 |  | 0 | 0 | 180117.6 | -180117.6 | Commercial Director | Sean Fogarty | 25016.3333 | 8.4 | 210137.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[54 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT DELIVERY | [52 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Project Director | Peter Jones | Commenced | 2020-04-01 |  | LOR |  | 0.6 | 0.53 | 0.4 | 0.11 | 0.07 | 0.2 | 0.21 | 0.2 | 0.2 | 0.2 | 0.2 | 0.19 | 0.2 | 0.19 | 0 |  | 0 | 0 | 0.14 | 0.17 | 0.21 | 0.18 | 0.15 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | [10 empty] | 4.35 |  | 0 | 5.2 |  | 0 | 0 | 128780.025 | -128780.025 | Project Director | Peter Jones | 14750 | 11.5 | 169625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Project Leader | Andy Smith | Commenced | 2020-04-01 |  | LOR | [47 empty] | 23 |  | 0 | 13 |  | 0 | 0 | 596313 | -596313 | Project Leader | Andrew Smith | 12500 | 42 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-04-01
PL | Design Coordinator Structures | Dave Harrison | Commenced | 2020-04-01 | 3 days per week | LOR |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 23 |  | 0 | 12.7 |  | 0 | 0 | 290660.475 | -290660.475 | Design Coordinator Structures | David Harrison | 7500 | 16.8 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | OLE Project Manager | Nigel Laing | Commenced | 2020-05-01 | Check Rate | AGENCY |  | 0.35 | 0.36 | 0.4 | 0.4 | 0.20376 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | [9 empty] | 6.3138 |  | 0 | 8.2 |  | 0 | 0 | 227777.6365 | -227777.6365 | OLE Project Manager | Nigel Laing | 13974.9893 | 15.5 | 216612.3334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Section Manager | Andy Pritchard | Commenced | 2020-10-01 |  | LOR |  | 1 | 1 | 1 | 1 | 1 | 0.4 | 1.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 23 |  | 0 | 19 |  | 0 | 0 | 412702.5 | -412702.5 | Section Manager | Andrew Pritchard | 7250 | 45 | 326250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Section Manager | Barry Flutter | Commenced | 2020-01-01 | incl Approvals and Consents | LOR | [47 empty] | 23 |  | 0 | 11 |  | 0 | 0 | 259413 | -259413 | Section Manager2 | Barry Flutter | 7000 | 35 | 245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-02-01
PL | Possession and Trackwork Manager | Paul Thomas | Commenced | 2020-02-01 |  | VR |  | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 22 |  | 0 | 11 |  | 0 | 0 | 426178.5 | -426178.5 | Possession & Trackwork Manager | Paul Thomas | 10833.325 | 39 | 422499.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | M&E Delivery Manager | Ian Yoxall | Commenced | 2020-03-01 | Temporary Role in July '17 | VR | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2018-07-01: 1; 2018-08-01: 0; 2018-09-01: 0.5; 2018-10-01: 0.5; 2018-11-01: 0.5; 2018-12-01: 0.5; 2019-01-01: 0.5; 2019-02-01: 0.4; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1; 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1 | 4.9 |  | 0 | 12 |  | 0 | 0 | 265701.8 | -265701.8 | M&E Delivery Manager | TBC | 7999.3333 | 26 | 207982.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Project Engineer | Gerald Knight | Commenced | 2020-04-01 |  | LOR | [47 empty] | 23 |  | 0 | 13 |  | 0 | 0 | 293103 | -293103 | Project Engineer | Gerald Knights | 7250 | 42 | 304500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-04-01
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ENGINEERING | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Project Surveyor | Simon Roberts | Commenced | 2020-01-01 |  | LOR |  | 0.94 | 0.93 | 1 | 1 | 1 | 0.91 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1.04 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 22.62 |  | 0 | 10 |  | 0 | 0 | 192319.365 | -192319.365 | Project Surveyor | Simon Roberts | 5250 | 30 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Senior Engineer Structures | Lawrence Smith | Commenced | 2020-01-01 |  | LOR |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 24 |  | 0 | 10 |  | 0 | 0 | 229092 | -229092 | Senior Engineer Structures | Lawrence Smith | 6000 | 35 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Senior Engineer - Section 1 - 2 Highways &Track | Ged Geraghty | Commenced | 2020-10-01 |  | VR | [47 empty] | 23 |  | 0 | 19 |  | 0 | 0 | 375502.0607 | -375502.0607 | Senior Engineer Highways & Track (1-2) | Ged Geraghty | 7691.6667 | 45 | 346125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-10-01
ENG | Senior Engineer - Section 3 - 4 Highways &Track | Chris Mee | Commenced | 2019-04-01 |  | LOR | [47 empty] | 23 |  | 0 | 1 |  | 0 | 0 | 256044 | -256044 | Senior Engineer All Highways (3-4) | Christopher Mee | 8500 | 37 | 314500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-04-01
ENG | Senior Engineer - Section 5 - 6 Highways &Track | Joe Heptinstall | Commenced | 2020-01-01 | Joe Heptinstall from June | LOR | [47 empty] | 23 |  | 0 | 10 |  | 0 | 0 | 203824.5 | -203824.5 | Senior Engineer Highways & Track (5-6), Third Parties | TBC | 6000 | 27 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-01-01
ENG | Section Engineer Structures (Sec 1) East of Trafford Rd Bridge | Nathan Graham | Commenced | 2019-09-01 | Nathan Graham from June | LOR |  | 1 | 1 | 1 | 1 | 1 | 0.87 | 1.13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 23 |  | 0 | 7 |  | 0 | 0 | 179118.5 | -179118.5 | Section Engineer Structures Sect 1 | TBC | 5500 | 26.5 | 145750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Highways & Track (1-2) (inc. All Sections Acc'm wks & Demo) | Stuart Melia | Commenced | 2019-09-01 |  | VR | [47 empty] | 23 |  | 0 | 6 |  | 0 | 0 | 208157.4083 | -208157.4083 | Section Engineer Highways & Track (1-2)(inc all Sects - Acc Works) | Stuart Melia | 5500 | 38 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-09-01
ENG | Section Engineer Highways & Track (3-4) incl All Highways initially | Dale Barlow | Commenced | 2020-10-01 |  | VR |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 20 |  | 0 | 6 |  | 0 | 0 | 240883.5 | -240883.5 | Section Engineer Highways & Track (3-4) | Joe Heptinstall | 5500 | 45 | 247500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Highways & Track (3-4) | Thomas McDonnell | Commenced | 2019-06-01 | Same as Below | LOR |  | 0 |  |  |  | 0 | [7 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 12 |  | 0 | 19 |  | 0 | 0 | 92647.5 | -92647.5 | Section Engineer Highways/Track (3-4) | TBC | 5500 | 12 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Highways & Track (5-6) | Rick Judge | Commenced | 2019-09-01 |  | LOR |  | 0 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [15 empty] | 18 |  | 0 | 8 |  | 0 | 0 | 148236 | -148236 | Section Engineer Highways & Track (5-6) | TBC | 5500 | 28 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Structures (Sec 1) then follow on Track works | Andy Finn | Commenced | 2020-01-01 | Need Engineer ASAP | LOR |  | 1 | 0.95 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 22.95 |  | 0 | 10 |  | 0 | 0 | 185014.25 | -185014.25 | Engineer Section 1 Structures/Track | Nathan Graham | 5000 | 32 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Structures (Sec 1) - Agreed (with TK of TfGM) additional Engineer | Andrew Hawkes | Commenced | 2019-04-01 | Required Dec '17 | LOR | 2017-05-01: 0; 2017-09-01: 0; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1; 2020-01-01: 1 | 16 |  | 0 | 10 |  | 0 | 0 | 119318.75 | -119318.75 | Engineer Structures (Sec 1) - Agreed (with TK of TfGM) additional Engineer | TBC | 4671.3333 | 17 | 79412.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 1-2 (DAYS) | Lara McLeod | Commenced | 2020-02-01 |  | LOR |  | 0 | 0.96 | 1 | 1 | 1 | 1 | 0.78 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 21.74 |  | 0 | 11 |  | 0 | 0 | 266560.895 | -266560.895 | Engineer Highways & Track 1-2 (DAYS) | Andrew Finn | 4500 | 38 | 171000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 1-2 (NIGHTS) | Phil Berry | 2018-05-01 | 2019-04-01 | Required June '18 | VR | 2017-05-01: 0; 2017-09-01: 0; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1 | 11 |  | 0 | 4 |  | 0 | 0 | 75802.5 | -75802.5 | Engineer Highways & Track 1-2 (NIGHT) | On Hold | 5625 | 19 | 106875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 1-2 (Highway & Acc'm Workswks) | Ben Waring | Commenced | 2020-02-01 |  | LOR | [47 empty] | 23 |  | 0 | 11 |  | 0 | 0 | 171819 | -171819 | Engineer Highways & Track 3-4(Always Highway Works) | Benjamin Waring | 2750 | 30 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-02-01
ENG | Engineer Section 3 (Support) | Jack Wilkinson | Commenced | 2019-02-01 |  | VR | 2018-09-01: 0.5; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1 | 6.5 |  | 0 | 2 |  | 0 | 0 | 61011.6542 | -61011.6542 | Section Engineer Highways & Track (1-2)(inc all Sects - Acc Works) | Stuart Melia | 5500 | 38 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 3-4 (Highways) | Rory Major | Commenced | 2020-10-01 |  | LOR | [47 empty] | 23 |  | 0 | 19 |  | 0 | 0 | 259413 | -259413 | Engineer Highways & Track 3-4(Initial Accom Works)2 | TBC | 4500 | 12 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-10-01
ENG | Engineer Track - Routewide | Ross Jefferies | 2018-01-01 | 2019-09-01 |  | VR | 2017-09-01: 0; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1 | 10 |  | 0 | 7 |  | 0 | 0 | 80856 | -80856 | Engineer Highways & Track 3-4(Always Highway Works) | Benjamin Waring | 2750 | 30 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 3-4 | Liam O'Toole | Commenced | 2020-01-01 | Same as Below | LOR | 2017-05-01: 0; 2017-09-01: 0; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1; 2020-01-01: 1 | 13 |  | 0 | 10 |  | 0 | 0 | 116230.5 | -116230.5 | Engineer Highways & Track 3-4(Initial Accom Works) | Richard Judge | 4250 | 45 | 191250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 5-6 - graduate | Nicholas Waite | Commenced | 2019-07-01 | Need Engineer ASAP | LOR | 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1 | 19 |  | 0 | 4 |  | 0 | 0 | 193717.5 | -193717.5 | Engineer Highways & Track 5-6 (2) | TBC | 4500 | 23 | 103500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Site Engineer (Summer Placement) | TBC | Summer | 2019-07-01 | Summer Placement | LOR | 2017-05-01: 0; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 0; 2018-05-01: 1; 2018-09-01: 0; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1 | 3 |  | 0 | 3 |  | 0 | 0 | 13476 | -13476 | Engineer Site Placement | TBC | 2000 | 9 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Site Engineer (Summer Placement) | TBC | Summer | 2019-07-01 | Summer Placement | LOR | 2017-05-01: 0; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 0; 2018-05-01: 1; 2018-09-01: 0; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1 | 3 |  | 0 | 3 |  | 0 | 0 | 13476 | -13476 | Engineer Site Placement2 | TBC | 2000 | 9 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Cadet (Section 5&6) | Jack Ramsden | Commenced | 2019-04-01 | Cadet Extended until end of 2018 | LOR | [47 empty] | 19 |  | 0 | 6 |  | 0 | 0 | 44920 | -44920 | Cadet | Lauren Smith | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-09-01 to 2019-09-01
ENG | Cadet (Section 5&6) | Beth Hodskinson | Commenced | 2020-02-01 | Cadet Extended until end of 2018 | LOR | [47 empty] | 19 |  | 0 | 11 |  | 0 | 0 | 67380 | -67380 | Cadet | Lauren Smith | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-09-01 to 2020-02-01
ENG | Cadet / School Leaver | Haika Ahmad | 2018-05-01 | 2019-01-01 | Cadet Extended until end of 2018 | LOR | [47 empty] | 10 |  | 0 | 9 |  | 0 | 0 | 22460 | -22460 | Cadet | Lauren Smith | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-06-01; 2018-05-01; 2018-09-01 to 2019-12-01
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CONSTRUCTION MANAGEMENT | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Senior Construction Manager | Eric Pritchard | Commenced | 2019-07-01 |  | LOR | [47 empty] | 23 |  | 0 | 5 |  | 0 | 0 | 310790.25 | -310790.25 | Senior Construction Manager | Eric Pritchard | 10250 | 38 | 389500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-08-01
CON | Construction Manager (1-2) | Craig McNicoll | Commenced | 2020-02-01 |  | LOR | [47 empty] | 23 |  | 0 | 11 |  | 0 | 0 | 295910.5 | -295910.5 | Construction Manager (1-2) | Craig McNicoll | 7750 | 27 | 209250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-02-01
CON | Section Foreman (Sec 1 Structures Only) Apr - Jun '17 on Acc'm Works S3 | Steve Lewis | Commenced | 2019-08-01 | Transfer from Maintenance Aug '17 | LOR | 2017-05-01: 0; 2017-07-01: 0.25; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1 | 20.25 |  | 0 | 6 |  | 0 | 0 | 170134.5 | -170134.5 | Section Foreman (Sect 1 Struct Only) | Steven Lewis | 5500 | 25 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Section Foreman (1-2) Highways & Track (Acc'm Wks/ TPA in 2017) - Days | Paul Lennon | Commenced | 2019-10-01 |  | WKLY | 2017-05-01: 0; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1 | 18 |  | 0 | 7 |  | 0 | 0 | 182487.5 | -182487.5 | Section Foreman ((1-2) Highways & Tracks - Days | David Jones | 5438.3333 | 29 | 157711.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Section Foreman (3-4) All Highway Works in 2017 | Dave Jones | Commenced | 2020-10-01 | Replace Mark Pritchard | LOR | [47 empty] | 23 |  | 0 | 19 |  | 0 | 0 | 400911 | -400911 | Section Foreman (3-4) | Adrian Pritchard | 8500 | 45 | 382500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-10-01
CON | Section Foreman (5-6) | Chris Byrne | Commenced | 2019-06-01 | Weekly paid offer made for Staff | WKLY | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 0.64; 2017-08-01: 1; 2017-09-01: 1.29; 2017-10-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1 | 21.93 |  | 0 | 3 |  | 0 | 0 | 153980.145 | -153980.145 | Section Foreman (5-6) | TBC | 5438.3333 | 36 | 195780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Section Foreman (Track) | Graham Dales | 2018-01-01 | 2019-09-01 |  | VR | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1 | 15 |  | 0 | 6 |  | 0 | 0 | 235830 | -235830 | Section Foreman (Track) | Paul Harrison ????? | 5438.3333 | 31 | 168588.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Logistics Manager | Mick Hearons | Commenced | 2020-03-01 |  | LOR |  | 1 | 1 | 1 | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 23 |  | 0 | 12 |  | 0 | 0 | 235830 | -235830 | Logistics Manager | Michael Hearons | 6000 | 38 | 228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UTILITIES | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UTL | Utilities CAD Technician/ Engineer | Andy Clough | Commenced | 2019-12-01 |  | VR | [47 empty] | 23 |  | 0 | 9 |  | 0 | 0 | 259753.8744 | -259753.8744 | Utilities Engineer (2) | Andrew Clough | 4671.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-12-01
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMMERCIAL | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial Lead | Steven Dykes | Commenced | 2020-08-01 |  | LOR |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 22 |  | 0 | 17 |  | 0 | 0 | 416071.5 | -416071.5 | Commercial Lead | Andrew Donegan / Steve Dykes | 9500 | 42 | 399000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial Manager (3-6) | Jamie Rathbone | Commenced | 2020-03-01 |  | VR |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 23 |  | 0 | 12 |  | 0 | 0 | 431714.3285 | -431714.3285 | Commercial Manager (3-6) | Jamie Rathbone | 10768.3333 | 42 | 452270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Senior QS (1-2) | Peter Boyce | Commenced | 2019-04-01 |  | LOR |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 22 |  | 0 | 6 |  | 0 | 0 | 161431.25 | -161431.25 | Senior QS (1-2) | Peter Boyce | 6250 | 22 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | QS (1-2) | Jon McGuinness | Commenced | 2020-10-01 |  | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 0.87; 2017-11-01: 1.13; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1 | 23 |  | 0 | 2 |  | 0 | 0 | 247621.5 | -247621.5 | QS (1-2) | James Harper | 5498.9567 | 45 | 247453.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | QS (5-6) | James Harper | Commenced | 2019-09-01 |  | VR | [47 empty] | 23 |  | 0 | 6 |  | 0 | 0 | 182666.2122 | -182666.2122 | QS (5-6) | Jonathan McGuinness | 4892.3333 | 37 | 181016.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-09-01
COM | Assistant QS/ Data Input | Paul Adderley | Commenced | 2020-04-01 |  | LOR |  | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 24 |  | 0 | 17 |  | 0 | 0 | 93489.75 | -93489.75 | Assistant QS (Data Input) | Paul Adderley | 2000 | 39 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Assistant QS/ Data Input | Michael Bell | Commenced | 2019-11-01 | Mike Bell ??? July '17 ??? | LOR |  | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 20 |  | 0 | 12 |  | 0 | 0 | 78610 | -78610 | Assistant QS (Data Input)2 | TBC | 2000 | 24 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FINANCE & ACCOUNTS | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Financial Controller | Vaidyanathan Chellam | Commenced | 2020-07-01 |  | VR |  | 0.35 | 0.3 | 0.4 | 0.3 | 0.2 | 0.7 | 0.7 | 0.39 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [7 empty] | 6.54 |  | 0 | 1.6 |  | 0 | 0 | 124850.8224 | -124850.8224 | Financial Controller | Vaidyanathan Chellam | 13390.3033 | 4.2 | 56239.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Project Accountant | Darianne O'Driscoll | Commenced | 2019-10-01 |  | VR |  | 0.15 | 0.31 | 0.5 | 0.4 | 0.4 | 1 | 1 | 1.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 12.51 |  | 0 | 3.5 |  | 0 | 0 | 186511.8574 | -186511.8574 | Project Accountant | Katherine Shaw | 10170.3333 | 34.98 | 355758.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Project Accountant | Carol France | Commenced | 2020-04-01 |  | VR |  | 0.25 | 0.6 | 0.5 | 0.6 | 0.6 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.33 | 0.33 | 0.33 | [10 empty] | 13.05 |  | 0 | 5.99 |  | 0 | 0 | 85057.2778 | -85057.2778 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PROCUREMENT | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRO | Assistant Procurement Manager | Paul Disley | Commenced | 2019-09-01 | Replacement for Liane Holmes | LOR |  | 0.98 | 0.96 | 1 | 0.93 | 0.89 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 22.76 |  | 0 | 6 |  | 0 | 0 | 110098.92 | -110098.92 | Assistant Procurement Manager2 | Paul Taylor | 2500 | 17.04 | 42600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLANNING | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLA | Principle Planner | John Fitzimmons | Commenced | 2020-05-01 |  | LOR | [47 empty] | 23 |  | 0 | 14 |  | 0 | 0 | 270081.5 | -270081.5 | Principle Planner | John Fitzsimmons | 6500 | 40 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-05-01
PLA | Principle Planner | Sonja Leslie | Commenced | 2019-12-01 | moves to Utility Planner for 18 months | VR | 2017-05-01: 0; 2017-07-01: 0; 2017-09-01: 0; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1 | 15 |  | 0 | 9 |  | 0 | 0 | 184648.152 | -184648.152 | Planner | Sonja Leslie | 6716.6667 | 27 | 181350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLA | Assistant Planner | Duane Anderson | Commenced | 2019-08-01 |  | LOR | 2017-05-01: 0; 2017-07-01: 0.09; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1 | 20.09 |  | 0 | 5 |  | 0 | 0 | 125409.997 | -125409.997 | Assistant Planner | TBC | 4363.6667 | 24 | 104728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DIGITAL ENGINEERING | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE | BIM Digital Engineer | Chris Cox | Commenced | 2019-02-01 |  | VR | [47 empty] | 2 |  | 0 | 14 |  | 0 | 0 | 89600 | -89600 | bar: 2019-02-01 to 2020-05-01
DE | As Built - CAD Engineer | Joseph Brownell | Commenced | 2020-02-01 |  | VR | [5 empty] | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 17 |  | 0 | 14 |  | 0 | 0 | 140000 | -140000 | Digital Engineer | Mattew Anderton | 5500 | 2.6 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OFFICE & SITE SUPPORT | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Approvals and Consents Assistant/ Document Control | Faye Woollam | Commenced | 2020-04-01 | From 2CC in April '17 | LOR | [47 empty] | 23 |  | 0 | 13 |  | 0 | 0 | 131391 | -131391 | Approvals and Consents Assistant/ Document Control | Faye Woollam | 3250 | 29 | 94250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-04-01
OS | Office Manager | Adele Dunn | Commenced | 2020-04-01 | Currently at 2CC | LOR |  | 1 | 1 | 1 | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | [10 empty] | 23 |  | 0 | 9.9 |  | 0 | 0 | 184733.5 | -184733.5 | Office Manager | Adele Dunne | 4750 | 34.4 | 163400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Reception/ Administrator Document Controller | Jenni Patterson | Commenced | 2020-04-01 |  | VR | [47 empty] | 23 |  | 0 | 13 |  | 0 | 0 | 134807.6006 | -134807.6006 | Reception/ Administrator Document Controller | TBA Claire Heaton | 3900 | 39 | 152100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-04-01
OS | HSQE Support & Office Admin | Debra Dore | Commenced | 2019-12-01 |  | VR | [47 empty] | 23 |  | 0 | 9 |  | 0 | 0 | 119828.9783 | -119828.9783 | HSQE Support & Office Admin | Debra Dore | 2873 | 42 | 120666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-12-01
OS | Personal Assistant | Sarah Collett | Commenced | 2020-04-01 |  | VR | [47 empty] | 23 |  | 0 | 13 |  | 0 | 0 | 170164.5892 | -170164.5892 | Personal Assistant | Sarah Collett | 4126.5467 | 39 | 160935.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2020-04-01
OS | HSQE Manager | Adrian Rowe | Commenced | 2020-06-01 |  | VR |  | 0 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | [8 empty] | 20 |  | 0 | 14 |  | 0 | 0 | 308323.5096 | -308323.5096 | HSQE Manager | Adrian Rowe | 6708 | 38 | 254904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Environmental & Sustainability support | Lauren Smith | Commenced | 2019-12-01 | From 2CC | LOR |  | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 17 |  | 0 | 9 |  | 0 | 0 | 87594 | -87594 | Environmental & Sustainability support | Sarah Barnes | 4500 | 38 | 171000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Materials Engineer | Stephen McCluskey | Commenced | 2020-03-01 | Within the Materials Testing Costs | LOR |  | 0.95 | 0.91 | 0.77 | 0.54 | 0.78 | 0.71 | 0.71 | 0.7 | 0.75 | 0.78 | 0.74 | 0.79 | 1 | 0.77 | 0.8 | 0.77 | 0.87 | 0.82 | 0.81 | 0.82 | 0.83 | 0.81 | 0.78 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 18.21 |  | 0 | 12 |  | 0 | 0 | 203554.98 | -203554.98 | Materials Engineer | Stephen McCluskey | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Quality Manager | Mark Newman | Commenced | 2018-05-01 | Within the Materials Testing Costs | LOR | 2017-06-01: 0.67; 2017-07-01: 0.09; 2017-08-01: 0.13; 2017-09-01: 0.09; 2017-10-01: 0.09; 2017-12-01: 0.09; 2018-01-01: 0.1; 2018-03-01: 0.2; 2018-04-01: 0.17; 2018-06-01: 0.23; 2018-08-01: 0.4; 2018-11-01: 0.24; 2018-12-01: 0.22; 2019-01-01: 0.21; 2019-02-01: 0.19; 2019-03-01: 0.2 | 3.32 |  | 0 | 0 |  | 0 | 0 | 33853.5088 | -33853.5088 | Materials Engineer | Stephen McCluskey | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site generated contingency | [55 empty] | 1 |  | 0 | 0 | 420834 | -420834 | bar: 2018-03-01
| Staff Contingency allowance - generated to date (adjusted forecasts etc) | [54 empty] | -676592.847 | 0 |  | 0 | -676592.847 | -676592.847 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CRUMPSALL | [5 empty] | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CRU | Site Engineer | Wes Morse |  | 2020-02-01 | Wes Morse (then Crumpsall) | VR | [47 empty] | 12 |  | 0 | 11 |  | 0 | 0 | 223851.3333 | -223851.3333 | Section Engineer Hovis/ITV Nights | Wes Morse | 6875 | 28 | 192500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-10-01 to 2018-02-01; 2018-09-01 to 2020-02-01
CRU | Foreman | Arwyn Pritchard |  | 2020-01-01 | Weekly paid (Move to Crumpsall) | LOR | [47 empty] | 13 |  | 0 | 10 |  | 0 | 0 | 167888.5 | -167888.5 | Section Foreman (1-2) Accom Works, Highway & Track - Nights | Arwyn Pritchard | 5438.3333 | 24 | 130520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-09-01 to 2018-02-01; 2018-09-01 to 2020-01-01
CRU |  | Possession Management - item 2 |  |  | Currently at 2CC |  | 2017-09-01: 0; 2021-02-01: 1 | 0 |  | 0 | 1 |  | 0 | 0 | 156463.91 | -156463.91 | Office Manager | Adele Dunne | 4750 | 34.4 | 163400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CRU | [6 empty] | 2017-09-01: 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | Quality Control Inspector | Covered by Adrian Rowe |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ALLOWANCES | [52 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overtime Allowance | [52 empty] | 0 |  | 0 | 1 |  | 0 | 0 | 124086.636 | -124086.636 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2021-02-01
OS | Miscellaneous Staff Allocation |  |  |  |  | LOR |  | 0.9 | 0.79 | 0.81 | 1.85 | 4.19 | 3 | 1.1 | 1.22 | 0.6 | 0.42 | 0.78 | 1.11 | 1.8213 | 1.36 | 1.3 | 2.12 | 1.1 | 0.17 | 0.12 | 0.28478 | 0.17 | 2.15 | 1.5 | 1.8533 | 1.8063 | 1.7563 | 1.6438 | 1.5063 | 1.4413 | 1.3663 | 1.3038 | 1.2638 | 1.1888 | 0.9095 | 0.727 | 0.5995 | 0.3925 | 0.3275 | [8 empty] | 28.866 |  | 0 | 18.0855 |  | 0 | 0 | 328676.5297 | -328676.5297 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 - 28 week staff forecast reduction saving | [52 empty] | 0 |  | 0 | 1 |  | 0 | 0 | 890000 | -890000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2021-02-01
[54 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LEFT PROJECT | [5 empty] | 2017-09-01: 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Lead Design Manager | Gordon Reilly | Commenced | #NAME? |  | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 0.3; 2017-09-01: 0.05 | 3.35 |  | 0 | 0 |  | 0 | 0 | 25125 | -25125 | Lead Design Manager | Gordon Reilly | 7500 | 1 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Structures (Sec 1) - West of Trafford Rd Bridge | Mike Kelly | Commenced | 2019-04-01 | Required Jan '18 | LOR | 2017-05-01: 0; 2017-09-01: 0; 2017-11-01: 0.22; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 0.34 | 13.56 |  | 0 | 0 |  | 0 | 0 | 83753.34 | -83753.34 | Section Engineer Structures Sect 1 (2) | TBC | 5500 | 16 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DIR | Operations Director | Bryan Glass | Commenced | 2020-04-01 |  | LOR |  | 0.35 | 0.45 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 8.2 |  | 0 | 0 |  | 0 | 0 | 318958.25 | -318958.25 | Operations Director | Bryan Glass | 25016.3333 | 8.4 | 210137.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Stops (with Ged) | Barry Davies | 2018-10-01 | 2019-09-01 | Required Oct '18 | VR | 2017-05-01: 0; 2017-09-01: 0; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1 | 4 |  | 0 | 0 |  | 0 | 0 | 24706 | -24706 | Engineer Stops (with Ged) | TBC | 4500 | 28 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Stops (with Ged) | James Addy | 2019-01-01 | 2019-09-01 |  | VR | [47 empty] | 3 |  | 0 | 0 |  | 0 | 0 | 55593 | -55593 | bar: 2019-01-01 to 2019-03-01
COM | Commercial Manager (1-2) | Vic Hardy | Commenced | 2019-02-01 |  | LOR | [47 empty] | 23 |  | 0 | 0 |  | 0 | 0 | 245375.5 | -245375.5 | Commercial Manager (1-2) | John Hardy | 9500 | 45 | 427500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2019-03-01
UTL | Utilities Project Manager | Tony David Hanna | Commenced | 2018-09-01 |  | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 0.69 | 16.69 |  | 0 | 0 |  | 0 | 0 | 157440.108 | -157440.108 | Utilities Project Manager | David Hanna | 7750 | 25 | 193750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRO | Graduate Procurement Manager | Laura Walsh | Commenced | 2018-10-01 |  | LOR | 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 0.91; 2018-07-01: 1; 2018-08-01: 0.64; 2018-09-01: 0.57; 2018-10-01: 1 | 11.12 |  | 0 | 0 |  | 0 | 0 | 61094.2845 | -61094.2845 | QS (1-2) | James Harper | 5498.9567 | 45 | 247453.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CRU |  | Possession Management - item 1 |  |  | From 2CC in April '17 |  | 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Approvals and Consents Assistant/ Document Control | Faye Woollam | 3250 | 29 | 94250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Assistant Design Manager / Design Engineer | Robert Martin | #NAME? |  | Left the Project | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Assistant Design Manager | Robert Martin | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Traffic Management Manager | Run with GTM Lee Pilling | #NAME? |  | Within the TM Package Costs (fixed) | AGENCY | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Traffic Management Manager | Run with GTM Lee Pilling | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | Project Engineer | Dominic Pearse | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Project Engineer2 | Dominic Pearse | 11000 | 7 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UTL | Utilities Engineer | TBC | #NAME? |  | Jan '17 | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Utilities CAD Technician / Engineer | TBC | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UTL | Utilities Planner | Stuart Taylor | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Utilities Planner (2) | Stuart Taylor | 6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial Services | Mark Lawton | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Commercial Services | Mark Lawton | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial third party review | Neil Waspe | #NAME? |  |  | VR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Commercial third party review | Neil Waspe | 6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Senior QS (Feasibility Stage Only) | Dave Natrass | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Senior QS (Feasibility Stage Only) | Dave Natrass | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Senior QS (3-6) | No Longer Required | #NAME? |  |  | N/A | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Senior QS (3-6) | TBC | 6981 | 19 | 132639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Traffic Management QS | No Longer Required | #NAME? |  | Within the TM Direct Costs (remeasure) | N/A | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Traffic Management QS | TBC | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EST | Estimating | Gordon Thomas Ritchie | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Estimating | Gordon Thomas Ritchie | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EST | Estimating | David Laird | #NAME? |  | Assist and Replace Gordon | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Estimating2 | David Laird | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EST | Estimating Assistant | Adam Devitt | #NAME? |  | Adam leaves for Lima 02/12/16 | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Estimating Assistant | Adam Devitt | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRO | Assistant Procurement Manager | Liane Holmes | #NAME? |  | As discussed with Chris Kent | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Assistant Procurement Manager | Liane Holmes | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE | Digital Engineer | Lindsay Collier | #NAME? |  |  | LOR | 2017-05-01: 0; 2017-07-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Digital Engineer3 | Lindsay Collier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE | Digital Engineer | Jonathan Han | Commenced | #NAME? |  | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 0 | 4 |  | 0 | 0 |  | 0 | 0 | 20000 | -20000 | Digital Engineer2 | Jonathan Han | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Approvals and Consents Manager | Covered by Bary Flutter (Costs above) | #NAME? | #NAME? |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Approvals and Consents Manager | Covered by Bary Flutter (Costs above) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Construction Manager (3-6) | TBC | #NAME? | #NAME? | Mark Pritchard??? | TBC | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Construction Manager (3-6) | TBC | 7750 | 35 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Cadet | Previously Lauren Smith - TBC | Commenced | #NAME? | Cadet Extended until end of 2018 | LOR | [47 empty] | 6 |  | 0 | 0 |  | 0 | 0 | 12000 | -12000 | Cadet | Lauren Smith | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-10-01
OS | Quality Control Inspector | Covered by Adrian Rowe | #NAME? |  |  | VR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Quality Control Inspector | Covered by Adrian Rowe |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial Services | Peter Heston | Commenced | #NAME? |  | VR | 2017-05-01: 1; 2017-06-01: 0.5; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 3.14 | 9.64 |  | 0 | 0 |  | 0 | 0 | 120393.647 | -120393.647 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE | Assistant Digital Engineer | Chris Cox | Commenced |  |  | AECOM | 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Digital Engineer | Mattew Anderton | 5500 | 2.6 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tony Vaughan Sub Contract Costs | [5 empty] | 2017-04-01: 1; 2017-05-01: 0; 2017-09-01: 0 | 1 |  | 0 |  |  |  | 0 | 30055 | -30055 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE | Digital Engineer | Matt Anderton | Commenced | #NAME? |  | LOR | 2017-05-01: 1; 2017-06-01: 0.85; 2017-07-01: 0.27; 2017-08-01: 0; 2017-09-01: 0.09; 2017-10-01: 0.1 | 2.31 |  | 0 | 0 |  | 0 | 0 | 12705 | -12705 | Digital Engineer | Mattew Anderton | 5500 | 2.6 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRO | Assistant Procurement Manager (Materials) | Kate Atkinson | Commenced | #NAME? | Kate Atkinson arrived May '17 | LOR | [47 empty] | 9 |  | 0 | 0 |  | 0 | 0 | 38250 | -38250 | Assistant Procurement Manager (Materials) | LOR Central/ Kate Atkinson | 4250 | 17.04 | 72420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2018-01-01
PRO | Procurement Manager | Chris Kent | Commenced | #NAME? | As discussed with Chris Kent | VR | [47 empty] | 8 |  | 0 | 0 |  | 0 | 0 | 69615.8789 | -69615.8789 | Procurement Manager | Chris Kent | 9022 | 11 | 99242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-12-01
ENG | Engineer Structures (Sec 1) - Suspended Quay Only | TBC | 2018-05-01 | 2019-04-01 | Required Jan '18 | VR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Engineer Section 1 Structures/Suspended Slabs | TBC | 4500 | 16 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UTL | Utilities Planner | Sonja Leslie | Commenced | #NAME? |  | VR | [47 empty] | 8 |  | 0 | 0 |  | 0 | 0 | 54808 | -54808 | Utilities Planner | Sonja Leslie | 6716.6667 | 8 | 53733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-12-01
UTL | Utilities Engineer | Andrew Hawkes - now in Engineering | Commenced | #NAME? | Then onto Section Engineer (TPL) | LOR | [47 empty] | 5 |  | 0 | 0 |  | 0 | 0 | 26250 | -26250 | Utilities Engineer | Andrew Hawkes | 5250 | 8 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-09-01
OS | Assistant Office manager - Labour | TBC | #NAME? | #NAME? |  | TBC | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Assistant Office manager - Labour | TBC | 2873 | 20 | 57460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 5-6 | TBC | 2018-05-01 | 2020-05-01 |  | LOR | 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Engineer Highways & Track 5-6 | TBC | 4500 | 37 | 166500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Assistant Office manager - Plant | TBC | #NAME? | #NAME? |  | TBC | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Assistant Office manager - Plant | TBC | 2873 | 20 | 57460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 5-6 | Previously Rick Judge | Commenced | 2017-09-01 |  | LOR | [47 empty] | 5 |  | 0 | 0 |  | 0 | 0 | 22500 | -22500 | Engineer Highways & Track 5-6 | TBC | 4500 | 37 | 166500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-09-01
CON | Section Foreman (3-4) | TBC | #NAME? | #NAME? | Same as below | LOR | 2017-05-01: 0; 2017-09-01: 1 | 1 |  | 0 | 0 |  | 0 | 0 | 5500 | -5500 | Section Foreman (3-4) (2) | TBC | 5438.3333 | 15 | 81575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Engineer Highways & Track 4 incl Structures | Thomas McDonnell | Commenced | #NAME? | Same as Above | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 0; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1 | 11 |  | 0 | 0 |  | 0 | 0 | 49500 | -49500 | Engineer Highways & Track 4 Structures | Tom McDonald | 4500 | 14 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Commercial Placement | TBC | Commenced | #NAME? | 3 months per year student | TBC | 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Commercial Placement | TBC | 2000 | 9 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | Core Commercial resource | Garry Richards | Commenced | #NAME? |  | LOR | 2017-05-01: 0; 2017-06-01: 0.2; 2017-07-01: 0; 2017-09-01: 0 | 0.2 |  | 0 | 0 |  | 0 | 0 | 1350 | -1350 | Core Commercial | Garry Richards | 6750 | 7.6 | 51300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | QS (3-4) | TBC | #NAME? | #NAME? |  | TBC | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | QS (3-4) | TBC | 4892.3333 | 35 | 171231.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Section Foreman (3-4) Structures | TBC | #NAME? | #NAME? | Same as above | WKLY | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2018-03-01: 1; 2018-04-01: 1 | 2 |  | 0 | 0 |  | 0 | 0 | 11000 | -11000 | Section Foreman (3-4) Structures | TBC | 5438.3333 | 12 | 65260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Adjustment for cost to date and forecast to complete | [5 empty] | 2017-09-01: 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inflation 2017 - 2018 | [52 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inflation 2018 - 2019 | [52 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inflation 2019 - 2020 | [52 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inflation 2020 - 2021 | [52 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | DCM E&M Interface Manager | Pete Tomlinson / or other | 2019-04-01 | 2020-10-01 |  | LOR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | DCM E&M Interface Manager | Peter Tomlinson | 10250 | 18.5 | 189625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL | OLE Delivery Manager | TBC | 2019-02-01 | 2020-06-01 | Required Feb '18 | TBC | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | OLE Delivery Manager | TBC | 7999.3333 | 19 | 151987.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | Section Foreman (1-2) Accm Wks, Highway & Track - Nights | Arwyn Pritchard | Commenced | 2019-06-01 | Weekly paid (Move to Crumpsall) | WKLY | [47 empty] | 9 |  | 0 | 0 |  | 0 | 0 | 49500 | -49500 | Section Foreman (1-2) Accom Works, Highway & Track - Nights | Arwyn Pritchard | 5438.3333 | 24 | 130520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-08-01; 2018-04-01 to 2018-08-01
CRU | Site Engineer | Liam O'Toole |  |  |  | LOR | [47 empty] | 7 |  | 0 | 0 |  | 0 | 0 | 42000 | -42000 | Approvals and Consents Manager | Covered by Bary Flutter (Costs above) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-08-01 to 2018-02-01
CON | OLE Supervisor | TBC | 2018-11-01 | 2020-08-01 |  | VR | 2017-05-01: 0; 2017-09-01: 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | OLE Supervisor | TBC | 5438.3333 | 22 | 119643.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Structures (4) | Barry Davies (S Eng Rate) | Commenced |  | Same as Above | VR | 2017-05-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 1; 2017-11-01: 1; 2018-01-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1 | 7 |  | 0 | 0 |  | 0 | 0 | 38500 | -38500 | Section Engineer Structures (3-4) | TBC | 5500 | 13 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS | Senior Materials Engineer | William Halley | Commenced | 2020-06-01 | Within the Materials Testing Costs | LOR | 2017-05-01: 0.13; 2017-06-01: 0.17; 2017-07-01: 0.04; 2017-08-01: 0.04; 2017-09-01: 0.02; 2017-10-01: 0.02; 2017-11-01: 0.04; 2017-12-01: 0.07; 2018-01-01: 0.05; 2018-02-01: 0.003; 2018-03-01: 0.02; 2018-04-01: 0.03; 2018-05-01: 0.2; 2018-08-01: 0 | 0.833 |  | 0 | 0 |  | 0 | 0 | 7563.64 | -7563.64 | Senior Materials Engineer | William Halley | 0 | 6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | Section Engineer Hovis (ITV) Acc'm wks) Nights | Wes Morse | Commenced | 2019-10-01 | Wes Morse (then Crumpsall) | VR | [47 empty] | 11 |  | 0 | 0 |  | 0 | 0 | 95333.3333 | -95333.3333 | Section Engineer Hovis/ITV Nights | Wes Morse | 6875 | 28 | 192500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-05-01 to 2017-09-01; 2018-03-01 to 2018-08-01
DE | Assistant Digital Engineer | Giedre Jurkonyte | Commenced | #NAME? | Giedre to be replaced in Summer '17 | LOR | 2017-05-01: 1; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 0.74 | 4.74 |  | 0 | 0 |  | 0 | 0 | 20145 | -20145 | Assistant Digital Engineer | Giedre Jurkonyte | 4250 | 42 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[54 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[54 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | LOR | [47 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[54 empty] | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[54 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2020-05-01
| Mpact | [5 empty] | 2 | 54.65 | 57.14 | 57.76 | 63.2 | 67.2138 | 61.47 | 67.92 | 66.71 | 65.55 | 62.253 | 62.79 | 64.14 | 69.0713 | 67.35 | 67.45 | 67.08 | 67.38 | 66.64 | 65.96 | 66.1448 | 65.41 | 67.98 | 67.88 | 65.9532 | 67.1063 | 65.0563 | 63.6437 | 59.8063 | 57.7413 | 49.6663 | 46.1037 | 44.5637 | 39.4887 | 32.0395 | 24.557 | 19.4295 | 11.5925 | 7.9275 | 7.1 | 7 | 5 | 5 | 0 | 0 | 0 | 3 |  |  | -676592.847 |  |  | 0 | -676592.847 | 22554526.2766 | -23231119.1236 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DIRECTORS |  |  |  |  | DIR | 0 | 0.55 | 0.65 | 0.6 | 0.6 | 0.6 | 0.5 | 0.5 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| PROJECT DELIVERY |  |  |  |  | PL | 0 | 7.45 | 7.39 | 7.8 | 6.81 | 6.3238 | 5.7 | 6.81 | 6.3 | 6.3 | 6.3 | 6.3 | 6.29 | 6.3 | 6.29 | 7.6 | 6.4 | 6.9 | 6.9 | 7.04 | 7.07 | 7.11 | 6.98 | 7.55 | 7.8 | 8 | 8 | 7.7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 1.6 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | 15363709.99 | Actual Coins Cost
| ENGINEERING |  |  |  |  | ENG | 0 | 14.94 | 15.84 | 17 | 17 | 19 | 18.78 | 18.93 | 19 | 20 | 19 | 21 | 21 | 26 | 25.04 | 24 | 24 | 24.5 | 25 | 25 | 25 | 24.34 | 24 | 24 | 23 | 24 | 23 | 23 | 19 | 19 | 16 | 14 | 13 | 12 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
| CONSTRUCTION MANAGEMENT |  |  |  |  | CON | 0 | 6 | 6 | 5.89 | 7 | 8.29 | 6 | 7 | 6 | 8 | 8 | 9 | 10 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 6 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  |  |  | Adjustments;
| UTILITIES |  |  |  |  | UTL | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.69 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 433265 | Staff transfer from Weekly Paid - to Week 14
| COMMERCIAL |  |  |  |  | COM | 0 | 7 | 7.7 | 7 | 10 | 9 | 8.87 | 9.13 | 10.14 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3239.5 | Safety Critical Staff
| FINANCE & ACCOUNTS |  |  |  |  | FIN | 0 | 0.75 | 1.21 | 1.4 | 1.3 | 1.2 | 2.7 | 2.7 | 2.64 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.3 | 1.3 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.6 | 0.6 | 0.6 | 0.43 | 0.43 | 0.43 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | -69551.68 | VolkerRail - Recharge Incorrectly Allocated (June 2018 - 318)
| CRUMPSALL |  |  |  |  | CRU | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 117365 | Nigel Laing from Sub-Contract
| PROCUREMENT |  |  |  |  | PRO | 0 | 2.98 | 2.96 | 3 | 2.93 | 2.89 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1.91 | 2 | 1.64 | 1.57 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 39868 | VR Agency staff - Accrual
| PLANNING |  |  |  |  | PLA | 0 | 1 | 1 | 1.09 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30055 | Tony Vaughan from Sub-Contract
| DIGITAL ENGINEERING |  |  |  |  | DE | 0 | 3 | 2.85 | 2.27 | 2 | 0.83 | 0.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | VR Agency staff - Accrual
| OFFICE & SITE SUPPORT |  |  |  |  | OS | 0 | 6.98 | 7.54 | 7.71 | 8.56 | 11.08 | 7.82 | 9.85 | 9.08 | 8.5 | 8.203 | 8.74 | 9.1 | 10.0213 | 9.36 | 9.1 | 10.29 | 8.97 | 7.99 | 8.17 | 8.3248 | 8.21 | 10.15 | 9.48 | 9.8533 | 9.8063 | 9.7563 | 9.6438 | 9.5062 | 9.4413 | 9.3663 | 9.3038 | 8.7637 | 6.6888 | 6.4095 | 5.927 | 4.7995 | 0.8925 | 0.8275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[56 empty] | 15917950.81 | Coins Prime Cost to Date (November 17) | bar: 2020-05-01
| TOTAL STAFF | [5 empty] | 0 | 43.52 | 46.42 | 47.45 | 53.16 | 56.3638 | 54.35 | 60.88 | 58.5 | 61.5 | 60.25 | 59.77 | 60.11 | 65.8713 | 64.35 | 64.45 | 64.08 | 67.38 | 66.64 | 65.96 | 66.1448 | 65.41 | 67.98 | 67.88 | 65.9532 | 67.1063 | 65.0563 | 63.6437 | 59.8063 | 57.7413 | 49.6663 | 46.1037 | 44.5637 | 39.4887 | 32.0395 | 24.557 | 19.4295 | 11.5925 | 7.9275 | 7.1 | 7 | 5 | 5 | 0 | 0 | 0 | 3
[56 empty] | -16594543.657 | Difference between Forecast Rates and Actual | bar: 2017-05-01; 2020-05-01
JOINT VENTURE STAFF SPLIT | bar: 2020-05-01
| LAING O'ROURKE |  |  |  |  | LOR | 0 | 39.05 | 35.35 | 35.01 | 39.46 | 48.52 | 35.25 | 44.18 | 42.76 | 42.2 | 41.95 | 42.47 | 42.81 | 47.5712 | 45.05 | 43.65 | 44.48 | 44.78 | 43.54 | 42.86 | 43.0448 | 42.31 | 43.88 | 43.18 | 42.4533 | 43.4062 | 42.3563 | 41.9437 | 39.1063 | 37.0413 | 32.9663 | 31.9038 | 30.3638 | 28.2888 | 21.0095 | 15.527 | 12.3995 | 7.3925 | 6.3275 | 6 | 6 | 4 | 4 | 0 | 0 | 0 | 0 |  | Note: Weekly labour cost transfer for the following staff;
| VOLKER RAIL |  |  |  |  | VR | 1 | 9.25 | 9.71 | 11.4 | 12.3 | 16.2 | 13.7 | 15.7 | 14.64 | 17.2 | 16.2 | 15.2 | 15.2 | 16.2 | 17.2 | 18.2 | 17.2 | 20.2 | 20.7 | 20.7 | 20.7 | 20.7 | 21.7 | 22.3 | 21.1 | 21.1 | 20.1 | 20.1 | 19.1 | 19.1 | 15.1 | 13.6 | 13.6 | 10.6 | 10.43 | 8.43 | 6.43 | 3.6 | 1.6 | 1.1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1. Paul Lennon S1 and 2
| TO BE CONFIRMED |  |  |  |  | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2. Arwyn Pritchard S1 and 2 Nights
| CURRENT LOR % | [6 empty] | 80.85% | 78.45% | 75.44% | 76.24% | 74.97% | 72.01% | 73.78% | 74.49% | 71.04% | 72.14% | 73.64% | 73.8% | 74.6% | 72.37% | 70.57% | 72.11% | 68.91% | 67.78% | 67.43% | 67.53% | 67.15% | 66.91% | 65.94% | 66.8% | 67.29% | 67.82% | 67.6% | 67.19% | 65.98% | 68.59% | 70.11% | 69.07% | 72.74% | 66.83% | 64.81% | 65.85% | 67.25% | 79.82% | 84.51% | 85.71% | 80% | 80% | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 3. Chris Byrne S5 and 6
| CURRENT VR % | [6 empty] | 19.15% | 21.55% | 24.56% | 23.76% | 25.03% | 27.99% | 26.22% | 25.51% | 28.96% | 27.86% | 26.36% | 26.2% | 25.4% | 27.63% | 29.43% | 27.89% | 31.09% | 32.22% | 32.57% | 32.47% | 32.85% | 33.09% | 34.06% | 33.2% | 32.71% | 32.18% | 32.4% | 32.81% | 34.02% | 31.41% | 29.89% | 30.93% | 27.26% | 33.17% | 35.19% | 34.15% | 32.75% | 20.18% | 15.49% | 14.29% | 20% | 20% | #DIV/0! | #DIV/0! | #DIV/0!
| LAING O'ROURKE FORECAST COST | [5 empty] | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: 287083.0134; 2017-12-01: 289996; 2018-01-01: 282294; 2018-02-01: 284419; 2018-03-01: 278874.0373; 2018-04-01: 279038.834; 2018-06-01: 279665.3467
| LAING O'ROURKE ACTUAL COST | [5 empty] | 2017-05-01: 247538.17; 2017-06-01: 273124.63; 2017-07-01: 259568.59; 2017-08-01: 274173.86; 2017-09-01: 312279.66; 2017-10-01: 300449.65; 2017-11-01: 285424.55; 2017-12-01: 347277.03; 2018-01-01: 287975.5; 2018-02-01: 288917; 2018-03-01: 258129.8183; 2018-04-01: 287360.03; 2018-06-01: 301958.95
| DIFFERENCE (£) | [5 empty] | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: 1658.4634; 2017-12-01: -57281.03; 2018-01-01: -5681.5; 2018-02-01: -4498; 2018-03-01: 20744.219; 2018-04-01: -8321.196; 2018-06-01: -22293.6033
| DIFFERENCE (%) | [5 empty] | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: 0.5777%; 2017-12-01: -19.75%; 2018-01-01: -2.013%; 2018-02-01: -1.581%; 2018-03-01: 7.439%; 2018-04-01: -2.982%; 2018-06-01: -7.972%
| VOLKER RAIL FORECAST COST | [5 empty] | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: #REF!; 2017-12-01: 156264; 2018-01-01: 123189.6877; 2018-02-01: 112206; 2018-03-01: 112205.9877; 2018-04-01: 116705.9877; 2018-06-01: 130177.1627
| VOLKER RAIL ACTUAL COST |  |  |  | 425.8 |  | 2017-05-01: 78239.64; 2017-06-01: 96334.09; 2017-07-01: 94645.27; 2017-08-01: 80902.6; 2017-09-01: 114748.34; 2017-10-01: 116550.84; 2017-11-01: 119741.8; 2017-12-01: 129840.16; 2018-01-01: 100361.53; 2018-02-01: 110096; 2018-04-01: 161557.3; 2018-06-01: 112425.14
| DIFFERENCE (£) |  |  |  | 432.7 |  | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: #REF!; 2017-12-01: 26423.84; 2018-01-01: 22828.1577; 2018-02-01: 2110; 2018-03-01: 112205.9877; 2018-04-01: -44851.3123; 2018-06-01: 17752.0227
| DIFFERENCE (%) |  |  |  | 441.4 |  | 2017-05-01: #REF!; 2017-06-01: #REF!; 2017-07-01: #REF!; 2017-08-01: #REF!; 2017-09-01: #REF!; 2017-10-01: #REF!; 2017-11-01: #REF!; 2017-12-01: 16.91%; 2018-01-01: 18.53%; 2018-02-01: 1.88%; 2018-03-01: 100%; 2018-04-01: -38.43%; 2018-06-01: 13.64%
454