## Overall Summary
Summary of EF8
 | time axis 2018-08-01 to 2022-03-01
 | time axis 2018-08-01 to 2022-03-01
CODE | DEPARTMENTS/ SUBPROJECTS | EF8 | CTD @ P11 | CTG | Total | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
GENERAL MANAGEMENT
A | STAFF | 47812.3733 | 27644.7322 | 20167.6411 | 47812.3733 | 23844.1798 | 617.3834 | 640.2754 | 635.2564 | 644.0304 | 644.0304 | 619.5764 | 639.5544 | 1073.1076 | 930.7717 | 907.6717 | 915.6717 | 930.6027 | 844.0627 | 831.7627 | 831.7627 | 831.7627 | 830.3547 | 818.0547 | 736.2047 | 742.3547 | 697.9547 | 678.3547 | 678.3547 | 678.3547 | 619.6547 | 576.5547 | 542.9497 | 508.0997 | 432.7737 | 401.9037 | 392.2537 | 372.0437 | 355.6157 | 331.3257 | 317.5257 | 315.3257 | 309.1657 | 55.332 | 20.2 | 20.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47812.3733
| LAB | 1995.0053 | 1274.1657 | 720.8396 | 1995.0053 | 1103.1657 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 37.2896 | 38.1 | 38.1 | 38.1 | 38.1 | 33.1 | 28.1 | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 16.95 | 16.95 | 16.95 | 13.35 | 15.35 | 15.35 | 15.35 | 15.35 | 15.35 | 15.35 | 13.35 | 9.75 | 9.75 | 33.75 | 33.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995.0053
| PLANT | 739.2659 | 599.9826 | 139.2834 | 739.2659 | 583.0396 | 2.613 | 2.866 | 2.866 | 2.866 | 2.866 | 2.866 | 2.866 | 3.8024 | 3.466 | 3.466 | 3.466 | 3.466 | 2.786 | 2.786 | 2.786 | 3.586 | 3.586 | 3.586 | 3.273 | 3.273 | 3.273 | 3.273 | 3.273 | 3.273 | 3.273 | 4.053 | 3.993 | 3.993 | 3.933 | 9.933 | 3.933 | 5.433 | 3.933 | 6.88 | 6.88 | 6.88 | 12.88 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739.2659
| MAT | 745.4538 | 391.7003 | 353.7535 | 745.4538 | 359.1403 | 5 | 8.2 | 7.96 | 2.2 | 7 | 2.2 | 2.14 | -20.9865 | 131.92 | 8.9 | 4.9 | 4.9 | 5.8 | 6.9 | 10.9 | 10.66 | 4.9 | 29.8 | 4.9 | 4.34 | 12.34 | 4.99 | 3.97 | 7.91 | 3.97 | 4.81 | 7.91 | 1.91 | 1.91 | 8.81 | 28.51 | 1.91 | 7.91 | 1.88 | 2.78 | 2.13 | 28.13 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 745.4538
| SUBCON | 4330.7135 | 2676.2265 | 1654.487 | 4330.7135 | 2319.3715 | 76.6 | 53.6 | 53.6 | 53.6 | 53.6 | 65.855 | 65.855 | 17.0605 | 57.4432 | 59.223 | 90.9692 | 46.968 | 45.1882 | 46.968 | 122.2977 | 124.0775 | 65.1882 | 46.968 | 45.1882 | 46.968 | 45.1882 | 46.968 | 45.1882 | 46.968 | 45.1882 | 49.968 | 41.0688 | 42.8486 | 41.0688 | 68.8486 | 41.0688 | 39.8486 | 38.0688 | 39.8486 | 38.0688 | 39.8486 | 64.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4330.7135
| MISC | 4816.9879 | 3808.9494 | 1008.0385 | 4816.9879 | 3610.1264 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 34.283 | 32.908 | 165.2765 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 34.283 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.908 | 32.158 | 32.158 | 32.158 | 30.908 | 30.158 | 21.158 | 19.398 | 18.575 | 13.66 | 13.28 | 12.98 | 12.68 | 12.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4816.9879
| WAO | 2572.2771 | 1492.537 | 1079.7401 | 2572.2771 | 1206.207 | 39.908 | 91.795 | 39.278 | 38.928 | 38.578 | 37.843 | 37.843 | -43.4995 | 49.3817 | 44.865 | 45.215 | 45.915 | 42.765 | 42.415 | 42.415 | 46.5817 | 42.24 | 41.19 | 38.565 | 38.915 | 36.815 | 36.465 | 36.465 | 40.6317 | 34.015 | 31.915 | 29.99 | 29.64 | 27.64 | 29.0067 | 24.49 | 23.15 | 22.45 | 20.7 | 27.9833 | 19.475 | 19.085 | 15.0333 | 17.6167 | 42.3667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2572.2771
|  | 63012.0768 | 37888.2936 | 25123.7832 | 63012.0768 | 33025.2302 | 802.9124 | 858.1444 | 800.3684 | 803.0324 | 807.4824 | 791.1234 | 809.6664 | 1232.0505 | 1243.9905 | 1095.1337 | 1131.2298 | 1102.8597 | 1006.6098 | 991.8397 | 1067.5443 | 1072.6758 | 1002.2768 | 995.6067 | 884.1388 | 891.8587 | 851.5788 | 826.0587 | 817.1088 | 826.9953 | 755.2088 | 712.8087 | 673.4195 | 632.7493 | 552.8335 | 555.01 | 525.0035 | 476.3103 | 454.9875 | 423.6643 | 415.9678 | 430.0893 | 479.7595 | 74.3653 | 37.8167 | 62.5667 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 63012.0768 | 0
ENGINEERING
B | STAFF | 18995.4832 | 13809.0002 | 5186.483 | 18995.4832 | 12205.1413 | 262.1923 | 267.5623 | 282.5123 | 275.6773 | 273.5973 | 242.3173 | 236.1673 | 807.7867 | 254.745 | 252.437 | 252.437 | 203.187 | 197.162 | 197.162 | 195.512 | 192.812 | 189.12 | 189.12 | 189.12 | 189.12 | 176.82 | 165.31 | 162.6 | 158.2 | 145.9 | 138.25 | 138.25 | 113.47 | 87.525 | 79.3 | 50.105 | 24.985 | 24.985 | 24.985 | 24.985 | 24.985 | 24.985 | 24.985 | 24.985 | 24.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18995.4832
| LAB | 297.7472 | 272.9367 | 24.8104 | 297.7472 | 272.9367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297.7472
| PLANT | 287.8753 | 274.2678 | 13.6075 | 287.8753 | 274.2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6075 | 40 | 3 | 3 | -38 | 3 | -149 | 3 | 130 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.8753
| MAT | 190.5602 | 183.8472 | 6.713 | 190.5602 | 274.5602 | 3 | 3 | 3 | 3 | 3 | -105.713 | 3 | 3.713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.5602
| SUBCON | 59600.4139 | 54481.6266 | 5118.7873 | 59600.4139 | 51592.7188 | 773.1133 | 490.4037 | 451.9936 | 418.2563 | 377.0054 | 378.1355 | 343.9468 | 537.734 | 539.8308 | 515.9254 | 506.4026 | 470.6044 | 347.1111 | 258.1445 | 203.0642 | 155.0651 | 152.6856 | 139.4056 | 122.9718 | 123.0618 | 121.6617 | 110.5295 | 109.0466 | 84.077 | 61.0723 | 57.8818 | 21.6373 | 2.5 | 2.5 | 2.5 | 2.5 | 7.5 | 11.0053 | 18.5974 | 17.9278 | 16.1223 | 15.4527 | 16.1223 | 10.1995 | 7.5 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 59600.4139
| MISC | 2284.305 | 2276.077 | 8.228 | 2284.305 | 2276.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284.305
| WAO | 1239.3701 | 1051.938 | 187.4321 | 1239.3701 | 952.2281 | 16.2884 | 16.7265 | 17.7375 | 17.165 | 17.165 | 14.6275 | 14.2905 | -19.5345 | 12.0928 | 12.0614 | 11.7474 | 10.0328 | 9.8529 | 9.8529 | 9.8215 | 9.5075 | 9.476 | 9.476 | 9.162 | 8.848 | 7.46 | 6.7861 | 6.763 | 6.5831 | 6.1446 | 5.7521 | 5.4381 | 4.6522 | 4.3565 | 3.537 | 1.9975 | 1.6191 | 1.6191 | 1.3051 | 1.3051 | 1.3051 | 1.3051 | 1.3051 | 1.3051 | 0.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239.3701
|  | 82895.7549 | 72349.6936 | 10546.0613 | 82895.7549 | 67847.93 | 1054.594 | 777.6925 | 755.2434 | 714.0986 | 670.7678 | 529.3674 | 597.4047 | 1378.345 | 846.6685 | 783.4237 | 773.5869 | 645.8242 | 557.1259 | 316.1593 | 411.3976 | 487.3846 | 354.2817 | 338.0016 | 321.2538 | 321.0299 | 305.9417 | 282.6256 | 278.4097 | 248.8601 | 213.1168 | 201.8839 | 165.3254 | 120.6222 | 94.3815 | 85.337 | 54.6025 | 34.1041 | 37.6094 | 44.8875 | 44.2179 | 42.4124 | 41.7428 | 42.4124 | 36.4896 | 32.6911 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 82895.7549 | 0
BATTERSEA STATION
C | STAFF | 13341.4208 | 8963.9865 | 4377.4343 | 13341.4208 | 7242.8478 | 254.5526 | 262.8086 | 274.3411 | 302.8765 | 323.4109 | 303.149 | 293.5048 | -493.3155 | 209.932 | 209.932 | 198.127 | 196.132 | 196.132 | 196.132 | 196.132 | 193.186 | 159.927 | 155.812 | 155.812 | 155.812 | 207.6265 | 207.6265 | 207.6265 | 207.6265 | 205.8034 | 201.5495 | 152.938 | 152.938 | 152.938 | 152.938 | 152.938 | 150.938 | 52.938 | 52.938 | 30.938 | 32.938 | 30.938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13341.4208
| LAB | 32841.9144 | 18805.1956 | 14036.7188 | 32841.9144 | 15168.6207 | 611.8973 | 626.9522 | 631.4151 | 601.1009 | 582.5998 | 582.6097 | 736.7506 | -345.7288 | 702.2217 | 833.4252 | 1397.2401 | 1035.2805 | 1223.1968 | 932.6033 | 827.4367 | 528.9852 | 451.8479 | 133.1276 | 482.1191 | 493.5969 | 427.0255 | 389.6078 | 393.7398 | 381.1142 | 381.1142 | 458.1517 | 520.4027 | 337.8104 | 251.2718 | 157.2128 | 143.6125 | 143.6125 | 143.6125 | 143.6125 | 143.6125 | 143.6125 | 45.4901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32841.9144
| PLANT | 13410.8439 | 10658.04 | 2752.8039 | 13410.8439 | 8281.7927 | 392.9667 | 394.6193 | 411.1202 | 381.7715 | 360.1991 | 435.5706 | 374.7321 | -804.1906 | 227.4183 | 168.7803 | 204.6856 | 170.6596 | 171.3938 | 122.1602 | 173.8275 | 95.083 | 81.7838 | 7.8029 | 141.234 | 167.8202 | 164.9083 | 137.1876 | 137.3684 | 130.9036 | 152.1808 | 161.1293 | 217.4404 | 56.1499 | 50.4854 | 38.2458 | 41.3119 | 31.1097 | 26.2771 | 26.2771 | 26.2771 | 26.2771 | 8.3461 | 0 | 0 | 0 | 5.9125 | 5.9125 | 5.9125 | 0 | 0 | 0 | 0 | 13410.8439
| MAT | 29830.7771 | 22339.9902 | 7490.7868 | 29830.7771 | 18902.7549 | 502.2138 | 515.4644 | 516.7859 | 529.1744 | 658.8446 | 714.7522 | 713.4624 | -1019.5225 | 562.8648 | 684.1028 | 896.5392 | 768.7738 | 854.9243 | 679.7493 | 788.489 | 432.6891 | 318.9389 | 102.5095 | 273.7298 | 268.3826 | 174.0544 | 154.8341 | 128.8872 | 115.102 | 162.8908 | 195.9681 | 151.6542 | 9.304 | 9.0631 | 8.6295 | 8.6295 | 8.6295 | 8.6295 | 8.6295 | 8.6295 | 8.6295 | 2.4104 | 0 | 0 | 0 | 0.19302 | 0.19302 | 0.19302 | 0 | 0 | 0 | 0 | 29830.7771
| SUBCON | 107271.9369 | 50864.1136 | 56407.8233 | 107271.9369 | 46243.8325 | 709.0097 | 730.925 | 513.8643 | 390.0172 | 680.7475 | 1595.7174 | 1805.9791 | 3922.0169 | 1494.9561 | 2345.69 | 2774.7696 | 3325.6813 | 2927.674 | 3224.7388 | 3556.9133 | 4074.3704 | 2358.4012 | 2390.7074 | 1050.2664 | 2479.75 | 2411.2805 | 2120.9959 | 2215.4997 | 1994.4923 | 1934.5692 | 1839.0248 | 2042.2684 | 1677.9265 | 271.5396 | 360.3789 | 453.8809 | 265.9738 | 117.6415 | 68.6415 | 659.6384 | 181.3896 | 60.7672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107271.9369
| MISC | 3760.7322 | 3511.431 | 249.3013 | 3760.7322 | 3348.1485 | 0 | 0 | 1.9769 | 27.677 | 66.1027 | 67.5259 | 52.2118 | 107.4179 | 9.2206 | 9.6277 | 10.2529 | 10.2156 | 10.014 | 8.8552 | 8.8651 | 0.67037 | 0.80075 | 0.04942 | 1.5355 | 1.5355 | 1.5355 | 1.5355 | 1.5355 | 1.5355 | 1.5355 | 1.5355 | 1.4298 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.79543 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3760.7322
| WAO | 1575.4393 | 1038.6293 | 536.81 | 1575.4393 | 805.0404 | 29.4938 | 28.1818 | 30.6796 | 39.2182 | 49.3839 | 56.6317 | 54.3809 | -134.5764 | 24.1463 | 28.1452 | 40.3206 | 34.1493 | 36.8394 | 30.4749 | 28.8563 | 21.0092 | 24.1741 | 2.3321 | 22.8728 | 22.8452 | 21.7233 | 21.0927 | 21.1623 | 20.9495 | 20.9495 | 20.7285 | 20.0653 | 25.0653 | 26.3071 | 21.8858 | 15.4748 | 14.1484 | 9.727 | 8.8427 | 8.8427 | 8.8427 | 8.8427 | 5.7478 | 0.44214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575.4393
|  | 202033.0645 | 116181.3861 | 85851.6783 | 202033.0645 | 99993.0374 | 2500.134 | 2558.9511 | 2380.183 | 2271.8357 | 2721.2885 | 3755.9565 | 4031.0218 | 1232.101 | 3230.7599 | 4279.7032 | 5521.9351 | 5540.8921 | 5420.1742 | 5194.7137 | 5580.5199 | 5345.9933 | 3395.8737 | 2792.3409 | 2127.5696 | 3589.7423 | 3408.1541 | 3032.8801 | 3105.8193 | 2851.7237 | 2859.0435 | 2878.0873 | 3106.1987 | 2259.9895 | 762.4005 | 740.0862 | 816.6429 | 615.2072 | 359.6209 | 309.7367 | 878.7336 | 402.4848 | 157.0219 | 5.7478 | 0.44214 | 0 | 6.1055 | 6.1055 | 6.1055 | 0 | 0 | 0 | 0 | 202033.0645 | 0
NINE ELMS STATION
D | STAFF | 9066.4506 | 5585.7873 | 3480.6633 | 9066.4506 | 4575.9223 | 162.08 | 165.695 | 167.505 | 170.945 | 170.945 | 172.695 | 172.695 | 132.7231 | 179.4717 | 168.1206 | 168.1206 | 168.1206 | 169.7356 | 169.7356 | 160.0918 | 157.2541 | 153.1935 | 153.1935 | 143.4574 | 143.4574 | 184.2261 | 178.5505 | 160.1396 | 150.5881 | 129.5009 | 105.3683 | 53.4793 | 47.8038 | 47.8038 | 47.8038 | 31.8846 | 22.2407 | 15.1809 | 15.1809 | 15.1809 | 11.1204 | 11.1204 | 7.0598 | 7.0598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9066.4506
| LAB | 22309.7368 | 12121.348 | 10188.3889 | 22309.7368 | 8970.6016 | 488.7721 | 646.7667 | 589.0062 | 482.4588 | 359.7153 | 584.0272 | 563.4989 | 873.5016 | 876.1571 | 839.1106 | 592.3088 | 976.6009 | 925.5507 | 618.4671 | 636.7355 | 574.7413 | 405.0331 | 262.4202 | 254.0697 | 198.5938 | 163.155 | 187.8154 | 154.0688 | 153.7488 | 137.0085 | 132.1246 | 122.2746 | 94.6964 | 63.1292 | 63.1292 | 58.3292 | 54.44 | 54.44 | 51.08 | 51.08 | 51.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22309.7368
| PLANT | 7460.9297 | 4952.7169 | 2508.2127 | 7460.9297 | 3883.2575 | 178.6267 | 219.16 | 186.3904 | 169.8983 | 126.0733 | 189.3107 | 164.8945 | 765.0541 | 277.7439 | 186.4211 | 120.6278 | 134.1193 | 110.4737 | 92.0014 | 76.2486 | 74.959 | 62.9224 | 54.156 | 54.9484 | 52.5892 | 38.5057 | 39.6548 | 35.0537 | 26.3006 | 23.2898 | 22.7813 | 18.0901 | 15.394 | 10.5373 | 8.6402 | 8.0474 | 7.3452 | 7.3452 | 6.8683 | 6.8683 | 6.3315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7460.9297
| MAT | 24307.6904 | 17996.7691 | 6310.9213 | 24307.6904 | 14307.7946 | 589.1392 | 859.7577 | 878.6452 | 538.944 | 243.7266 | 578.7617 | 807.2044 | 297.1925 | 616.2323 | 558.6064 | 375.502 | 677.9333 | 658.8945 | 433.586 | 621.739 | 450.2537 | 250.529 | 112.4149 | 116.7693 | 65.4831 | 36.5008 | 37.7109 | 25.5398 | 28.6716 | 28.1556 | 26.0884 | 23.1862 | 18.3197 | 9.2691 | 8.2553 | 5.8338 | 4.801 | 4.801 | 3.8472 | 3.8472 | 3.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24307.6904
| SUBCON | 61786.3877 | 23511.6373 | 38274.7504 | 61786.3877 | 20539.7713 | 208.0613 | 126.3051 | 415.6302 | 598.7544 | 536.2371 | 1086.8779 | 1628.7883 | 1744.098 | 1684.3274 | 1890.8294 | 2255.6023 | 2776.2247 | 2713.854 | 2783.5749 | 3338.5642 | 3342.0807 | 3159.9112 | 1496.494 | 2263.1032 | 2378.4447 | 1404.4569 | 1112.5336 | 972.9703 | 481.4672 | 336.2326 | 182.7805 | 123.3113 | 60.9923 | 39.0621 | 32.7103 | 32.439 | 19.0824 | 6.2137 | 6.2137 | 4.2213 | 4.166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61786.3877
| MISC | 2061.9592 | 1880.3452 | 181.614 | 2061.9592 | 1523.0471 | 50.7211 | 77.1783 | 85.6766 | 64.6471 | 35.0189 | 44.0562 | 47.5008 | -279.9741 | 31.7944 | 27.4478 | 27.229 | 27.229 | 33.3526 | 33.3526 | 23.1956 | 23.1956 | 23.1956 | 19.8099 | 19.8099 | 19.8099 | 19.8099 | 15.0553 | 11.6696 | 6.8719 | 6.8719 | 6.8719 | 6.836 | 3.4503 | 3.4503 | 3.4503 | 3.4 | 3.3857 | 3.3857 | 3.3857 | 3.3857 | 3.3857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061.9592
| WAO | 1510.033 | 847.0873 | 662.9457 | 1510.033 | 670.541 | 28.8774 | 28.4404 | 28.4404 | 28.6591 | 31.0645 | 31.0645 | 34.3447 | 104.3447 | 32.2481 | 33.9134 | 32.0412 | 38.801 | 38.9789 | 33.8167 | 32.5167 | 30.8885 | 27.4685 | 25.0559 | 23.5766 | 22.6971 | 21.8395 | 20.9537 | 18.0802 | 16.5894 | 13.2982 | 9.5316 | 8.3469 | 7.4611 | 7.4611 | 7.4611 | 4.9765 | 3.4713 | 2.3694 | 2.3694 | 2.3694 | 1.7356 | 1.7356 | 1.1019 | 1.1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510.033
|  | 128503.1874 | 66895.691 | 61607.4964 | 128503.1874 | 54470.9354 | 1706.2779 | 2123.3032 | 2351.294 | 2054.3066 | 1502.7808 | 2686.7932 | 3418.9266 | 3636.9398 | 3697.9748 | 3704.4492 | 3571.4317 | 4799.0288 | 4650.84 | 4164.5343 | 4889.0915 | 4653.3728 | 4082.2533 | 2123.5443 | 2875.7346 | 2881.0751 | 1868.494 | 1592.2743 | 1377.522 | 864.2376 | 674.3574 | 485.5467 | 355.5244 | 248.1176 | 180.7129 | 171.4502 | 144.9104 | 114.7663 | 93.7358 | 88.9451 | 86.9528 | 81.5725 | 12.856 | 8.1617 | 8.1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128503.1874 | 0
TUNNELS
E | STAFF | 11720.5935 | 11723.1236 | -2.5302 | 11720.5935 | 11293.9957 | 180.3149 | 172.8873 | 75.9258 | 0 | 0 | 0 | 0 | -33.3302 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11720.5935
| LAB | 41727.8322 | 41783.9559 | -56.1237 | 41727.8322 | 40407.1467 | 814.4105 | 255.9686 | 253.4301 | 35 | 9 | 9 | 9 | -190.1237 | 25 | 25 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41727.8322
| PLANT | 23180.3704 | 25284.375 | -2104.0047 | 23180.3704 | 25165.8753 | 47.1659 | 34.3828 | 36.9511 | 0 | 0 | 0 | 0 | 310.7245 | 5.3902 | 2 | 2 | 2 | -1214.0597 | -1214.0596 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23180.3704
| MAT | 24958.3997 | 24951.5012 | 6.8985 | 24958.3997 | 24714.2419 | 99.8249 | 96.406 | 41.0283 | 0 | 0 | 0 | 0 | -0.10149 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24958.3997
| SUBCON | 42954.8691 | 22598.6457 | 20356.2234 | 42954.8691 | 18893.5857 | 684.9385 | 270.7458 | 557.5591 | 636.7949 | 800.8058 | 754.2159 | 1354.9704 | 402.1517 | 386.4564 | 664.5817 | 1630.5458 | 2229.9517 | 2782.1062 | 2988.5383 | 2263.6939 | 1433.5737 | 1004.4655 | 417.5398 | 567.1756 | 601.4942 | 641.705 | 292.0692 | 280.4517 | 237.0014 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42954.8691
| MISC | 2487.5821 | 2290.4595 | 197.1226 | 2487.5821 | 2277.9595 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 122.0032 | 6 | 6 | 6 | 6 | 18.0597 | 18.0597 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487.5821
| WAO | 855.186 | 859.0954 | -3.9094 | 855.186 | 777.7301 | 32.5461 | 32.5461 | 16.273 | 0 | 0 | 0 | 0 | -29.6878 | 3.6826 | 3.6826 | 3.6826 | 3.6826 | 3.6826 | 3.6826 | 3.6826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855.186
|  | 147884.8329 | 129491.1563 | 18393.6766 | 147884.8329 | 123530.5349 | 1871.7008 | 862.9366 | 981.1675 | 671.7949 | 809.8058 | 763.2159 | 1363.9704 | 581.6363 | 431.9292 | 706.6644 | 1662.6284 | 2262.0343 | 1610.1889 | 1816.6209 | 2304.7765 | 1433.5737 | 1004.4655 | 417.5398 | 567.1756 | 601.4942 | 641.705 | 292.0692 | 280.4517 | 237.0014 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147884.8329 | 0
KENNINGTON SHAFTS
F | STAFF | 3200.437 | 2092.1087 | 1108.3283 | 3200.437 | 1651.0837 | 55.4247 | 111.1161 | 55.3067 | 59.88 | 79.31 | 79.9875 | 80.3525 | 70.8789 | 67.7269 | 61.7 | 61.7 | 61.7 | 61.7 | 61.7 | 72.06 | 50.01 | 47.81 | 47.81 | 47.81 | 43.41 | 43.41 | 41.21 | 23.285 | 23.285 | 20.21 | 12.56 | 12.56 | 12.56 | 10.36 | 10.36 | 10.36 | 10.36 | 10.36 | 10.36 | 10.36 | 10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200.437
| LAB | 8017.3231 | 3573.8603 | 4443.4627 | 8017.3231 | 2503.6047 | 193.3462 | 213.9873 | 179.8998 | 183.562 | 124.236 | 175.2243 | 153.6971 | 978.1907 | 236.9532 | 177.8417 | 154.3003 | 195.397 | 226.0025 | 286.5262 | 306.7544 | 119.3796 | 141.9431 | 77.5532 | 199.9886 | 234.29 | 234.8807 | 175.5659 | 118.5645 | 64.4594 | 34.1006 | 32.6006 | 32.6006 | 33.1006 | 28.8353 | 28.8353 | 28.8353 | 28.8353 | 25.07 | 25.07 | 25.07 | 38.2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8017.3231
| PLANT | 2580.5075 | 1127.1009 | 1453.4066 | 2580.5075 | 808.6263 | 63.913 | 84.2965 | 41.4637 | 46.2578 | 35.7149 | 46.8287 | 50.9015 | 887.1625 | 87.2709 | 45.2459 | 39.4039 | 24.5904 | 18.2882 | 21.7931 | 26.3671 | 14.9982 | 16.1427 | 13.9932 | 55.0972 | 44.273 | 43.1108 | 25.7096 | 12.8371 | 7.7392 | 0.8392 | 0.8392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2580.5075
| MAT | 7547.8345 | 5104.7569 | 2443.0776 | 7547.8345 | 3342.1087 | 338.9845 | 361.7972 | 275.0313 | 267.6841 | 295.0647 | 224.0864 | 186.6579 | -130.0386 | 137.3783 | 222.5019 | 266 | 256.5222 | 220.794 | 253.3518 | 338.0126 | 110.2936 | 104.9901 | 41.0263 | 129.2475 | 92.2189 | 66.4202 | 75.0237 | 50.4402 | 19.0924 | 0 | 2.0965 | 0 | 0 | 1.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7547.8345
| SUBCON | 13118.8961 | 5204.9773 | 7913.9188 | 13118.8961 | 4348.9419 | 123.8118 | 78.3715 | 87.6753 | 108.7202 | 131.0223 | 326.4343 | 565.1989 | -443.5718 | 223.6938 | 359.9772 | 523.7962 | 560.7409 | 987.1218 | 707.481 | 816.5647 | 728.2694 | 696.3789 | 371.241 | 282.7495 | 370.3403 | 400.7827 | 371.7106 | 170.1556 | 102.2144 | 37.7246 | 37.3086 | 1.6194 | 3.8994 | 1.5123 | 1.4944 | 1.4944 | 1.4944 | 1.4944 | 13.9093 | 6.4363 | 10.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13118.8961
| MISC | 6386.3671 | 5202.7566 | 1183.6105 | 6386.3671 | 4965.8939 | 38.4361 | 32.3607 | 50.6083 | 59.892 | 29.3478 | 26.2178 | 25.1611 | -251.8824 | 20.4879 | 20.6045 | 19.8545 | 17.6622 | 42.0862 | 28.3973 | 10.2125 | 8.7125 | 149.7136 | 9.4125 | 215.4296 | 344.2532 | 286.4372 | 128.4048 | 3.8312 | 4.8312 | 3.8312 | 4.5812 | 4.8312 | 4.8312 | 3.8312 | 4.5812 | 3.8312 | 3.8312 | 3.8312 | 4.5812 | 3.8312 | 53.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6386.3671
| WAO | 606.3015 | 224.1548 | 382.1466 | 606.3015 | 176.2741 | 1.491 | 8.3972 | 9.0141 | 9.7469 | 9.5719 | 9.6594 | 9.4844 | 2.3471 | 14.2945 | 14.7748 | 15.9591 | 17.9752 | 19.7818 | 24.1561 | 25.569 | 19.0152 | 20.1261 | 16.3036 | 18.6886 | 17.6954 | 17.6831 | 17.0886 | 12.9393 | 11.6536 | 9.9392 | 8.1507 | 7.6507 | 7.4007 | 7.2257 | 7.2257 | 7.2257 | 7.2257 | 6.6567 | 6.6567 | 5.7567 | 5.4967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606.3015
|  | 41457.6668 | 22529.7156 | 18927.9512 | 41457.6668 | 17796.5334 | 815.4072 | 890.3266 | 698.9991 | 735.743 | 704.2677 | 888.4384 | 1071.4534 | 1113.0864 | 787.8054 | 902.646 | 1081.014 | 1134.5878 | 1575.7745 | 1383.4055 | 1595.5402 | 1050.6785 | 1177.1044 | 577.3399 | 949.0111 | 1146.4806 | 1092.7247 | 834.7133 | 392.0529 | 233.2752 | 106.6448 | 98.1368 | 59.2619 | 61.7919 | 52.8128 | 52.4966 | 51.7466 | 51.7466 | 47.4123 | 60.5772 | 51.4542 | 135.1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41457.6668 | 0
RAIL SYSTEMS
G | STAFF | 2184.7269 | 1827.475 | 357.252 | 2184.7269 | 1183.7356 | 87.3482 | 119.5226 | 95.0226 | 79.6539 | 131.096 | 131.096 | 131.096 | -94.8768 | 69.6024 | 69.6024 | 60.4136 | 50.5197 | 42.1136 | 23.4332 | 1.3994 | 1.3994 | 1.3994 | 1.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2184.7269
| LAB | 6591.8722 | 4663.8857 | 1927.9865 | 6591.8722 | 2463.492 | 206.6669 | 448.537 | 420.268 | 374.407 | 366.4553 | 384.0595 | 400.3891 | 278.1447 | 744.8273 | 333.9234 | 116.779 | 14.9584 | 12.9758 | 6.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6863 | 4.2781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6591.8722
| PLANT | 1786.4858 | 1821.2911 | -34.8053 | 1786.4858 | 1112.737 | 70.1302 | 135.8765 | 101.8913 | 100.2176 | 107.9302 | 192.5083 | 137.7675 | -368.5118 | 113.9948 | 46.8815 | 10.2429 | 2.9092 | 1.5733 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 1.209 | 0.9931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786.4858
| MAT | 7542.3499 | 5845.6865 | 1696.6634 | 7542.3499 | 3010.2048 | 242.332 | 1356.5563 | 569.2749 | 134.1116 | 135.856 | 397.3508 | 1425.2306 | -38.553 | 128.0616 | 106.2046 | 35.5505 | 4.0335 | 1.1369 | 1.1369 | 1.1369 | 1.1369 | 1.1369 | 0.9339 | 0 | 0 | 0 | 0 | 0 | 23.192 | 6.3251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7542.3499
| SUBCON | 7468.3241 | 4087.2845 | 3381.0397 | 7468.3241 | 2764.4862 | 180.8417 | 72.2865 | 179.963 | 143.4721 | 388.2053 | 358.0297 | 569.7166 | -332.3977 | 5.0151 | 59.265 | 66.0377 | 579.8709 | 772.7954 | 715.4311 | 515.4311 | 359.8743 | 0 | 0 | 0 | 6.6667 | 6.6667 | 6.6667 | 6.6667 | 6.6667 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7468.3241
| MISC | 855.9248 | 19.5255 | 836.3993 | 855.9248 | 7.0774 | 1.833 | 1.833 | 1.833 | 1.833 | 1.833 | 3.283 | 4.733 | 38.1624 | 241.3232 | 131.5211 | 88.4075 | 29.0282 | 25.6908 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 90.3011 | 27.7177 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 4.2489 | 3.0349 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855.9248
| WAO | 191.1681 | 60.3931 | 130.775 | 191.1681 | 27.3027 | 1.2148 | 8.9141 | 6.1082 | 5.9811 | 5.5149 | 5.3572 | 5.4681 | 78.2524 | 11.4194 | 11.0697 | 8.9102 | 5.9077 | 5.49 | 3.9314 | 0.13525 | 0.06213 | 0.06213 | 0.06213 | 0.00444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.1681
|  | 26620.8518 | 18325.5412 | 8295.3106 | 26620.8518 | 10569.0356 | 790.3669 | 2143.526 | 1374.3612 | 839.6764 | 1136.8907 | 1471.6845 | 2674.4009 | -439.7798 | 1314.2439 | 758.4678 | 386.3415 | 687.2275 | 861.7759 | 755.415 | 523.5606 | 367.9307 | 8.0563 | 7.6034 | 5.4623 | 12.1245 | 12.1245 | 12.1245 | 12.1245 | 137.0551 | 40.3632 | 6.2912 | 6.2912 | 6.2912 | 6.2912 | 6.0753 | 5.0822 | 5.0822 | 4.2489 | 3.0349 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26620.8518 | 0
SUMMARY OF SITES |  | EF8 | CTD @ P11 | CTG | Total
A | GENERAL MANAGEMENT | 63012.0768 | 37888.2936 | 25123.7832 | 63012.0768 | 33025.2302 | 802.9124 | 858.1444 | 800.3684 | 803.0324 | 807.4824 | 791.1234 | 809.6664 | 1232.0505 | 1243.9905 | 1095.1337 | 1131.2298 | 1102.8597 | 1006.6098 | 991.8397 | 1067.5443 | 1072.6758 | 1002.2768 | 995.6067 | 884.1388 | 891.8587 | 851.5788 | 826.0587 | 817.1088 | 826.9953 | 755.2088 | 712.8087 | 673.4195 | 632.7493 | 552.8335 | 555.01 | 525.0035 | 476.3103 | 454.9875 | 423.6643 | 415.9678 | 430.0893 | 479.7595 | 74.3653 | 37.8167 | 62.5667 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 63012.0768
B | ENGINEERING | 82895.7549 | 72349.6936 | 10546.0613 | 82895.7549 | 67847.93 | 1054.594 | 777.6925 | 755.2434 | 714.0986 | 670.7678 | 529.3674 | 597.4047 | 1378.345 | 846.6685 | 783.4237 | 773.5869 | 645.8242 | 557.1259 | 316.1593 | 411.3976 | 487.3846 | 354.2817 | 338.0016 | 321.2538 | 321.0299 | 305.9417 | 282.6256 | 278.4097 | 248.8601 | 213.1168 | 201.8839 | 165.3254 | 120.6222 | 94.3815 | 85.337 | 54.6025 | 34.1041 | 37.6094 | 44.8875 | 44.2179 | 42.4124 | 41.7428 | 42.4124 | 36.4896 | 32.6911 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 82895.7549
C | BATTERSEA STATION | 202033.0645 | 116181.3861 | 85851.6783 | 202033.0645 | 99993.0374 | 2500.134 | 2558.9511 | 2380.183 | 2271.8357 | 2721.2885 | 3755.9565 | 4031.0218 | 1232.101 | 3230.7599 | 4279.7032 | 5521.9351 | 5540.8921 | 5420.1742 | 5194.7137 | 5580.5199 | 5345.9933 | 3395.8737 | 2792.3409 | 2127.5696 | 3589.7423 | 3408.1541 | 3032.8801 | 3105.8193 | 2851.7237 | 2859.0435 | 2878.0873 | 3106.1987 | 2259.9895 | 762.4005 | 740.0862 | 816.6429 | 615.2072 | 359.6209 | 309.7367 | 878.7336 | 402.4848 | 157.0219 | 5.7478 | 0.44214 | 0 | 6.1055 | 6.1055 | 6.1055 | 0 | 0 | 0 | 0 | 202033.0645
D | NINE ELMS STATION | 128503.1874 | 66895.691 | 61607.4964 | 128503.1874 | 54470.9354 | 1706.2779 | 2123.3032 | 2351.294 | 2054.3066 | 1502.7808 | 2686.7932 | 3418.9266 | 3636.9398 | 3697.9748 | 3704.4492 | 3571.4317 | 4799.0288 | 4650.84 | 4164.5343 | 4889.0915 | 4653.3728 | 4082.2533 | 2123.5443 | 2875.7346 | 2881.0751 | 1868.494 | 1592.2743 | 1377.522 | 864.2376 | 674.3574 | 485.5467 | 355.5244 | 248.1176 | 180.7129 | 171.4502 | 144.9104 | 114.7663 | 93.7358 | 88.9451 | 86.9528 | 81.5725 | 12.856 | 8.1617 | 8.1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128503.1874
E | TUNNELS | 147884.8329 | 129491.1563 | 18393.6766 | 147884.8329 | 123530.5349 | 1871.7008 | 862.9366 | 981.1675 | 671.7949 | 809.8058 | 763.2159 | 1363.9704 | 581.6363 | 431.9292 | 706.6644 | 1662.6284 | 2262.0343 | 1610.1889 | 1816.6209 | 2304.7765 | 1433.5737 | 1004.4655 | 417.5398 | 567.1756 | 601.4942 | 641.705 | 292.0692 | 280.4517 | 237.0014 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 19.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147884.8329
F | KENNINGTON SHAFTS | 41457.6668 | 22529.7156 | 18927.9512 | 41457.6668 | 17796.5334 | 815.4072 | 890.3266 | 698.9991 | 735.743 | 704.2677 | 888.4384 | 1071.4534 | 1113.0864 | 787.8054 | 902.646 | 1081.014 | 1134.5878 | 1575.7745 | 1383.4055 | 1595.5402 | 1050.6785 | 1177.1044 | 577.3399 | 949.0111 | 1146.4806 | 1092.7247 | 834.7133 | 392.0529 | 233.2752 | 106.6448 | 98.1368 | 59.2619 | 61.7919 | 52.8128 | 52.4966 | 51.7466 | 51.7466 | 47.4123 | 60.5772 | 51.4542 | 135.1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41457.6668
G | RAIL SYSTEMS | 26620.8518 | 18325.5412 | 8295.3106 | 26620.8518 | 10569.0356 | 790.3669 | 2143.526 | 1374.3612 | 839.6764 | 1136.8907 | 1471.6845 | 2674.4009 | -439.7798 | 1314.2439 | 758.4678 | 386.3415 | 687.2275 | 861.7759 | 755.415 | 523.5606 | 367.9307 | 8.0563 | 7.6034 | 5.4623 | 12.1245 | 12.1245 | 12.1245 | 12.1245 | 137.0551 | 40.3632 | 6.2912 | 6.2912 | 6.2912 | 6.2912 | 6.0753 | 5.0822 | 5.0822 | 4.2489 | 3.0349 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26620.8518
|  | 692407.4351 | 463661.4776 | 228745.9576 | 692407.4351 | 407233.2369 | 9541.3931 | 10214.8804 | 9341.6166 | 8090.4877 | 8353.2836 | 10886.5793 | 13966.8442 | 8734.3793 | 11553.3723 | 12230.4879 | 14128.1675 | 16172.4545 | 15682.4893 | 14622.6883 | 16372.4307 | 14411.6094 | 11024.3118 | 7251.9767 | 7730.3458 | 9443.8054 | 8180.7229 | 6872.7456 | 6263.4889 | 5399.1484 | 4668.4847 | 4402.5047 | 4385.7712 | 3349.3118 | 1669.1825 | 1630.2053 | 1617.7382 | 1316.9668 | 1017.3649 | 930.8458 | 1477.3263 | 1201.7346 | 691.3802 | 130.6872 | 82.9101 | 95.2578 | 12.6055 | 6.1055 | 18.1055 | 0 | 0 | 0 | 0 | 692407.4352 | 0
| SUMMARY OF COST ELEMENT | EF8 | CTD @ P11 | CTG | Total
| STAFF | 106321.4852 | 71646.2134 | 34675.2718 | 106321.4852 | 61996.9062 | 1619.2961 | 1739.8673 | 1585.8698 | 1533.0631 | 1622.3896 | 1548.8212 | 1553.37 | 1462.9737 | 1716.6497 | 1673.8637 | 1660.8699 | 1614.662 | 1515.3059 | 1484.3255 | 1461.3579 | 1426.4241 | 1381.8046 | 1365.1397 | 1272.4041 | 1274.1541 | 1310.0373 | 1271.0517 | 1232.0058 | 1218.0543 | 1121.069 | 1034.2825 | 900.177 | 834.8714 | 731.4004 | 692.3054 | 637.5412 | 580.5674 | 459.0796 | 434.7896 | 398.9896 | 394.729 | 376.209 | 87.3768 | 52.2448 | 45.185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106321.4852
| LAB | 113781.4312 | 82495.3479 | 31286.0833 | 113781.4312 | 70889.5681 | 2343.593 | 2220.7118 | 2102.5193 | 1705.0287 | 1470.5063 | 1763.4206 | 1891.8357 | 1656.0845 | 2623.2593 | 2247.4009 | 2313.7282 | 2275.3369 | 2435.8258 | 1886.7211 | 1809.0266 | 1246.2061 | 1021.9241 | 496.201 | 959.2773 | 949.5807 | 848.1613 | 776.0891 | 683.3231 | 631.9587 | 573.4513 | 636.2268 | 690.6278 | 480.9574 | 358.5863 | 264.5272 | 246.1269 | 242.2377 | 236.4724 | 229.5124 | 229.5124 | 266.664 | 79.2401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113781.4312
| PLANT | 49446.2785 | 44717.7744 | 4728.5041 | 49446.2785 | 40109.5961 | 755.4155 | 871.201 | 780.6827 | 701.0112 | 632.7836 | 867.0843 | 731.1616 | 809.6486 | 755.2842 | 455.7948 | 383.4263 | 299.7445 | -906.5447 | -1123.11 | 285.4382 | 319.8351 | 168.6439 | 80.7471 | 255.7617 | 269.1643 | 251.0069 | 207.0341 | 189.7411 | 169.4253 | 180.7918 | 190.0118 | 240.7325 | 76.7459 | 66.1648 | 57.8121 | 53.2923 | 43.8879 | 37.5553 | 40.0254 | 40.0254 | 56.2924 | 21.2261 | 4 | 0 | 0 | 5.9125 | 5.9125 | 5.9125 | 0 | 0 | 0 | 0 | 49446.2785
| MAT | 95123.0656 | 76814.2513 | 18308.8143 | 95123.0656 | 64910.8053 | 1780.4945 | 3201.1817 | 2291.7257 | 1475.1142 | 1343.4919 | 1811.4381 | 3137.6953 | -908.2965 | 1577.457 | 1581.3157 | 1579.4918 | 1713.1627 | 1742.5497 | 1375.724 | 1761.2775 | 1005.0334 | 680.4949 | 286.6847 | 524.6466 | 430.4245 | 289.3154 | 272.5587 | 208.8371 | 193.9681 | 201.3415 | 228.963 | 182.7504 | 29.5338 | 21.2905 | 25.6947 | 42.9732 | 15.3405 | 21.3405 | 14.3567 | 15.2567 | 14.5128 | 30.5404 | 0 | 0 | 0 | 0.19302 | 0.19302 | 12.193 | 0 | 0 | 0 | 0 | 95123.0656
| SUBCON | 296531.5413 | 163424.5115 | 133107.0298 | 296531.5413 | 146702.7079 | 2756.3763 | 1822.6375 | 2260.2855 | 2349.6151 | 2967.6234 | 4565.2657 | 6334.4552 | 5847.0915 | 4391.7227 | 5895.4917 | 7848.1234 | 9990.0419 | 10575.8506 | 10724.8767 | 10816.5291 | 10217.3112 | 7437.0307 | 4862.3558 | 4331.4547 | 6006.7257 | 5031.7416 | 4061.4735 | 3799.9788 | 2952.8871 | 2435.3703 | 2187.5472 | 2250.4887 | 1808.7502 | 376.2662 | 486.5157 | 551.9665 | 354.4827 | 194.1737 | 147.2105 | 726.2926 | 282.2129 | 140.2888 | 16.1223 | 10.1995 | 7.5 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 296531.5413
| MISC | 22653.8584 | 18989.5442 | 3664.3141 | 22653.8584 | 18008.3299 | 136.3982 | 144.28 | 173.0028 | 186.9571 | 165.2104 | 175.3658 | 162.5147 | -90.7686 | 341.7341 | 228.1091 | 184.6518 | 123.0429 | 162.1113 | 125.8215 | 95.8051 | 69.7353 | 210.8668 | 66.4287 | 273.9319 | 402.7554 | 344.9394 | 182.1524 | 54.1932 | 136.4477 | 72.1143 | 49.3955 | 49.5039 | 44.2338 | 42.4838 | 34.2338 | 31.6736 | 30.8362 | 25.9212 | 25.0772 | 20.9924 | 150.4683 | 12.9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22653.8584
| WAO | 8549.775 | 5573.8349 | 2975.9402 | 8549.775 | 4615.3233 | 149.8196 | 215.0011 | 147.5309 | 139.6983 | 151.2783 | 155.1835 | 155.8117 | -42.354 | 147.2653 | 148.5119 | 157.8761 | 156.4636 | 157.3906 | 148.3296 | 142.9963 | 127.0642 | 123.5469 | 94.4197 | 112.8695 | 111.0007 | 105.521 | 102.3861 | 95.4099 | 96.4073 | 84.3465 | 76.0779 | 71.491 | 74.2193 | 72.9904 | 69.1162 | 54.1645 | 49.6145 | 42.8222 | 39.8739 | 46.2572 | 36.8552 | 30.9685 | 23.1881 | 20.4658 | 42.5728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8549.775
|  | 692407.4352 | 463661.4776 | 228745.9576 | 692407.4352 | 407233.2369 | 9541.3931 | 10214.8804 | 9341.6166 | 8090.4877 | 8353.2836 | 10886.5793 | 13966.8442 | 8734.3793 | 11553.3723 | 12230.4879 | 14128.1675 | 16172.4545 | 15682.4893 | 14622.6883 | 16372.4307 | 14411.6094 | 11024.3118 | 7251.9767 | 7730.3458 | 9443.8054 | 8180.7228 | 6872.7457 | 6263.4889 | 5399.1484 | 4668.4847 | 4402.5047 | 4385.7712 | 3349.3118 | 1669.1825 | 1630.2053 | 1617.7382 | 1316.9668 | 1017.3649 | 930.8458 | 1477.3263 | 1201.7346 | 691.3802 | 130.6872 | 82.9102 | 95.2578 | 12.6055 | 6.1055 | 18.1055 | 0 | 0 | 0 | 0 | 692407.4352 | 0

## Summary Breakdown
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
A08100 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 1038208.71 | 39908 | 91795 | 39278 | 38928 | 38578 | 37843 | 37843 | -43499.54 | 49381.67 | 44865 | 45215 | 45915 | 42765 | 42415 | 42415 | 46581.67 | 42240 | 41190 | 38565 | 38915 | 36815 | 36465 | 36465 | 40631.67 | 34015 | 31915 | 29990 | 29640 | 27640 | 29006.67 | 24490 | 23150 | 22450 | 20700 | 27983.33 | 19475 | 19085 | 15033.33 | 17616.67 | 42366.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2404278.85
A09999 | Overhead Temporary code (to be reconciled periodically) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | MAT | Materials | BUDGET | Approved Early Budget | -18205.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18205.42
A09999 | Overhead Temporary code (to be reconciled periodically) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 9762.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9762.2
A09999 | Overhead Temporary code (to be reconciled periodically) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21647.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -891.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20755.79
A09999 | Overhead Temporary code (to be reconciled periodically) | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 678492.04 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 1573.5 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030615.54
A11000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1449972.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92180.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542152.57
A11000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2287.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8564.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6277.66
A11000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 20295634.95 | 387859.66 | 385757.66 | 378107.66 | 373707.66 | 373707.66 | 348253.66 | 348253.66 | 160889.07 | 360888.66 | 346838.66 | 346838.66 | 346838.66 | 331638.66 | 322588.66 | 322588.66 | 322588.66 | 335088.66 | 335088.66 | 304738.66 | 304738.66 | 304738.66 | 295688.66 | 295688.66 | 295688.66 | 295688.66 | 258238.66 | 254413.66 | 250013.66 | 245613.66 | 242903.66 | 247303.66 | 233243.66 | 233243.66 | 233243.66 | 225593.66 | 223393.66 | 221633.66 | 20200 | 20200 | 20200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31449567.78
A11000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 167998.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167998.25
A11002 | OH Prelims HHRR - Springboard | MISC | Miscellaneous | BUDGET | Approved Early Budget | 181175 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | -3810 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327250
A11004 | OH Prelims H&S - Park Health | MAT | Materials | BUDGET | Approved Early Budget | 1897.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897.2
A11004 | OH Prelims H&S - Park Health | MISC | Miscellaneous | BUDGET | Approved Early Budget | 929873.93 | 27330 | 27330 | 27330 | 27330 | 27330 | 28705 | 27330 | -23121.68 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 28705 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 26580 | 26580 | 26580 | 25330 | 24580 | 15580 | 13820 | 13740 | 13660 | 13280 | 12980 | 12680 | 12680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776162.25
A11004 | OH Prelims H&S - Park Health | STAFF | Staff | BUDGET | Approved Early Budget | -44519.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44519.85
A11006 | OH Prelims Engineering - Obsolete | MAT | Materials | BUDGET | Approved Early Budget | 372.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372.13
A11006 | OH Prelims Engineering - Obsolete | MISC | Miscellaneous | BUDGET | Approved Early Budget | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6
A11006 | OH Prelims Engineering - Obsolete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168
A11010 | ME, Testing and Commissioning | LAB | Labour | BUDGET | Approved Early Budget | 8685.92 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | -17316.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54369.47
A11010 | ME, Testing and Commissioning | STAFF | Staff | BUDGET | Approved Early Budget | 3362961.01 | 229523.74 | 254517.74 | 257148.74 | 270322.74 | 270322.74 | 271322.74 | 291300.74 | 882998.87 | 552183 | 543133 | 551133 | 553764 | 451264 | 443614 | 443614 | 443614 | 429706 | 429706 | 378206 | 384356 | 335556 | 325006 | 325006 | 325006 | 266306 | 266306 | 243636 | 213186 | 142260 | 114100 | 100050 | 93900 | 77472 | 53182 | 47032 | 47032 | 42632 | 35132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14747512.06
A11010 | ME, Testing and Commissioning | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45781 | 0 | 0 | 0 | 77109.5 | 77109.5 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000
A11011 | Labour Redundancy Cost | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13048 | 15000 | 15000 | 15000 | 15000 | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100048
A11012 | LUL16 Management | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17700 | 17700 | 17700 | 17700 | 30000 | 61160 | 65560 | 65560 | 65560 | 65560 | 53260 | 53260 | 53260 | 57660 | 57660 | 57660 | 57660 | 57660 | 52010 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418190
A11030 | Site Facilities & Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1149.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1477.2
A11030 | Site Facilities & Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -8838.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8838.07
A11031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3425.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3425.61
A11034 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 11364.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11364.71
A11034 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 319467.25 | 1800 | 1000 | 1000 | 1000 | 1800 | 1000 | 1000 | -7600 | 1900 | 1000 | 1000 | 1000 | 1900 | 1000 | 1000 | 1000 | 1000 | 1900 | 1000 | 500 | 500 | 1150 | 250 | 250 | 250 | 1150 | 250 | 250 | 250 | 1150 | 250 | 250 | 250 | 250 | 1150 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343267.25
A11034 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 361968.63 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 4375.91 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388634.54
A11034 | Temporary Accommodation | STAFF | Staff | BUDGET | Approved Early Budget | 2640.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063.53
A11036 | IT Equipment & running costs | MAT | Materials | BUDGET | Approved Early Budget | 9821.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9821.6
A11036 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 130656.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131186.64
A11036 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2136.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136.14
A11036 | IT Equipment & running costs | STAFF | Staff | BUDGET | Approved Early Budget | 62786.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62786.82
A11038 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 1477.35 | 0 | 0 | 5760 | 0 | 0 | 0 | 0 | -5760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237.35
A11038 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11620.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13615.67
A11038 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2478.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3978.63
A11038 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
A11040 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 28147.2 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | -6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 70147.2
A11040 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 76869.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77394.13
A11040 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5487.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5487.07
A11040 | H&S Quality Environmental | STAFF | Staff | BUDGET | Approved Early Budget | 67025.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11199.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78225.03
A11042 | Liaison and co ordination with others | MAT | Materials | BUDGET | Approved Early Budget | 12396.55 | 2000 | 0 | 0 | 0 | 4000 | 0 | 0 | -723 | 2000 | 5940 | 2000 | 2000 | 2000 | 4000 | 2000 | 2000 | 2000 | 26000 | 2000 | 2000 | 4000 | 2000 | 2000 | 5940 | 2000 | 2000 | 800 | 800 | 800 | 800 | 27400 | 800 | 800 | 800 | 800 | 800 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144953.55
A11042 | Liaison and co ordination with others | MISC | Miscellaneous | BUDGET | Approved Early Budget | 139062.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71926.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210989.66
A11042 | Liaison and co ordination with others | STAFF | Staff | BUDGET | Approved Early Budget | 93536.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89318.79
A11042 | Liaison and co ordination with others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 18500 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | -30500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11044 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14077
A11044 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2269.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032.24
A11044 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13241
A11044 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000
A11046 | Logistics | LAB | Labour | BUDGET | Approved Early Budget | 398299.19 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 39984.56 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 3600 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744283.75
A11046 | Logistics | MAT | Materials | BUDGET | Approved Early Budget | 2594.61 | 600 | 600 | 600 | 600 | 600 | 600 | 540 | 2386.52 | 122020 | 1960 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1840 | 1840 | 1840 | 1720 | 1720 | 1720 | 1660 | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 830 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171881.13
A11046 | Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 281564.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298796.08
A11046 | Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 293572.83 | 2613 | 2866 | 2866 | 2866 | 2866 | 2866 | 2866 | 11217.76 | 2866 | 2866 | 2866 | 2866 | 2186 | 2186 | 2186 | 2986 | 2986 | 2986 | 2673 | 2673 | 2673 | 2673 | 2673 | 2673 | 2673 | 1953 | 1893 | 1893 | 1833 | 1833 | 1833 | 1833 | 1833 | 4780 | 4780 | 4780 | 4780 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408314.59
A11046 | Logistics | STAFF | Staff | BUDGET | Approved Early Budget | 4114.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4114.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8229.11
A11046 | Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 8100 | 1600 | 1600 | 1600 | 1600 | 13855 | 13855 | -29955 | 12255 | 12255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36765
A11048 | Security & Access Control (Servest) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 32490.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34842.69
A11048 | Security & Access Control (Servest) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 134381.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134381.99
A11048 | Security & Access Control (Servest) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2319371.5 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 77515.52 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4003948.46
A11070 | Small Plant & PPE | LAB | Labour | BUDGET | Approved Early Budget | 6323.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6323.81
A11070 | Small Plant & PPE | MAT | Materials | BUDGET | Approved Early Budget | 4.8 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | -4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8
A11070 | Small Plant & PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1676.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676.46
A11070 | Small Plant & PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 125319.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144492.84
A11072 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000
A11072 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
B08200 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 759625.69 | 16288.4 | 16726.5 | 17737.5 | 17165 | 17165 | 14627.55 | 14290.55 | -19534.49 | 12092.75 | 12061.35 | 11747.35 | 10032.85 | 9852.85 | 9852.85 | 9821.45 | 9507.45 | 9476.05 | 9476.05 | 9162.05 | 8848.05 | 7460.05 | 6786.05 | 6763.05 | 6583.05 | 6144.55 | 5752.05 | 5438.05 | 4652.2 | 4356.5 | 3537 | 1997.5 | 1619.1 | 1619.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 206.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046767.75
B12000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 267002.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21257.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288259.71
B12000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 9471592.33 | 201805 | 207175 | 222125 | 219415 | 219415 | 190835 | 184685 | -95274.26 | 190395 | 190395 | 190395 | 179395 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 161070 | 149560 | 146850 | 142450 | 130150 | 130150 | 130150 | 105370 | 82125 | 73900 | 44705 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14432058.07
B12000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 541.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541.3
B12031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.1
B12050 | CP Health & Safety Services Ltd (Chris Purslow) | STAFF | Staff | BUDGET | Approved Early Budget | 56100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56100
B12060 | OTB Engineering Limited (Jon Austin) | STAFF | Staff | BUDGET | Approved Early Budget | 98469.75 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | -9393 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110526.75
B12060 | OTB Engineering Limited (Jon Austin) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
B12070 | Matchtech (Paul Kick) | STAFF | Staff | BUDGET | Approved Early Budget | 304816.81 | 37000 | 37000 | 37000 | 37000 | 37000 | 37000 | 37000 | 13850.94 | 45900 | 45900 | 45900 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822467.75
B12080 | Aspects (John Bailey) | STAFF | Staff | BUDGET | Approved Early Budget | 266625 | 10800 | 10800 | 10800 | 10800 | 10800 | 8100 | 8100 | 15862.5 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598387.5
B12090 | Protechning | STAFF | Staff | BUDGET | Approved Early Budget | 447441.09 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 3512.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463328.18
B22136 | Equipment supply and installation | LAB | Labour | BUDGET | Approved Early Budget | 5934.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3552.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9487.45
B22136 | Equipment supply and installation | MAT | Materials | BUDGET | Approved Early Budget | 274560.19 | 3000 | 3000 | 3000 | 3000 | 3000 | -105713 | 3000 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190560.19
B22136 | Equipment supply and installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 62791.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62791.82
B22136 | Equipment supply and installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 274177.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15607.47 | 40000 | 3000 | 3000 | -38000 | 3000 | -149000 | 3000 | 130000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287785.22
B22136 | Equipment supply and installation | STAFF | Staff | BUDGET | Approved Early Budget | 49620.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2728.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46892.5
B22136 | Equipment supply and installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17763.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9512.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27276.06
B22136 | Equipment supply and installation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 192061.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192061.1
B22600 | Geotechnical Observations Ltd (Automated Monitoring) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2143051.81 | 22510 | 22510 | 22210 | 15560 | 0 | 0 | 0 | 23484.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2249326.7
B22610 | Amey (SW Storm Sewer Temp works) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1271618.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1271618.92
B22611 | Geotechnical Consulting Group | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17752
B22620 | Thames Water Utilities Limited | MISC | Miscellaneous | BUDGET | Approved Early Budget | 284643.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284643.75
B22630 | EDF Cable Tunnel (Monitoring and protection) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 142556.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142556.56
B22660 | London Ring Main (Monitoring and protection) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22670 | ESG (Boreholes) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 56021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56021
B22680 | DI Harris (Geotechnical Monitoring) | STAFF | Staff | BUDGET | Approved Early Budget | 295101.92 | 6812.31 | 6812.31 | 6812.31 | 6812.31 | 4732.31 | 4732.31 | 4732.31 | 27969.98 | 6000 | 3692 | 3692 | 3692 | 3692 | 3692 | 3692 | 3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396362.07
B22680 | DI Harris (Geotechnical Monitoring) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1722.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1722.5
B22710 | CPM Surveys (Dilapidation Surveys) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 388130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396358
B32810 | Mott MacDonald (Permanent Design to RIBA4) | STAFF | Staff | BUDGET | Approved Early Budget | 1166126.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166126.39
B32810 | Mott MacDonald (Permanent Design to RIBA4) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 39653685.57 | 240143.1 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 294610.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40208438.83
B32811 | Mott MacDonald (Post RIBA4) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 773638.28 | 25000 | 25000 | 25000 | 25000 | 10000 | 10000 | 10000 | -27597.92 | 55000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081040.36
B32812 | Mott MacDonald (BPSDC Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 8148.69 | 20000 | 20000 | 10000 | 0 | 0 | 0 | 0 | 127684.55 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285833.24
B32813 | Mott MacDonald (Defect Correction) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | -46346.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46346.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32816 | Mott MacDonald Site Support | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4358081.78 | 293768.19 | 301613.66 | 298503.6 | 283416.29 | 277725.45 | 284405.53 | 268666.84 | 970118.53 | 446830.77 | 403925.37 | 391402.57 | 355604.37 | 312111.09 | 223144.49 | 170064.16 | 152565.1 | 150185.62 | 127005.6 | 103770.58 | 103860.64 | 102460.48 | 91328.32 | 89845.44 | 64875.84 | 41871.08 | 38680.65 | 2436.16 | 0 | 0 | 0 | 0 | 0 | 3505.28 | 11097.41 | 10427.81 | 8622.34 | 7952.74 | 8622.34 | 2699.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10761195.66
B32817 | FLO support to Mott MacDonald | STAFF | Staff | BUDGET | Approved Early Budget | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853986.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898986.47
B32817 | FLO support to Mott MacDonald | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 242152.51 | 95280 | 73280 | 73280 | 73280 | 73280 | 73280 | 61280 | -818840.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -53727.75
B32820 | OTB Engineering Limited (Tunnel Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 710667.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2417.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708250.25
B32825 | OTB Engineering Limited Site Support | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1154584.67 | 58412 | 20000 | 0 | 0 | 0 | 0 | 0 | -77714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155282.67
B32830 | Firstco (Comms Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1614688.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5927.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1608760.57
B32840 | York (Electro Magnetic Consultant) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 26290.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186501.21
B32860 | Explore (DFMA Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 30718.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30718.5
B32870 | Epofore (Rebar Detailing) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 241692.5 | 7000 | 7000 | 7000 | 7000 | 7000 | 6450 | 0 | 9017.5 | 2000 | 2000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301160
B32875 | Computer and Design Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 52658 | 4000 | 4000 | 4000 | 2000 | 2000 | 0 | 0 | -3284 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68374
B32880 | Gal Ziedler (CAT 3 checking of Tunnel Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 269215.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269215.8
B32890 | RUL (Geotechnical analysis and Report) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 42820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42820
B32900 | Clancy Docwra (Tunnel Intrusive Surveys) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 60972.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60972.96
B32911 | OTB (Various TW Designs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 99896 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | -4112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100784
B32912 | RMP (Various TW Designs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 75420 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | -7205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78215
B32913 | Tony Gee (Various TW Designs) | STAFF | Staff | BUDGET | Approved Early Budget | 1437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1437.5
B32914 | Steer Davies & Gleave Limited (TM Design) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8842
B32915 | Testing and Consultancy Services Ltd (Tunnel Vent Design) | STAFF | Staff | BUDGET | Approved Early Budget | 2810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2810
B32916 | Campbell Reith Hill LLP (BCDH Pile Design) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
B32920 | Building Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 53792.69 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 333.63 | 8000 | 10000 | 10000 | 10000 | 10000 | 10000 | 8000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 262126.32
B32921 | Small Works Orders | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 50625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1723 | 0 | 25000 | 25000 | 30000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207348
C08300 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 797208.65 | 26651 | 26651 | 27836.76 | 35500.61 | 45447.69 | 45479.1 | 40166.81 | -142860.24 | 20192.08 | 22071.43 | 23994.19 | 23662.96 | 22956.96 | 20300.34 | 20615.09 | 17372.68 | 20290.01 | 1024.45 | 21170.61 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20728.48 | 20065.27 | 25065.27 | 26307.11 | 21885.75 | 15474.77 | 14148.36 | 9727 | 8842.73 | 8842.73 | 8842.73 | 8842.73 | 5747.77 | 442.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436392.26
C08310 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 2842.82 | 1530.75 | 2842.82 | 3717.54 | 3936.22 | 11152.61 | 14214.11 | 8283.85 | 3954.21 | 6073.75 | 16326.4 | 10486.32 | 13882.43 | 10174.58 | 8241.19 | 3636.51 | 3884.11 | 1307.6 | 1702.2 | 1895.63 | 773.73 | 143.14 | 212.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131215.29
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | LAB | Labour | BUDGET | Approved Early Budget | -0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | MISC | Miscellaneous | BUDGET | Approved Early Budget | -60.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60.62
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 172.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.62
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | STAFF | Staff | BUDGET | Approved Early Budget | 1439.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.05
C13000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 1449984.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355226.74 | 65235 | 70725.87 | 71384.78 | 71384.78 | 68834.49 | 55780.55 | 53723.39 | 51690.54 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 43941.03 | 37293.57 | 26527.37 | 15494.49 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 3171.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953897.49
C13000 | General management & Supervision | MAT | Materials | BUDGET | Approved Early Budget | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
C13000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2042.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042.65
C13000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23811.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5868.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29680.65
C13000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 7233352.5 | 254552.63 | 262808.58 | 274341.07 | 302876.48 | 323410.92 | 303149 | 293504.81 | -493315.55 | 209932 | 209932 | 198127 | 196132 | 196132 | 196132 | 196132 | 193186 | 159927 | 155812 | 155812 | 155812 | 158887 | 158887 | 158887 | 158887 | 157063.9 | 152810 | 152938 | 152938 | 152938 | 152938 | 152938 | 150938 | 52938 | 52938 | 30938 | 32938 | 30938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13039488.34
C13022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | 62293.59 | 0 | 0 | 0 | 0 | 0 | 0 | 908.37 | -1476.06 | 0 | 723.32 | 0 | 0 | 752.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63201.56
C13022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 517096.28 | 14840.56 | 14965.36 | 14965.36 | 14965.36 | 14965.36 | 14965.36 | 19536.75 | -86544.46 | 13554.76 | 17721.17 | 14849.7 | 14795.68 | 18327.77 | 12825.36 | 13838.73 | 32628.94 | 14084.84 | 869.18 | 27009 | 27009 | 27009 | 27009 | 27009 | 26815.98 | 26815.98 | 26815.98 | 22985.13 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 0 | 0 | 0 | 0 | 193.02 | 193.02 | 193.02 | 0 | 0 | 0 | 0 | 934046.37
C13022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 646818.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773501.92
C13022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 467830.73 | 23050.42 | 27195.82 | 27195.82 | 27195.82 | 27195.82 | 27195.82 | 27400.22 | -138125.87 | 19449.95 | 20304.52 | 18187.3 | 18121.14 | 15918.31 | 7442.4 | 11002.48 | 9375 | 11198.15 | 691.04 | 21473.51 | 21473.51 | 21473.51 | 21473.51 | 21473.51 | 15560.98 | 15560.98 | 15560.98 | 13337.98 | 5912.52 | 5912.52 | 7482.35 | 14703.58 | 8738.22 | 5912.52 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0 | 899350.19
C13022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1422087.75 | 59086.21 | 56406.34 | 54018.64 | 54018.64 | 54018.64 | 54018.64 | 54018.64 | -37181.69 | 50198.26 | 51789.35 | 52604.75 | 52413.38 | 51379.29 | 45433.59 | 48673.07 | 46082.35 | 49538.69 | 3057.05 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 102449.38 | 60762.46 | 53888 | 61840.5 | 155342.49 | 72887.23 | 33829.47 | 33829.47 | 33829.47 | 33829.47 | 9665.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3633775.65
C13022 | Temporary Services | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 787.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787.5
C13024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 577758.41 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 6792.94 | 14239.78 | 14754.45 | 15712.45 | 15655.29 | 15346.42 | 13570.5 | 14538.1 | 12387.63 | 14796.65 | 913.11 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 37301.57 | 23218.8 | 14934.87 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 2952.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164884.16
C13024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 49467.19 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | -24877.39 | 3122.35 | 3651.99 | 4273.79 | 4258.24 | 4174.23 | 3691.18 | 3954.36 | 3369.44 | 4024.69 | 248.37 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 10171.83 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 2090.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232219.28
C13024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1109448.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12538.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121986.1
C13024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 152185.55 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | -5858.19 | 4694.97 | 4864.66 | 5180.52 | 5161.67 | 5059.84 | 4474.3 | 4793.33 | 4084.3 | 4878.57 | 301.06 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9751.59 | 15480.02 | 12130.39 | 11761.15 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 3170.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415494.22
C13024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 563.64 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | -11113.59 | 1482.51 | 1536.1 | 1635.83 | 1629.88 | 1597.73 | 1412.84 | 1513.57 | 1289.69 | 1540.49 | 95.06 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 101641.21 | 165458.47 | 2954.03 | 16677.78 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 293.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330514.66
C13024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 6881.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6881.94
C13026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 41278.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46823.16
C13026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3701.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3701.92
C13028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 3203.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1041.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4245.54
C13028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 29869.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32919.04
C13028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 12413 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | -1589.39 | 142.38 | 147.52 | 157.1 | 156.53 | 153.44 | 135.68 | 145.36 | 123.86 | 147.94 | 9.13 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 243.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15662.33
C13028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 118100.59 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 260.11 | 1606.13 | 1664.18 | 1772.24 | 1765.79 | 1730.95 | 1530.65 | 1639.78 | 1397.23 | 1668.95 | 102.99 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 2743.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172946.77
C13030 | H&S Quality Environmental | LAB | Labour | BUDGET | Approved Early Budget | 9153.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10524.24
C13030 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 2762.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | -46263.35 | 8975.82 | 9300.23 | 9904.09 | 9868.07 | 9673.37 | 8553.95 | 9163.86 | 7808.35 | 9326.84 | 575.56 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 15330.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283069.58
C13030 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 290640.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66061.74 | 8892.7 | 9214.1 | 9812.37 | 9776.68 | 9583.79 | 8474.73 | 8457.58 | 323.1 | 385.94 | 23.82 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 634.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428202.35
C13030 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 692776.89 | 8972.32 | 8972.32 | 8972.32 | 8972.32 | 9408.85 | 11416.86 | 11416.86 | 76696.36 | 10017.84 | 10379.91 | 11053.88 | 11013.67 | 10796.37 | 9547 | 10227.71 | 8714.83 | 10409.6 | 642.38 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 17406.15 | 2074.7 | 1333.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110913.99
C13030 | H&S Quality Environmental | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | -88457.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6369.3
C13034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 7049.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7049.43
C13034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 27831.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8129.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35960.91
C13034 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1435.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5973.93
C13034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 241762.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58332.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300094.71
C13034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 9182.85 | 9182.85 | 13646.18 | 19597.29 | 19597.29 | 19597.29 | 19597.29 | -95824.59 | 16326.62 | 16916.71 | 18015.1 | 17949.57 | 16316.81 | 10282.89 | 11016.07 | 9386.58 | 11211.99 | 691.9 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 74405.56 | 170942.94 | 170942.94 | 66741.08 | 17382.31 | 17382.31 | 17382.31 | 17382.31 | 4966.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915219.22
C13036 | Access, temporary roads and walkways | LAB | Labour | BUDGET | Approved Early Budget | 1143039.89 | 52141.82 | 52141.82 | 52141.82 | 52141.82 | 52141.82 | 55910.03 | 78519.29 | -45619.64 | 76611.15 | 79380.08 | 84534.19 | 84226.68 | 82564.92 | 73010.36 | 78216.1 | 66646.41 | 53858.94 | 3323.66 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 158862.57 | 103279.55 | 91164.57 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 24124.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3969636.4
C13036 | Access, temporary roads and walkways | MAT | Materials | BUDGET | Approved Early Budget | 408802.38 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 23514.82 | 630.18 | 652.96 | 695.35 | 692.82 | 679.16 | 600.56 | 643.38 | 548.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7350.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450625.73
C13036 | Access, temporary roads and walkways | MISC | Miscellaneous | BUDGET | Approved Early Budget | 37944.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52294.42
C13036 | Access, temporary roads and walkways | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 422325.88 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | -48235.51 | 7823.46 | 8106.22 | 8632.55 | 8601.15 | 7659.38 | 4269.69 | 4574.12 | 3897.52 | 2978.48 | 183.8 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 81572.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628886.08
C13036 | Access, temporary roads and walkways | STAFF | Staff | BUDGET | Approved Early Budget | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395
C13036 | Access, temporary roads and walkways | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 126144.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13644.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139788.46
C13038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 694331.4 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | -12880.91 | 10631.99 | 11016.26 | 11731.54 | 11688.87 | 11458.25 | 10132.28 | 10854.73 | 9249.1 | 11047.77 | 681.76 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 20438.79 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 10538.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268624.51
C13038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 4140.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140.5
C13038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 29376.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60426.82
C13038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4928.08 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | -4264.75 | 519.98 | 538.77 | 573.75 | 571.67 | 560.39 | 495.54 | 530.87 | 452.35 | 540.31 | 33.34 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 888.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21913.79
C13038 | Security & Access Control | STAFF | Staff | BUDGET | Approved Early Budget | 7661.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7661.27
C13038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | -64415.24 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | -8333.62 | 1502.8 | 8635.06 | 1658.22 | 1652.19 | 1619.59 | 1432.17 | 1534.29 | 1307.33 | 1561.57 | 96.37 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 16605.89 | 2994.46 | 78395.44 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 855.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104774.31
C13040 | Plant & Equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3673.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3673.63
C13040 | Plant & Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -2689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097.13
C13042 | Battersea Prelims Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | LAB | Labour | BUDGET | Approved Early Budget | 961341.94 | 71681.84 | 66679.04 | 66679.04 | 66679.04 | 66679.04 | 68966.86 | 88003.22 | -186335.09 | 55480.09 | 70465.54 | 83785.45 | 81383.25 | 82068.59 | 67337.16 | 72138.4 | 53638.61 | 53893.79 | 3325.81 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 98939.37 | 72497.29 | 48464.63 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 4703.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060511.07
C13044 | Craneage | MAT | Materials | BUDGET | Approved Early Budget | 38039.17 | 3134.66 | 2336.06 | 2336.06 | 2733.51 | 2781.2 | 3771.72 | 6161.25 | -20412.29 | 4288.61 | 5242.2 | 5777.84 | 4906.86 | 4718.71 | 3337.09 | 3575.03 | 2840.07 | 2953.43 | 182.26 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5110.71 | 1794.17 | 1553.25 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 319.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140626.49
C13044 | Craneage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4793.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4793.62
C13044 | Craneage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1958145.72 | 161808.56 | 154469.36 | 154469.36 | 164571.55 | 165783.81 | 254955.44 | 205270.72 | -310212.34 | 83284.06 | 30915.74 | 48627.79 | 43936.36 | 44124.35 | 31479.67 | 87183.5 | 21232.41 | 23426.2 | 1445.64 | 44921.94 | 71006.02 | 71006.02 | 44921.94 | 44921.94 | 44921.94 | 55355.57 | 44921.94 | 41928.98 | 23971.27 | 19417.06 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 2648.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3899737.18
C13044 | Craneage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 158749.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19913.85 | 38117.8 | 39495.48 | 37997.94 | 29315.65 | 25263.78 | 17737.43 | 15706.75 | 15863.16 | 19222.08 | 979.23 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 36860.14 | 30428.55 | 26081.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694304.23
C13045 | Tower cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13046 | Mobile cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13046 | Mobile cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13050 | Passenger/good hoists | LAB | Labour | BUDGET | Approved Early Budget | 21411.29 | 10784.94 | 10784.94 | 15346.46 | 15733.21 | 15733.21 | 15733.21 | 15733.21 | -27029.36 | 24555.43 | 25442.93 | 27094.93 | 26996.36 | 26463.73 | 23401.3 | 25069.85 | 21361.53 | 25515.7 | 1574.59 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 25761.07 | 9207.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845963.27
C13050 | Passenger/good hoists | MAT | Materials | BUDGET | Approved Early Budget | 18.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.86
C13050 | Passenger/good hoists | MISC | Miscellaneous | BUDGET | Approved Early Budget | -14111.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14111.51
C13050 | Passenger/good hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 29873.06 | 3366.9 | 3366.9 | 22883.19 | 14894 | 6594 | 6594 | 6594 | -23557.32 | 6052.93 | 6271.7 | 12683.7 | 6654.63 | 6523.33 | 5768.44 | 6179.74 | 5265.63 | 6289.64 | 388.14 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 22904.57 | 22904.57 | 12060.98 | 12060.98 | 12060.98 | 10398.9 | 6243.71 | 2006.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305694.09
C13052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 369438.73 | 25363.44 | 25363.44 | 25363.44 | 25363.44 | 25363.44 | 14931.64 | 12663.85 | -27772.17 | 19299.6 | 19997.14 | 21295.54 | 21218.08 | 20799.45 | 18392.5 | 19703.91 | 16789.32 | 10050.84 | 620.24 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 12390.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869370.13
C13052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | -217.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832.1
C13052 | Scaffolding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 20503.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20503.54
C13052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 167483.38 | 21290.12 | 21290.12 | 21290.12 | 3201.04 | 1809.57 | 4527.04 | 5614.03 | -76954.93 | 7673.35 | 8928.49 | 11117.48 | 11077.04 | 10858.49 | 5540.44 | 3874.44 | 3301.33 | 3943.34 | 243.35 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 6707 | 2378.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298126.15
C13054 | Surveyor and monitoring | LAB | Labour | BUDGET | Approved Early Budget | 1904.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904.32
C13054 | Surveyor and monitoring | MAT | Materials | BUDGET | Approved Early Budget | 63.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.07
C13054 | Surveyor and monitoring | MISC | Miscellaneous | BUDGET | Approved Early Budget | 326.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.94
C13054 | Surveyor and monitoring | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 12277.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12277.68
C13056 | Communication and radios | MAT | Materials | BUDGET | Approved Early Budget | 25311.6 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | -21094.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25311.6
C13056 | Communication and radios | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8995.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9301.68
C13056 | Communication and radios | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2072.96 | 2321.86 | 2405.77 | 2561.98 | 2552.66 | 2502.3 | 2212.73 | 2370.5 | 2019.85 | 2412.65 | 148.89 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 1321.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108180.82
C13058 | Hoarding and fences | LAB | Labour | BUDGET | Approved Early Budget | 47513.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -965.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46547.65
C13058 | Hoarding and fences | MAT | Materials | BUDGET | Approved Early Budget | 21279.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22182.68
C13058 | Hoarding and fences | MISC | Miscellaneous | BUDGET | Approved Early Budget | 64.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.4
C13058 | Hoarding and fences | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14393.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14232.08
C13058 | Hoarding and fences | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 60834.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54014.1 | 0 | 9409.08 | 40080.02 | 0 | 0 | 0 | 3119.78 | 37216.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10570.15 | 42280.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114751.24 | 41727.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414003.58
C13061 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13061 | PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13061 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13065 | Maintenance of protective equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13065 | Maintenance of protective equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | LAB | Labour | BUDGET | Approved Early Budget | 57639.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3895.68 | 46472.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108007.37
C13077 | Set-up of assembly and store areas | MAT | Materials | BUDGET | Approved Early Budget | 238193.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 3293.16 | 39284.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281098.86
C13077 | Set-up of assembly and store areas | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7053.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7053.56
C13077 | Set-up of assembly and store areas | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 25913.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286.17 | 17348.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44548.07
C13077 | Set-up of assembly and store areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798.27 | 21451.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23250.02
C13080 | Temporary Works | LAB | Labour | BUDGET | Approved Early Budget | 81602.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718.81 | 0 | 0 | 0 | 0 | 0 | 3920.9 | 20022.24 | 20043.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60509.37 | 80679.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268495.74
C13080 | Temporary Works | MAT | Materials | BUDGET | Approved Early Budget | 1121730.31 | 10145.72 | 25749.41 | 22350.79 | 22802.83 | 22802.83 | 54695.87 | 112517.55 | -218849.94 | 84255.93 | 53390.71 | 45202.94 | 29330.46 | 26387.17 | 27094.74 | 16783.76 | 24733.03 | 17082.25 | 2592.05 | 32756.81 | 32756.81 | 32756.81 | 56651.2 | 26255.94 | 26255.94 | 74044.73 | 101301.1 | 90706.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974283.86
C13080 | Temporary Works | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497
C13080 | Temporary Works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 338941.53 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6360.39 | 3224.36 | 3340.9 | 3557.82 | 3544.88 | 3474.94 | 3072.82 | 3291.91 | 2804.97 | 3350.46 | 206.76 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 26402.09 | 32143.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521767.18
C13080 | Temporary Works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 565826.41 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | -17329.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565826.41
C13080 | Temporary Works | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 162.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.27
C13081 | Temporary works for D-Walls and piling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13082 | Sheet Piling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13082 | Sheet Piling | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | LAB | Labour | BUDGET | Approved Early Budget | 17808.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17808.01
C23112 | General | MAT | Materials | BUDGET | Approved Early Budget | 4594.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594.05
C23112 | General | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14777.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54777.5
C23112 | General | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3782.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3662.31
C23112 | General | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794.35 | 3524.77 | 3753.63 | 3739.98 | 3666.19 | 3241.93 | 3473.08 | 2959.35 | 3534.85 | 218.14 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 1936.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154854.34
C23114 | Sewer Utilities | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5184
C23114 | Sewer Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107000
C23114 | Sewer Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23116 | Water Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 313071.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311941.7
C23118 | Gas Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 84015.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84015.52
C23118 | Gas Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.77
C23118 | Gas Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46110.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46110.85
C23120 | Other Utilities | LAB | Labour | BUDGET | Approved Early Budget | 40874.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40874.74
C23120 | Other Utilities | MAT | Materials | BUDGET | Approved Early Budget | 32786.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32786.95
C23120 | Other Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 247366.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.91 | 413.63 | 440.48 | 438.88 | 430.22 | 380.44 | 407.56 | 347.27 | 414.81 | 25.6 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 227.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265538.06
C23120 | Other Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4436.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4436.84
C23122 | Utilities Permanent Connections | MAT | Materials | BUDGET | Approved Early Budget | 32.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.85
C23122 | Utilities Permanent Connections | MISC | Miscellaneous | BUDGET | Approved Early Budget | 271549.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291549.29
C23122 | Utilities Permanent Connections | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 100.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23122 | Utilities Permanent Connections | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55706.52 | 43115.14 | 0 | 151799.73 | 182109.92 | 269022.95 | 200234.92 | 757669.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252658.49
C23124 | UXO Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7350
C23140 | Work to existing Jetty for river traffic use and other river facilities | MAT | Materials | BUDGET | Approved Early Budget | 563483.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40638.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522845.26
C23140 | Work to existing Jetty for river traffic use and other river facilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 273.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.58
C23140 | Work to existing Jetty for river traffic use and other river facilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 11055.17 | 0 | 3406.73 | 0 | 0 | 0 | 0 | 0 | -3406.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11055.17
C23140 | Work to existing Jetty for river traffic use and other river facilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 95715.68 | 26415.1 | 42264.17 | 0 | 0 | 0 | 0 | 0 | -19333.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145061.08
C23150 | Haulage of the spoil from the overrun tunnels to muck bin area | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
C23161 | Conveyor maintenance before and after TBM excavation | LAB | Labour | BUDGET | Approved Early Budget | 586633.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588003.2
C23161 | Conveyor maintenance before and after TBM excavation | MAT | Materials | BUDGET | Approved Early Budget | 51586.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51586.34
C23161 | Conveyor maintenance before and after TBM excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
C23161 | Conveyor maintenance before and after TBM excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 89784.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90378.52
C23161 | Conveyor maintenance before and after TBM excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 728600.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -240.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728360.26
C23162 | Conveyor maintenance - TBM period | LAB | Labour | BUDGET | Approved Early Budget | 1048282.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048282.65
C23162 | Conveyor maintenance - TBM period | MAT | Materials | BUDGET | Approved Early Budget | -670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -670
C23162 | Conveyor maintenance - TBM period | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481
C23162 | Conveyor maintenance - TBM period | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 24606.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1530.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23075.88
C23162 | Conveyor maintenance - TBM period | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 174823.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174823.27
C23163 | Dismantling of the outside conveyors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 356922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356922.01
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | MAT | Materials | BUDGET | Approved Early Budget | 111552.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63424.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48127.69
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 102610.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102610.7
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2486365.81 | 0 | 0 | 0 | -150000 | 0 | 0 | 0 | 149999.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -149757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2336608.79
C31101 | Battersea Station D-Walls | LAB | Labour | BUDGET | Approved Early Budget | 408837.48 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | -31271.09 | 2968.37 | 3075.66 | 3275.36 | 3263.44 | 3199.05 | 2828.85 | 3030.56 | 1383.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435693.03
C31101 | Battersea Station D-Walls | MAT | Materials | BUDGET | Approved Early Budget | 245573.83 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | -19309.63 | 1802.23 | 1867.36 | 1988.61 | 1981.38 | 1942.29 | 1717.52 | 1839.98 | 839.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261162.13
C31101 | Battersea Station D-Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17071
C31101 | Battersea Station D-Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 469772.51 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | -6521.36 | 530.07 | 549.23 | 584.89 | 582.76 | 571.26 | 505.15 | 541.17 | 247.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473617.56
C31101 | Battersea Station D-Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 19047032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19047031.99
C31102 | Battersea Station Demobilisation of d-wall grabs and bentonite plant (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31103 | Battersea Station Diaphragm wall prelims and Project management (Station Box) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31103 | Battersea Station Diaphragm wall prelims and Project management (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31107 | Battersea Station Install and supply plunge columns twin 356x406x634UC fixing and connections | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31107 | Battersea Station Install and supply plunge columns twin 356x406x634UC fixing and connections | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31109 | Battersea Station Cleaning d-walls surface | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31110 | Battersea Station Inclinometers & sonic loggin tubes and tests D-walls (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31111 | Battersea Station Install and supply B40 female coupler with starter bar set into box-out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31112 | Battersea Station Slab box-out 50 mm deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31112 | Battersea Station Slab box-out 50 mm deep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31150 | Battersea Station Piling | LAB | Labour | BUDGET | Approved Early Budget | 88566.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88566.55
C31150 | Battersea Station Piling | MAT | Materials | BUDGET | Approved Early Budget | 274041.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274041.13
C31150 | Battersea Station Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 40679.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40679.15
C31150 | Battersea Station Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4622918.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4622918.79
C31151 | Battersea Station Piling prelims & demobilise Piling Rig #1 & 2100m and 2400mm piling equipment | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31152 | Battersea Station Bore Piles excavation concrete reinforcement and backfilling (Station Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31152 | Battersea Station Bore Piles excavation concrete reinforcement and backfilling (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31153 | Battersea Station Install and supply plunge columns in bore piles fittings and connections included | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31153 | Battersea Station Install and supply plunge columns in bore piles fittings and connections included | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31155 | Battersea Station Sonic loggin tubes install grouting & tests piles (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31157 | Battersea Station Pile Mat remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31157 | Battersea Station Pile Mat remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | LAB | Labour | BUDGET | Approved Early Budget | 1357262.74 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 8184.63 | -34243.63 | 8393.51 | 8696.88 | 9261.56 | 9227.87 | 9045.81 | 7999.01 | 8569.35 | 3911.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521310.99
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | MAT | Materials | BUDGET | Approved Early Budget | 2465267.29 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 8628.34 | -48478.87 | 8393.51 | 8696.88 | 9261.56 | 9227.87 | 9045.81 | 7999.01 | 8569.35 | 3911.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2622300.71
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11810.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11810.42
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 211716.89 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 1003.2 | 37212.96 | 585.59 | 606.76 | 646.15 | 643.8 | 631.1 | 558.07 | 597.86 | 272.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269796.94
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9011.3 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 2930.1 | -45763.74 | 2147.17 | 2224.78 | 2369.23 | 2360.61 | 2314.04 | 2046.26 | 2192.16 | 1000.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27583.21
C31201 | Battersea Station Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31201 | Battersea Station Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31208 | Battersea Station Standard coupler to connect beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31208 | Battersea Station Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31214 | Battersea Station lower mall (basement level -1) beams: Lattice plank prep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31214 | Battersea Station lower mall (basement level -1) beams: Lattice plank prep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31215 | Plint on top of beams in Level B1 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | LAB | Labour | BUDGET | Approved Early Budget | 363435.99 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 209258.75 | 6941.3 | 7192.18 | 7659.17 | 7631.3 | 7480.74 | 6615.06 | 7086.72 | 3234.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712626.93
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | MAT | Materials | BUDGET | Approved Early Budget | 1075265.89 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | -218377.37 | 52671.54 | 54575.23 | 58118.77 | 57907.35 | 56764.86 | 50195.94 | 49332.15 | 21206.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709564.24
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2021.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021.12
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 184721.43 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | -88969.76 | 10026.33 | 10388.71 | 11063.24 | 11022.99 | 10805.51 | 9555.08 | 10236.37 | 4672.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285602.38
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | -11127.75 | 14653.86 | 15183.49 | 16169.35 | 16110.53 | 15792.67 | 13965.12 | 14960.85 | 6829.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329651.62
C31241 | Battersea Main Works Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31242 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31242 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31246 | Battersea Main Works Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31247 | Battersea Station Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31247 | Battersea Station Exposure of couplers in beams and slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31255 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31255 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31256 | Removal of temporary Props | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31258 | Bulkheads in the Western and Eastern entrances | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31258 | Bulkheads in the Western and Eastern entrances | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31259 | Making Good Prior to handover to MEP/Fitout and BPSDC | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | LAB | Labour | BUDGET | Approved Early Budget | 632854.55 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 18837.47 | -178866.32 | 17918.65 | 18566.27 | 19771.77 | 19699.85 | 19311.18 | 17076.45 | 7186.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880056.33
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | MAT | Materials | BUDGET | Approved Early Budget | 1312314.11 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 12211.91 | -63621.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447414.1
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7501.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7501.77
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 88487.68 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 3566.54 | -48998.53 | 2481.04 | 2570.71 | 2737.63 | 2727.67 | 2673.85 | 2364.43 | 995.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114076.9
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31266 | Battersea Station Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31267 | Battersea Station Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31270 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | LAB | Labour | BUDGET | Approved Early Budget | 476867.92 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | -24168.88 | 16910.02 | 17521.2 | 18658.84 | 18590.97 | 18224.17 | 16115.24 | 6782.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685269.29
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | MAT | Materials | BUDGET | Approved Early Budget | 1008631.12 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | -59739.7 | 8182.27 | 8478 | 9028.47 | 8995.63 | 8818.15 | 7797.7 | 3281.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099810.11
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 148907.16 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 13055.35 | 6000.33 | 6217.2 | 6620.88 | 6596.79 | 6466.64 | 5718.31 | 2406.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265168.23
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | -151015.8 | 23455.84 | 24303.6 | 25881.62 | 25787.47 | 25278.69 | 22353.4 | 9407.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177409.9
C31291 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31291 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31297 | Battersea Station Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31300 | Waterproofing system base slab (Ticket Hall) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31300 | Waterproofing system base slab (Ticket Hall) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31303 | Jacking Points | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31304 | Removal of Temp Props | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31308 | Extra Penetrations for B02 Gantry Slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31310 | Battersea Station Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 469085.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470638.72
C31310 | Battersea Station Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 1747487.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67604.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1815091.36
C31310 | Battersea Station Base Slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14900
C31310 | Battersea Station Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 98174.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7677.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90496.96
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31314 | Battersea Station Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31319 | Standard coupler | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31330 | Battersea Station West Core (Roof Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 18176.39 | 18176.39 | 18176.39 | 18176.39 | 18176.39 | 16878.07 | 0 | -7881.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99878.58
C31330 | Battersea Station West Core (Roof Slab) | MAT | Materials | BUDGET | Approved Early Budget | 14423.48 | 39758.62 | 39758.62 | 39758.62 | 39758.62 | 39758.62 | 36918.72 | 0 | -23424.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226711.05
C31330 | Battersea Station West Core (Roof Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1751.9 | 7270.7 | 7270.7 | 7270.7 | 7270.7 | 7270.7 | 6751.37 | 0 | -44509.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347.47
C31330 | Battersea Station West Core (Roof Slab) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 3526.22 | 3526.22 | 3526.22 | 3526.22 | 3526.22 | 3274.35 | 0 | 9770.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30676
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31340 | Couplers | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31370 | Battersea Station Ticket Hall Columns | LAB | Labour | BUDGET | Approved Early Budget | 139316.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -507.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138808.84
C31370 | Battersea Station Ticket Hall Columns | MAT | Materials | BUDGET | Approved Early Budget | 119313.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119493.99
C31370 | Battersea Station Ticket Hall Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 33941.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2442.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31498.85
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31380 | Battersea Station Platform Columns | LAB | Labour | BUDGET | Approved Early Budget | 104759.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32104.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72655.85
C31380 | Battersea Station Platform Columns | MAT | Materials | BUDGET | Approved Early Budget | 83464.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -654.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82809.58
C31380 | Battersea Station Platform Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7160.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -381.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6778.19
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31386 | Making good columns (embedded sockets,...) between B3 and B2 for cladding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31390 | Battersea Station Base Slab Columns | LAB | Labour | BUDGET | Approved Early Budget | 87124.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87124.15
C31390 | Battersea Station Base Slab Columns | MAT | Materials | BUDGET | Approved Early Budget | 16929.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31968.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48898.38
C31390 | Battersea Station Base Slab Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16524.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12477.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4047.14
C31391 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31391 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31400 | Battersea Station Platform Construction | LAB | Labour | BUDGET | Approved Early Budget | 362617.26 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | -20319.34 | 7817.63 | 8100.18 | 8626.12 | 8594.74 | 8425.17 | 5587.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433811.83
C31400 | Battersea Station Platform Construction | MAT | Materials | BUDGET | Approved Early Budget | 1228667.28 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | -301.56 | 3127.05 | 3240.07 | 3450.45 | 3437.9 | 3370.07 | 2235.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304725.16
C31400 | Battersea Station Platform Construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 92380.44 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 47111.12 | 781.76 | 810.02 | 862.61 | 859.47 | 842.52 | 558.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150871.33
C31400 | Battersea Station Platform Construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1631.8 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | -186445.65 | 27361.69 | 28350.61 | 30191.4 | 30081.57 | 29488.08 | 19556.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191090.48
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31403 | Concrete Mix C50/60 primary structures B4 level (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31403 | Concrete Mix C50/60 primary structures B4 level (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31405 | Reinforcement for estructural "in situ" elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31405 | Reinforcement for estructural "in situ" elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31407 | 700mmm x 700mm Linear Insert to form channel in mass concrete at | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31410 | Construction of connection between box, headwall and tunnels inc | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31410 | Construction of connection between box, headwall and tunnels inc | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31411 | Reinforcement for estructural "in situ" elements (walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31411 | Reinforcement for estructural "in situ" elements (walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31412 | PC Beams 650x650 mm & 1000x1000 mm (under slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31416 | Waterproofing D Wall before first stage concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31420 | Battersea Station Mezzanine | LAB | Labour | BUDGET | Approved Early Budget | 60110.73 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | -11380.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59756.22
C31420 | Battersea Station Mezzanine | MAT | Materials | BUDGET | Approved Early Budget | 59935.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26133.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33801.61
C31420 | Battersea Station Mezzanine | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22051.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23711.15
C31420 | Battersea Station Mezzanine | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | -12805.61 | 1532.16 | 1587.54 | 1690.62 | 1684.47 | 1651.23 | 1460.15 | 1564.26 | 1332.88 | 1592.08 | 28.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15491.38
C31421 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31421 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31423 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31423 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31424 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31424 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31425 | PC Beams 650x650 mm & 1000x1000 mm (under slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31427 | Precast Walls - 300mm wide | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31427 | Precast Walls - 300mm wide | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31440 | Battersea Station Walls Platform | LAB | Labour | BUDGET | Approved Early Budget | 906.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906.54
C31440 | Battersea Station Walls Platform | MAT | Materials | BUDGET | Approved Early Budget | 2082.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082.72
C31445 | Precast Walls - 250mm (Platform) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31445 | Precast Walls - 250mm (Platform) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31450 | Battersea Station STAIRCASES | LAB | Labour | BUDGET | Approved Early Budget | 5427.93 | 8235.38 | 8235.38 | 8235.38 | 8235.38 | 8235.38 | 2647.09 | 0 | 19002.72 | 225.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68479.79
C31450 | Battersea Station STAIRCASES | MAT | Materials | BUDGET | Approved Early Budget | 65853.66 | 9304.08 | 9304.08 | 9304.08 | 9304.08 | 9304.08 | 2990.6 | 0 | 213683.52 | 1801.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330849.41
C31450 | Battersea Station STAIRCASES | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 3559.07 | 3559.07 | 3559.07 | 3559.07 | 3559.07 | 1143.99 | 0 | -13925.53 | 450.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5464.12
C31450 | Battersea Station STAIRCASES | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 72213.15 | 72213.15 | 72213.15 | 72213.15 | 72213.15 | 23211.37 | 0 | -358010.78 | 3152.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29418.49
C31451 | Stairs Flight | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31451 | Stairs Flight | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31451 | Stairs Flight | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31452 | Stairs landing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31452 | Stairs landing | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31453 | Making good staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31464 | Mass fill concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31464 | Mass fill concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31465 | Banagher Quotation - Landing Beam | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31466 | In-Situ Mass Fill Stairs Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31467 | Central Dividing Wall for East & West Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31467 | Central Dividing Wall for East & West Core | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31469 | Fireproofing - MITIE or ANOTHER | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | LAB | Labour | BUDGET | Approved Early Budget | 796341.65 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 33319.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910143.93
C31470 | Battersea Station West Core (in situ walls and precast walls) | MAT | Materials | BUDGET | Approved Early Budget | 687410.87 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 54635.56 | 8028.45 | 1485.46 | 5874.96 | 5853.59 | 5738.1 | 5074.08 | 5435.87 | 4631.8 | 5532.54 | 48.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859305.48
C31470 | Battersea Station West Core (in situ walls and precast walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 355.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355.8
C31470 | Battersea Station West Core (in situ walls and precast walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 397784.95 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | -17912.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426190.25
C31470 | Battersea Station West Core (in situ walls and precast walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 15600.92 | 54603.22 | 54603.22 | 54603.22 | 231891.07 | 0 | 0 | 111624.28 | 111218.22 | 109023.92 | 96407.49 | 103281.48 | 88004.12 | 105118.28 | 636000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771979.44
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31474 | Battersea Station Precast Walls between 200-400 mm wide including connections to RC columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31474 | Battersea Station Precast Walls between 200-400 mm wide including connections to RC columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31475 | Battersea Station GL B/C 2-3 406mm x 16mm thick Dia. CHS Diagonal Bracing to Western Core Walls from | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31476 | Precast Walls - 250 mm thick (lift shaft) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31476 | Precast Walls - 250 mm thick (lift shaft) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31479 | KILNBRIDGE structural steel work | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31490 | Battersea Station East Core (in situ walls and precast walls) | LAB | Labour | BUDGET | Approved Early Budget | 256995.88 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 232044.48 | 17001.42 | 3145.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646216.68
C31490 | Battersea Station East Core (in situ walls and precast walls) | MAT | Materials | BUDGET | Approved Early Budget | 306203.15 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 150692.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555209.4
C31490 | Battersea Station East Core (in situ walls and precast walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 105436.19 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 110684.1 | 3778.09 | 699.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292400.63
C31490 | Battersea Station East Core (in situ walls and precast walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | -15923.13 | 18418.2 | 3407.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38269.86
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31498 | Scabbling downstand kickers | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31500 | Battersea Station West & East Cores (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 94430.87 | 13717.84 | 13717.84 | 13717.84 | 13717.84 | 8638.28 | 4828.61 | 4828.61 | 95452.34 | 1195.98 | 1239.21 | 1319.67 | 1314.87 | 1288.93 | 1139.77 | 1221.04 | 1040.42 | 1242.76 | 21.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274074.63
C31500 | Battersea Station West & East Cores (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 111253.24 | 13301.95 | 13301.95 | 13301.95 | 13301.95 | 8376.39 | 4682.22 | 4682.22 | 145244.2 | 1025.14 | 1062.19 | 1131.15 | 1127.04 | 1104.8 | 976.95 | 1046.61 | 891.8 | 1065.23 | 18.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336895.76
C31500 | Battersea Station West & East Cores (Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 81812.27 | 4188.09 | 4188.09 | 4188.09 | 4188.09 | 2637.29 | 1474.19 | 1474.19 | -114529.64 | 341.71 | 354.06 | 377.05 | 375.68 | 368.27 | 325.65 | 348.87 | 297.27 | 355.08 | 6.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7229.44
C31500 | Battersea Station West & East Cores (Slabs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 30191.73 | 30191.73 | 30191.73 | 30191.73 | 19012.08 | 10627.34 | 10627.34 | -139857.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21176
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31508 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31508 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | LAB | Labour | BUDGET | Approved Early Budget | 45792.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16603.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62395.63
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | MAT | Materials | BUDGET | Approved Early Budget | 56461.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12638.89 | 4422.33 | 9869.28 | 10510.09 | 10471.85 | 10265.25 | 9077.33 | 9724.56 | 4438.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112602.29
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1597.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.7
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12965.92 | 14522.72 | 15047.61 | 16024.64 | 15966.35 | 15651.34 | 13840.14 | 14826.96 | 12633.76 | 15090.65 | 266.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146836.16
C31547 | Installation of drainage Channel | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31547 | Installation of drainage Channel | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31547 | Installation of drainage Channel | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | LAB | Labour | BUDGET | Approved Early Budget | 97401.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3998.73 | 209.67 | 217.24 | 231.35 | 230.51 | 225.96 | 199.81 | 214.06 | 97.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103026.68
C31601 | Battersea Crossover D-Walls | MAT | Materials | BUDGET | Approved Early Budget | 95910.38 | 693.47 | 693.47 | 693.47 | 693.47 | 693.47 | 693.47 | 272.44 | -3734.87 | 358.46 | 371.41 | 395.53 | 394.09 | 386.32 | 341.61 | 365.97 | 167.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99389.21
C31601 | Battersea Crossover D-Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 92.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.12
C31601 | Battersea Crossover D-Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 149682.96 | 207.35 | 207.35 | 207.35 | 207.35 | 207.35 | 207.35 | 81.46 | -1228.95 | 108.21 | 112.13 | 119.41 | 118.97 | 116.62 | 103.13 | 110.48 | 50.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150618.95
C31601 | Battersea Crossover D-Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 7118782.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7118782.01
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31603 | Battersea Crossover Diaphragm wall prelims and Project management (Xover Box) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31603 | Battersea Crossover Diaphragm wall prelims and Project management (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31604 | Battersea Crossover Guide Wall install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31604 | Battersea Crossover Guide Wall install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31608 | Battersea Crossover Cleaning d-walls surface | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31608 | Battersea Crossover Cleaning d-walls surface | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31610 | Battersea Crossover B40 female coupler with starter bar set into box-out (h above) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31611 | Battersea Crossover Slab Box-out - 50mm deep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31640 | Battersea Crossover Piling | LAB | Labour | BUDGET | Approved Early Budget | 21718.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21718.78
C31640 | Battersea Crossover Piling | MAT | Materials | BUDGET | Approved Early Budget | 5036.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5036.6
C31640 | Battersea Crossover Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2454.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454.37
C31640 | Battersea Crossover Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1613698.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613698.01
C31641 | Battersea Crossover Piling prelims & Mobilise Piling Rig #1 & equipment (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31641 | Battersea Crossover Piling prelims & Mobilise Piling Rig #1 & equipment (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31642 | Battersea Crossover Bore Piles excavation concrete reinforcement and backfilling (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31642 | Battersea Crossover Bore Piles excavation concrete reinforcement and backfilling (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31643 | Battersea Crossover Install and supply plunge columns in bore piles fittings and connections include | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31644 | Battersea Crossover Cropping Bore piles and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31644 | Battersea Crossover Cropping Bore piles and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31645 | Battersea Crossover Sonic loggin tubes install grouting & tests piles (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31646 | Battersea Crossover Pile Mat install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31646 | Battersea Crossover Pile Mat install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31647 | Battersea Crossover Pile Mat remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | LAB | Labour | BUDGET | Approved Early Budget | 659091.06 | 53364.91 | 53364.91 | 53364.91 | 53364.91 | 34223.15 | 23588.84 | 23588.84 | 10214.08 | 19290.7 | 19987.91 | 21285.72 | 21208.29 | 17077.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063015.61
C31670 | Battersea Crossover Beams (Basement level -1) | MAT | Materials | BUDGET | Approved Early Budget | 1155349.88 | 35921.59 | 35921.59 | 35921.59 | 35921.59 | 23036.67 | 15878.38 | 15878.38 | 92084.16 | 14146.51 | 14657.8 | 15609.53 | 15552.74 | 12523.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518403.82
C31670 | Battersea Crossover Beams (Basement level -1) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 79.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.5
C31670 | Battersea Crossover Beams (Basement level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 236893.44 | 10241.34 | 10241.34 | 10241.34 | 10241.34 | 6567.82 | 4526.97 | 4526.97 | -39492.48 | 3429.46 | 3553.41 | 3784.13 | 3770.36 | 3035.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271561.42
C31670 | Battersea Crossover Beams (Basement level -1) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 5270.13 | 5270.13 | 5270.13 | 5270.13 | 3379.76 | 2329.55 | 2329.55 | -23761.18 | 6001.55 | 6218.46 | 6622.22 | 6598.13 | 5312.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36111.52
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31678 | Battersea Crossover Insitu cruciform stitch connection between precast & instu beams to top of plung | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31680 | Battersea Crossover Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31682 | Waterproofing capping beam | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31685 | Wateproofing of beams Level B01 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31686 | Protection of waterproofing in beams with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | LAB | Labour | BUDGET | Approved Early Budget | 94316.7 | 25593.23 | 25593.23 | 25593.23 | 12010.23 | 6577.03 | 6577.03 | 6577.03 | -82055.58 | 12760.25 | 13221.44 | 14079.9 | 2004.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162847.82
C31690 | Battersea Crossover Slabs(Basement level -1) | MAT | Materials | BUDGET | Approved Early Budget | 212160.94 | 33041.9 | 33041.9 | 33041.9 | 15505.69 | 8491.21 | 8491.21 | 8491.21 | -7964.88 | 38280.74 | 39664.3 | 42239.69 | 6012.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470498.1
C31690 | Battersea Crossover Slabs(Basement level -1) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3229.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229.96
C31690 | Battersea Crossover Slabs(Basement level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 32743.04 | 6970.11 | 6970.11 | 6970.11 | 3270.89 | 1791.2 | 1791.2 | 1791.2 | -30632.6 | 8256.63 | 8555.05 | 9110.52 | 1296.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58884.23
C31690 | Battersea Crossover Slabs(Basement level -1) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 13626.07 | 13626.07 | 13626.07 | 6394.36 | 3501.67 | 3501.67 | 3501.67 | -57777.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.276e-12
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31695 | Battersea Crossover 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31695 | Battersea Crossover 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31698 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31698 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31710 | Battersea Crossover Beams (Basement Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 420740.38 | 32433.33 | 32433.33 | 32433.33 | 32433.33 | 12741.67 | 0 | 0 | -163118.94 | 13124.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413221.16
C31710 | Battersea Crossover Beams (Basement Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 496259.47 | 64967.47 | 64967.47 | 64967.47 | 64967.47 | 25522.94 | 0 | 0 | -265134.61 | 32499.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549017.01
C31710 | Battersea Crossover Beams (Basement Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 112389.94 | 33796.79 | 33796.79 | 33796.79 | 33796.79 | 13277.31 | 0 | 0 | -128721.47 | 16874.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149007.59
C31710 | Battersea Crossover Beams (Basement Level -2) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14072.94 | 15762.66 | 16332.36 | 17392.81 | 2475.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66036.42
C31711 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31711 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31716 | Battersea Crossover Precast beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31718 | Battersea Crossover Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31719 | Battersea Crossover Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31722 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31722 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31723 | Saw concrete slab between GL 40 and GL41 - Subcontract | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31723 | Saw concrete slab between GL 40 and GL41 - Subcontract | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31730 | Battersea Crossover Slabs (Basement Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 39123.95 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18031.85 | -108318.63 | 7936.24 | 8223.08 | 8757 | 8725.14 | 1527.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96204.15
C31730 | Battersea Crossover Slabs (Basement Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 139373.48 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7464.36 | 269124.82 | 9258.95 | 9593.59 | 10216.5 | 10179.34 | 1781.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503437.83
C31730 | Battersea Crossover Slabs (Basement Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9068.9 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1518.53 | -6720.16 | 1984.06 | 2055.77 | 2189.25 | 2181.28 | 381.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108.08
C31730 | Battersea Crossover Slabs (Basement Level -2) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 16663.02 | -54198.26 | 46956.09 | 48653.21 | 51812.24 | 51623.76 | 9036.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274227.67
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31735 | Battersea Crossover 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31735 | Battersea Crossover 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31738 | Standard couplers | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31739 | Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31740 | Battersea Crossover Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 218556.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2357.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216199.78
C31740 | Battersea Crossover Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 1215772.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78403.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137369.63
C31740 | Battersea Crossover Base Slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 9.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.04
C31740 | Battersea Crossover Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 45665.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45665.69
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31748 | Formwork "in situ" elements (Beams, walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31748 | Formwork "in situ" elements (Beams, walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31749 | Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31760 | Battersea Crossover Columns Intermediate | LAB | Labour | BUDGET | Approved Early Budget | 53222.38 | 40988.07 | 20494.03 | 0 | 0 | 0 | 731.93 | 20494.03 | -74752.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61177.72
C31760 | Battersea Crossover Columns Intermediate | MAT | Materials | BUDGET | Approved Early Budget | 53287.83 | 6703.45 | 3351.72 | 0 | 0 | 0 | 119.7 | 3351.72 | 2885.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69699.47
C31760 | Battersea Crossover Columns Intermediate | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9356.8 | 827.95 | 413.98 | 0 | 0 | 0 | 14.78 | 413.98 | 690.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11717.66
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31764 | Battersea Crossover Precast Concrete Beam connecting to Plunge Column; to include Insitu stitch at c | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31770 | Battersea Crossover Columns Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 64636.78 | 27278.62 | 27278.62 | 27278.62 | 8768.13 | 0 | 0 | 0 | -68967.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86273.58
C31770 | Battersea Crossover Columns Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 113723.32 | 17821.97 | 17821.97 | 17821.97 | 5728.49 | 0 | 0 | 0 | -51691.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121226.49
C31770 | Battersea Crossover Columns Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 35866.07 | 1080.69 | 1080.69 | 1080.69 | 347.37 | 0 | 0 | 0 | 1356.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40811.86
C31770 | Battersea Crossover Columns Base Slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31775 | Battersea Crossover Supply and place concrete to protect columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31776 | Couplers for columns between B4 and B2. (Crossover) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31780 | Battersea Crossover Walls (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 102260.18 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | -49497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101501.38
C31780 | Battersea Crossover Walls (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 88094.2 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | -37030.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106449.95
C31780 | Battersea Crossover Walls (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22667.17 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | -18643.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17290.74
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31789 | In situ wall connection between d-walls and tunnel eyes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31790 | Vent Shaft, Stairs and Others | LAB | Labour | BUDGET | Approved Early Budget | 13308.61 | 40370.94 | 40370.94 | 40370.94 | 12120.1 | 7411.63 | 7411.63 | 7411.63 | -82201.8 | 0 | 0 | 0 | 0 | 5348.25 | 5757.46 | 6167.98 | 5255.61 | 6277.67 | 387.4 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 10748.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246897.42
C31790 | Vent Shaft, Stairs and Others | MAT | Materials | BUDGET | Approved Early Budget | 12028.94 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | -229203.13 | 0 | 13140.54 | 17035.87 | 16973.9 | 16639.01 | 14713.51 | 15762.61 | 13431.01 | 16042.94 | 990.02 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 27467.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441648.14
C31790 | Vent Shaft, Stairs and Others | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 26072.09 | 26072.09 | 26072.09 | 5073.71 | 1573.98 | 1573.98 | 1573.98 | 17066.88 | 0 | 3427.97 | 4444.14 | 4427.97 | 4340.61 | 3838.31 | 4111.98 | 3503.74 | 4185.11 | 258.27 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 7165.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200959.77
C31790 | Vent Shaft, Stairs and Others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 16520.22 | 16520.22 | 16520.22 | 16520.22 | 25459.54 | 66580.39 | 66580.39 | -224701.2 | 0 | 35422.33 | 45922.78 | 45755.72 | 44852.98 | 39662.51 | 42490.51 | 36205.33 | 43246.18 | 2668.74 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 74043.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990770.61
C31791 | Concrete Upstands to receive cladding across Station & Crossover Box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31794 | Ramp Connections between Station & Crossover Box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31803 | KILNBRIDGE - Temporary Steel Structure for Vent Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31803 | KILNBRIDGE - Temporary Steel Structure for Vent Core | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31805 | Making good prior to handover to BPSDC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | LAB | Labour | BUDGET | Approved Early Budget | 333453.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333822.64
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | MAT | Materials | BUDGET | Approved Early Budget | 675208.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676458.22
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | MISC | Miscellaneous | BUDGET | Approved Early Budget | 27164.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27215.52
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 628300.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4079.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624221.04
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5280489.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280489.55
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33219 | Battersea Station Extra excavation sequencing & methodology to increased depth of capping beam to en | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33221 | Battersea Station allowance to import suitable fill l&c to D Wall plant tracking area (162m * 15m * | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33221 | Battersea Station allowance to import suitable fill l&c to D Wall plant tracking area (162m * 15m * | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33222 | Battersea Main Works PilingC Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33222 | Battersea Main Works PilingC Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | LAB | Labour | BUDGET | Approved Early Budget | 104368.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104368.81
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | MAT | Materials | BUDGET | Approved Early Budget | 441710.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441710.02
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4766.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4715.62
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 161539.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162159.03
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1703349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1703349
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1695.5 | 23737.03 | 23737.03 | 23737.03 | 10173.01 | 24904.54 | 27932.12 | 28941.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164857.92
C38010 | Dwarf Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1091.92 | 15286.81 | 15286.81 | 15286.81 | 6551.49 | 68612.81 | 31587.76 | 32729.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186433.84
C38010 | Dwarf Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1469.96 | 20579.39 | 20579.39 | 20579.39 | 8819.74 | -72027.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 569.37 | 7971.24 | 7971.24 | 7971.24 | 3416.25 | 4218.43 | 8307.86 | 8608.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49033.76
C38010 | Dwarf Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 204.08 | 2857.14 | 2857.14 | 2857.14 | 1224.49 | -9999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38012 | Drilling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38016 | Scabbling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 44321.62 | 45963.16 | 45963.16 | -1578.85 | 34834.69 | 36093.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205597.48
C38020 | Concrete Deck | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 50453.22 | 52321.86 | 52321.86 | 92218.16 | 53367.27 | 55296.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355978.47
C38020 | Concrete Deck | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 38425.71 | 39848.89 | 39848.89 | -118123.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 16481.72 | 17092.16 | 17092.16 | -14606.82 | 9327.39 | 9664.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55051.12
C38020 | Concrete Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 18089.37 | 18759.35 | 18759.35 | -55608.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38021 | Installation of Concrete for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38021 | Installation of Concrete for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38022 | Installation of Lattice Planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38022 | Installation of Lattice Planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38025 | Installation of Screed | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38025 | Installation of Screed | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 584.76 | 8186.61 | 8186.61 | 8186.61 | 3508.55 | -9629.11 | 4920.92 | 5098.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29043.73
C38030 | Retaining Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 593.62 | 8310.66 | 8310.66 | 8310.66 | 3561.71 | -6635.5 | 5807.58 | 6017.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34276.87
C38030 | Retaining Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 506.97 | 7097.58 | 7097.58 | 7097.58 | 3041.82 | -24841.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 235.97 | 3303.64 | 3303.64 | 3303.64 | 1415.85 | -7770.59 | 980.91 | 1016.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5789.42
C38030 | Retaining Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 510.2 | 7142.86 | 7142.86 | 7142.86 | 3061.22 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38032 | Installation of Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38032 | Installation of Formwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729.98 | 188.82 | 195.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114.45
C38040 | Bridge Build-up | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38042 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578.28 | 3878.9 | 1152.93 | 1194.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6804.71
C38060 | Waterproofing | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6307.89 | 26303.73 | 8435.61 | 8740.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49787.72
C38060 | Waterproofing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501.35 | -501.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.66 | 27.85 | 28.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.37
C38061 | Installation of Horizontal Waterproofing on Deck | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38061 | Installation of Horizontal Waterproofing on Deck | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38061 | Installation of Horizontal Waterproofing on Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38063 | Installation of Vertical Waterproofing on Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3832.73 | 991.41 | 1027.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5851.38
C38080 | Carriageway | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38082 | Installation of Bollards (HVM) and Baseplates | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38083 | Installation of Parapet Posts and Baseplates | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38083 | Installation of Parapet Posts and Baseplates | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43354 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 143288.26 | 88951.9 | 0 | 0 | 0 | 0 | 0 | 0 | 211559.34 | 0 | 0 | 0 | 153156.33 | 18207.4 | 117812.56 | 214204.66 | 519446.3 | 240596.76 | 160653.49 | 48196.05 | 14000 | 14000 | 14000 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986073.05
C43356 | Fire Suppression | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3178.5 | 0 | 0 | 893.57 | 1530.39 | 42184.59 | 96345.31 | 50728.3 | 82921.63 | 22840.28 | 17130.21 | 15611.33 | 22078.94 | 25885.65 | 10662.6 | 1522.69 | 4948.73 | 761.34 | 3045.37 | 761.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403030.77
C43358 | Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9545.63 | 0 | 0 | 2683.57 | 4596.04 | 4410.96 | 50734.02 | 84059.73 | -24545.56 | 10402.91 | 129563.55 | 103083.41 | 40665.93 | 56506.73 | 86779.21 | 100851.51 | 88784.13 | 89370.48 | 81568.29 | 56033.87 | 47285.97 | 19860.11 | 5201.46 | 1472.86 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058914.81
C43360 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 31144.12 | 15572.06 | 18975.31 | 35768.26 | 35768.26 | 35768.26 | 35768.26 | 49860.24 | 140918.15 | 5044.11 | 78183.75 | 189154.24 | 172760.88 | 137452.08 | 154955.16 | 549669.62 | 197666.18 | 173391.39 | 145648.77 | 337325.07 | 298863.7 | 208069.67 | 143126.71 | 102773.81 | 6305.14 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319964.2
C43362 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 52628.76 | 113354.25 | 113354.25 | -234259.85 | 34234.88 | 124633.6 | 96591.04 | 213576.66 | 208194.76 | 190491.12 | 115427.71 | 39656.14 | 708.15 | 13454.76 | 43196.87 | 25493.24 | 2832.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153568.92
C43362 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 32821.52 | 70692.5 | 91293.11 | 88278.15 | 102824.2 | 182604.47 | 234109.83 | 314871.65 | 314611.7 | 288006.1 | 186287.37 | 87880.64 | 3465.34 | 21950.09 | 133930.34 | 106679.28 | 55170.85 | 26463.89 | 46473.18 | 18072.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2406487.11
C43364 | Escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 172973.45 | 0 | 0 | 0 | 0 | 0 | 2444120.55 | 0 | 0 | 47957.76 | 319718.43 | 319718.43 | 303732.51 | 379665.63 | 439612.84 | 407641 | 59947.21 | 119894.41 | 119894.41 | 119894.41 | 107904.97 | 113899.69 | 17984.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5494559.86
C43366 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 78495.28 | 0 | 0 | 0 | 0 | 134177.35 | 174202.71 | -36701.61 | 0 | 329893.16 | 329893.16 | 0 | 0 | 59105.86 | 73309.59 | 73309.59 | 73309.59 | 32531.13 | 0 | 134706.37 | 235965.24 | 65978.63 | 69644.11 | 69644.11 | 73309.59 | 47193.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017966.91
C43369 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 10830 | 0 | 40551.74 | 58666.94 | 58666.94 | 58666.94 | 94751.4 | 268462.29 | -70850.09 | 234634.39 | 360403.87 | 968774.77 | 622236.13 | 823754.69 | 603738.46 | 489015.25 | 215783.21 | 230474.83 | 77590.13 | 101004.91 | 112482.74 | 45911.32 | 8493.59 | 12625.61 | 0 | 0 | 16528.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5443198.14
C43369 | M&E Labour | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43369 | M&E Labour | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9796.34 | 0 | 1853.58 | 1853.58 | 3442.36 | 4501.54 | 4766.34 | 13504.62 | 31677.97 | 10262.82 | 15763.93 | 42373.86 | 27216.38 | 36030.73 | 26407.3 | 21389.35 | 9438.28 | 10080.88 | 3393.76 | 4417.92 | 4919.95 | 2008.14 | 371.51 | 552.24 | 0 | 0 | 722.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286746.31
C43371 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 9731.1 | 8058.7 | 9731.1 | 16117.4 | 35374.19 | 131912.7 | 137751.7 | 148438.12 | -297201.3 | 129426.06 | 198801.43 | 534383.3 | 343230.03 | 454389.16 | 333026.58 | 526450.11 | 232301.74 | 248118.03 | 83529.77 | 108736.98 | 121093.46 | 49425.9 | 9143.79 | 13592.12 | 0 | 0 | 9117.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3594679.18
C43371 | M&E Material | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43371 | M&E Material | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43372 | M&E Subcontractor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43372 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 43959.55 | 291.47 | 108.02 | 0 | 0 | 17371.31 | 16272.91 | 24281.48 | 78125.96 | 80220.64 | 118771.23 | 132173.83 | 202088.18 | 14069.43 | 40929.25 | 170597.7 | 186381.11 | 54814.28 | 17906.55 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1298362.9
C43600 | Floor finishes | LAB | Labour | BUDGET | Approved Early Budget | 6795.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6738.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.33
C43600 | Floor finishes | MAT | Materials | BUDGET | Approved Early Budget | 41516.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41578.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62.54
C43600 | Floor finishes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 107.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.5
C43600 | Floor finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 24875.09 | 24875.09 | 0 | 0 | 0 | 102518 | 128148 | -156528.34 | 143372.63 | 135039.47 | 86977.2 | 92624.59 | 64200.36 | 62933.71 | 55650.91 | 59618.9 | 73024.84 | 87225.98 | 5382.75 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3920700.53
C43601 | Station Box Underplatform level - Concrete subbase 200mm | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43601 | Station Box Underplatform level - Concrete subbase 200mm | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43601 | Station Box Underplatform level - Concrete subbase 200mm | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43606 | Front of House FoH Stone flooring and bedding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43608 | Floor Concrete Plinths for M&E Equipments | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43610 | Wall finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
C43610 | Wall finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 95166 | 190333 | 162386.92 | 203667.8 | 302974.42 | 391482.6 | 499494.21 | 497677.19 | 487858.18 | 360068.75 | 385742.16 | 328683.32 | 392602.38 | 24227.67 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10650571.95
C43611 | Double coat of Paint to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43614 | Station Box - FoH cladding (Stainless steel cladding to walls and columns, Stainless steel skirting | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43615 | Station Box - GRC cladding to walls, columns, escalators walls, beams | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43620 | Ceiling finishes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446
C43620 | Ceiling finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49506.86 | 10607.2 | 22595.8 | 26990 | 3331.13 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816917.03
C43621 | Concrete sealant to soffits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43621 | Concrete sealant to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43622 | Back of House BoH soffit insulation and grid ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43630 | Metalwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.13
C43630 | Metalwork | MAT | Materials | BUDGET | Approved Early Budget | 45193.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43658.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534.78
C43630 | Metalwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310.4
C43630 | Metalwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14820.38 | 14766.46 | 14475.13 | 32001.2 | 34282.93 | 46738.63 | 69784.46 | 6459.67 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915797.69
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43640 | SOR control desk and fit out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465.89 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275540
C43650 | Install furniture, fixtures and fittings, including seatings, advertisements, signage and others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23013.51 | 19609.36 | 46844.8 | 2890.81 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721174.17
C43653 | BoH office furniture | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43660 | Internal blockwork, Durasteel, Drywalling and acoustic cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 333545.86 | 126845.33 | 126845.33 | 126845.33 | 126843 | 126843 | 338247 | 394622 | 970810.42 | 216461.4 | 268141.51 | 277832.86 | 295872.42 | 266552.52 | 261293.53 | 218814.24 | 195073.88 | 121521.09 | 98437.08 | 10604.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4902052.61
C43661 | Acoustic wall lining Wall type E24 - West core shafts, East Vent shaft, gridline 41 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43662 | Durasteel - Wal ltypes G20, G21, Fire rated ceiling 01 & 02. Located in MainBox all levels and Cross | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43665 | Internal blockwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43670 | Internal doors | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8385.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8385.89
C43670 | Internal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49753.61 | 51551.84 | 137248.53 | 136749.26 | 268102.48 | 237077.2 | 253981.14 | 216412.34 | 258498.05 | 15952.03 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914132.69
C43674 | Intenal slab access hatches. Aver 1m*2m. 6nr | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43680 | Firestopping & BWIC | MAT | Materials | BUDGET | Approved Early Budget | 610.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -328.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282.44
C43680 | Firestopping & BWIC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4866.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5195.12
C43680 | Firestopping & BWIC | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 37170 | 37170 | -40035.41 | 50985.73 | 57107.52 | 116967.09 | 155335.37 | 185432.87 | 181774.34 | 160739.11 | 143725.6 | 73941.43 | 59340.79 | 1873.53 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1578783.96
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43690 | External Cladding & Roofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 48381.26 | 0 | 0 | 0 | 0 | 0 | 214176 | 214176 | 1155556.8 | 269004.66 | 301303.67 | 312193.58 | 332464.17 | 331254.75 | 324719.21 | 287142.15 | 307615.78 | 136754.77 | 163349.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4398092.28
C43691 | Eastern Headhouse envelope | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43695 | East Vent shaft cladding, roof, louvres and external doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43696 | West core cladding, roof, louvres and external doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C53400 | Completion of landscaping paving external areas and the like | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C53400 | Completion of landscaping paving external areas and the like | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138157.7
C63504 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241.51 | 9241.51 | 9241.51 | 9241.51 | 9241.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46207.55
C63506 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180279.09
C63508 | Station Ventilation | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292437.12
D08400 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 653334.02 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 82649.13 | 28011.5 | 26239.85 | 26239.85 | 26239.85 | 26491.92 | 26491.92 | 24986.73 | 24543.82 | 23910.06 | 23910.06 | 22390.48 | 22390.48 | 21839.54 | 20953.71 | 18080.18 | 16589.41 | 13298.17 | 9531.62 | 8346.92 | 7461.09 | 7461.09 | 7461.09 | 4976.46 | 3471.28 | 2369.4 | 2369.4 | 2369.4 | 1735.64 | 1735.64 | 1101.88 | 1101.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384573.92
D08410 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 1093.04 | 656.04 | 656.04 | 874.71 | 3280.18 | 3280.18 | 6560.36 | 21695.54 | 4236.58 | 7673.52 | 5801.34 | 12561.12 | 12486.97 | 7324.78 | 7529.97 | 6344.71 | 3558.46 | 1145.81 | 1186.15 | 306.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108252.12
D09999 | Nine Elms Temporary code (to be reconciled periodically) | LAB | Labour | BUDGET | Approved Early Budget | 1957.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1957.92
D09999 | Nine Elms Temporary code (to be reconciled periodically) | MAT | Materials | BUDGET | Approved Early Budget | -14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684
D14000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 7.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.35
D14000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | -75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75
D14000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 696.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696.09
D14000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 4575922.27 | 162080 | 165695 | 167505 | 170945 | 170945 | 172695 | 172695 | 132723.08 | 179471.73 | 168120.64 | 168120.64 | 168120.64 | 169735.63 | 169735.63 | 160091.83 | 157254.06 | 153193.5 | 153193.5 | 143457.41 | 143457.41 | 139927.5 | 134251.96 | 115841.05 | 106289.53 | 85202.35 | 61069.76 | 53479.3 | 47803.76 | 47803.76 | 47803.76 | 31884.55 | 22240.74 | 15180.92 | 15180.92 | 15180.92 | 11120.37 | 11120.37 | 7059.82 | 7059.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800659.13
D14000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
D14022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | 1398.21 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | -2752.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398.21
D14022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 23654.43 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 4662.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32470.52
D14022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 225603.57 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | -25868.85 | 27085.37 | 27085.37 | 27085.37 | 27085.37 | 23699.7 | 23699.7 | 13542.69 | 13542.69 | 13542.69 | 10157.02 | 10157.02 | 10157.02 | 10157.02 | 10157.02 | 6771.34 | 6771.34 | 6771.34 | 6771.34 | 6771.34 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600794.24
D14022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 99131.1 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 10113.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115038.11
D14022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 372543.42 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 137356.97 | 19384.82 | 19384.82 | 19384.82 | 19384.82 | 16961.72 | 16961.72 | 9692.41 | 9692.41 | 9692.41 | 7269.31 | 7269.31 | 7269.31 | 7269.31 | 7269.31 | 4846.21 | 4846.21 | 4846.21 | 4846.21 | 4846.21 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787575.5
D14024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 292622.25 | 8315.58 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 18538.37 | 12800 | 12800 | 12800 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 14300 | 14300 | 14300 | 14300 | 14300 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736527.06
D14024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 21244.38 | 1610.83 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | -9496.22 | 2672 | 2672 | 2672 | 2672 | 2338 | 2338 | 2338 | 2338 | 2004 | 1002 | 1002 | 1002 | 1002 | 1002 | 668 | 334 | 334 | 334 | 334 | 334 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57618.01
D14024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 560996.23 | 4433 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | -13052.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589613.74
D14024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23531.23 | 2059.05 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 41828.08 | 3383.67 | 3383.67 | 3383.67 | 3383.67 | 2960.71 | 2960.71 | 2960.71 | 2960.71 | 2537.75 | 1268.88 | 1268.88 | 1268.88 | 1268.88 | 1268.88 | 845.92 | 422.96 | 422.96 | 422.96 | 422.96 | 422.96 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123626.55
D14024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15178.92 | 15178.92 | 15178.92 | 15178.92 | 15178.92 | 13281.56 | 13281.56 | 13281.56 | 13281.56 | 11384.19 | 5692.1 | 5692.1 | 5692.1 | 5692.1 | 5692.1 | 3794.73 | 1897.37 | 1897.37 | 1897.37 | 1897.37 | 1897.37 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189736.55
D14024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 14151.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14151.79
D14026 | IT Equipment & running costs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | -1416.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2737e-13
D14026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 34186.23 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | -1026.08 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 100.54 | 100.54 | 100.54 | 64.63 | 64.63 | 64.63 | 64.63 | 14.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42938.65
D14026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -98.65 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 622 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 64.35 | 64.35 | 64.35 | 41.36 | 41.36 | 41.36 | 41.36 | 9.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3676.83
D14026 | IT Equipment & running costs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | -2207.79 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 542.59 | 542.59 | 542.59 | 348.81 | 348.81 | 348.81 | 348.81 | 77.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15502.59
D14026 | IT Equipment & running costs | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2980.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2980.17
D14028 | Environmental Control | LAB | Labour | BUDGET | Approved Early Budget | 33160.18 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 36746.45 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101394.87
D14028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 8696.19 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | -1222.37 | 422.21 | 422.21 | 422.21 | 422.21 | 375.3 | 375.3 | 187.65 | 187.65 | 140.74 | 140.74 | 140.74 | 140.74 | 117.28 | 93.83 | 93.83 | 93.83 | 93.83 | 93.83 | 46.91 | 46.91 | 46.91 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14073.83
D14028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 22556.09 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | -7495.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24323.54
D14028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 53172.82 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 9174.04 | 2867.28 | 2867.28 | 2867.28 | 2867.28 | 2548.69 | 2548.69 | 1274.35 | 1274.35 | 955.76 | 955.76 | 955.76 | 955.76 | 796.47 | 637.17 | 637.17 | 637.17 | 637.17 | 637.17 | 318.59 | 318.59 | 318.59 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95575.95
D14028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 166967.53 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 4225.12 | 3719.57 | 3719.57 | 3719.57 | 3719.57 | 3306.29 | 3306.29 | 1653.14 | 1653.14 | 1239.86 | 1239.86 | 1239.86 | 1239.86 | 1033.22 | 826.57 | 826.57 | 826.57 | 826.57 | 826.57 | 413.29 | 413.29 | 413.29 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214787.84
D14034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 1202.17 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | -3109.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202.17
D14034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 9028.02 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | -30509.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20097.38
D14034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 120889.6 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 104304.57 | 16744.95 | 16744.95 | 16744.95 | 16744.95 | 14884.4 | 14884.4 | 7442.2 | 7442.2 | 5581.65 | 5581.65 | 5581.65 | 5581.65 | 4651.38 | 3721.1 | 3721.1 | 3721.1 | 3721.1 | 3721.1 | 1860.55 | 1860.55 | 1860.55 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396853.67
D14034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2590 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | -54924.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2590
D14036 | General Logistics | LAB | Labour | BUDGET | Approved Early Budget | 533174.93 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 55828.76 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834232.74
D14036 | General Logistics | MAT | Materials | BUDGET | Approved Early Budget | 219743.45 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | -14357.16 | 8341.63 | 8341.63 | 8341.63 | 8341.63 | 7414.78 | 7414.78 | 3707.39 | 3707.39 | 2780.54 | 2780.54 | 2780.54 | 2780.54 | 2317.12 | 1853.7 | 1853.7 | 1853.7 | 1853.7 | 1853.7 | 926.85 | 926.85 | 926.85 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314124.35
D14036 | General Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17382.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17382.02
D14036 | General Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 109664.35 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 2256.92 | 6074.19 | 6074.19 | 6074.19 | 6074.19 | 5399.28 | 5399.28 | 2699.64 | 2699.64 | 2024.73 | 2024.73 | 2024.73 | 2024.73 | 1687.28 | 1349.82 | 1349.82 | 1349.82 | 1349.82 | 1349.82 | 674.91 | 674.91 | 674.91 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184650.19
D14036 | General Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 112118.84 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | -26600.52 | 3499.97 | 3499.97 | 3499.97 | 3499.97 | 3111.09 | 3111.09 | 1555.54 | 1555.54 | 1166.66 | 1166.66 | 1166.66 | 1166.66 | 972.22 | 777.77 | 777.77 | 777.77 | 777.77 | 777.77 | 388.89 | 388.89 | 388.89 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151007.41
D14038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 871232.29 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 16714.62 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 18200 | 18200 | 18200 | 18200 | 18200 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1598954.33
D14038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 1691.91 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 2277.39 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 171.28 | 171.28 | 171.28 | 171.28 | 171.28 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 65.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9720.82
D14038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17992 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 10703.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35732
D14038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 147.5 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | -9793.1 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 1399.1 | 1399.1 | 1399.1 | 1399.1 | 1399.1 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 538.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42727.55
D14038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 27135 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 1747.32 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 241.73 | 241.73 | 241.73 | 241.73 | 241.73 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 93.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37200.05
D14040 | Plant & Equipment | LAB | Labour | BUDGET | Approved Early Budget | 8904.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8904.13
D14040 | Plant & Equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | -560.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -560.5
D14040 | Plant & Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -3696.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3379.18
D14042 | Materials Handling Plant | LAB | Labour | BUDGET | Approved Early Budget | 40806.26 | 2306.58 | 2306.58 | 2306.58 | 3459.87 | 3459.87 | 4613.15 | 4613.15 | 12577.56 | 10400 | 10400 | 10400 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237649.6
D14042 | Materials Handling Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 47.16 | 47.16 | 47.16 | 70.74 | 70.74 | 94.32 | 94.32 | -471.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.6843e-14
D14042 | Materials Handling Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1101.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101.5
D14042 | Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 45515.56 | 735.5 | 735.5 | 735.5 | 1103.25 | 1103.25 | 1471 | 1471 | 13133.73 | 2167.07 | 2167.07 | 2167.07 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1066.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99329.12
D14044 | Craneage | LAB | Labour | BUDGET | Approved Early Budget | 489573.34 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 41490.51 | 1751.53 | 41400 | 17200 | 17200 | 23200 | 11700 | 17700 | 17200 | 17700 | 11700 | 23200 | 11700 | 17700 | 17200 | 17700 | 11700 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168948.98
D14044 | Craneage | MAT | Materials | BUDGET | Approved Early Budget | 90026.08 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1500 | 6926.04 | 2687.5 | 1117.5 | 1117.5 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131264.62
D14044 | Craneage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361
D14044 | Craneage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 947633.1 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 37932.9 | 133484.79 | 14727.5 | 6123.9 | 6123.9 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1589.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506853.59
D14044 | Craneage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 411.31 | 411.31 | 411.31 | 411.31 | 411.31 | 411.31 | 352.56 | -1745.42 | 1075 | 447 | 447 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
D14046 | Passenger/Goods Hoists | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 66474.22 | 4600 | 4600 | 4600 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194852.14
D14046 | Passenger/Goods Hoists | MISC | Miscellaneous | BUDGET | Approved Early Budget | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281
D14046 | Passenger/Goods Hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 178 | 0 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 33179.43 | 3789.33 | 3789.33 | 3789.33 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 9069.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155595.96
D14048 | General Plant | LAB | Labour | BUDGET | Approved Early Budget | 788 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | -2958.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788
D14048 | General Plant | MAT | Materials | BUDGET | Approved Early Budget | 79.35 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 1559.43 | 134.27 | 134.27 | 134.27 | 134.27 | 119.35 | 119.35 | 59.68 | 59.68 | 44.76 | 44.76 | 44.76 | 44.76 | 37.3 | 29.84 | 29.84 | 29.84 | 29.84 | 29.84 | 14.92 | 14.92 | 14.92 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4475.75
D14048 | General Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8492.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8492.6
D14048 | General Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 172973.71 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 81915.26 | 8971.35 | 8971.35 | 8971.35 | 8971.35 | 7974.53 | 7974.53 | 3987.26 | 3987.26 | 2990.45 | 2990.45 | 2990.45 | 2990.45 | 2492.04 | 1993.63 | 1993.63 | 1993.63 | 1993.63 | 1993.63 | 996.82 | 996.82 | 996.82 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392414.71
D14048 | General Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | -15932.95 | 3314.25 | 3314.25 | 3314.25 | 3314.25 | 2946 | 2946 | 1473 | 1473 | 1104.75 | 1104.75 | 1104.75 | 1104.75 | 920.63 | 736.5 | 736.5 | 736.5 | 736.5 | 736.5 | 368.25 | 368.25 | 368.25 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36825.04
D14052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 204906.3 | 13794.56 | 13794.56 | 13794.56 | 13794.56 | 13794.56 | 17243.21 | 17243.21 | 38689.02 | 22600 | 22600 | 22600 | 37100 | 37100 | 37100 | 37100 | 37100 | 31900 | 31900 | 31900 | 31900 | 31900 | 26700 | 21500 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822554.54
D14052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | 2760.06 | 369.78 | 369.78 | 369.78 | 369.78 | 369.78 | 462.23 | 462.23 | -2648.88 | 124.48 | 124.48 | 124.48 | 204.25 | 204.25 | 204.25 | 204.25 | 204.25 | 175.54 | 175.54 | 175.54 | 175.54 | 175.54 | 146.84 | 118.13 | 98.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520.16
D14052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225240.44 | 6911.92 | 6911.92 | 6911.92 | 6911.92 | 6911.92 | 8639.89 | 8639.89 | -2153.62 | 3065.23 | 3065.23 | 3065.23 | 5029.43 | 5029.43 | 5029.43 | 5029.43 | 5029.43 | 4322.59 | 4322.59 | 4322.59 | 4322.59 | 4322.59 | 3615.75 | 2908.91 | 2419.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339826.21
D14062 | Concrete, Soil and Water testing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 12877.57 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40392.53
D14062 | Concrete, Soil and Water testing | MAT | Materials | BUDGET | Approved Early Budget | 480.94 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | -1853.13 | 72.15 | 72.15 | 72.15 | 72.15 | 72.15 | 48.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961.94
D14062 | Concrete, Soil and Water testing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 33343.48 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | -8869.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42788.81
D14062 | Concrete, Soil and Water testing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3320.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055.26 | 701.18 | 701.18 | 701.18 | 701.18 | 701.18 | 467.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9349.07
D14062 | Concrete, Soil and Water testing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 3022.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30221.2
D14064 | PPE and the like | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567.06
D14064 | PPE and the like | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24491.86 | 7514.1 | 7514.1 | 7514.1 | 7514.1 | 6679.2 | 6679.2 | 3339.6 | 3339.6 | 2504.7 | 2504.7 | 2504.7 | 2504.7 | 2087.25 | 1669.8 | 1669.8 | 1669.8 | 1669.8 | 1669.8 | 834.9 | 834.9 | 834.9 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100467.76
D14064 | PPE and the like | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 162126.67 | 3834 | 3834 | 3834 | 3834 | 3834 | 3834 | 3834 | 27104.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216069.48
D14066 | Signage | MAT | Materials | BUDGET | Approved Early Budget | 4946.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | -1531.51 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 427.33 | 213.66 | 213.66 | 213.66 | 213.66 | 106.83 | 106.83 | 106.83 | 53.42 | 53.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15679.66
D14066 | Signage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 345.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.12
D14068 | Fuel and Tanks | MAT | Materials | BUDGET | Approved Early Budget | 123447.07 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | -30109.23 | 7985.25 | 7985.25 | 7985.25 | 7985.25 | 7098 | 7098 | 3549 | 3549 | 2661.75 | 2661.75 | 2661.75 | 2661.75 | 2218.13 | 1774.5 | 1774.5 | 1774.5 | 1774.5 | 1774.5 | 887.25 | 887.25 | 887.25 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219385.13
D14068 | Fuel and Tanks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17399.47 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 3836.33 | 1136.55 | 1136.55 | 1136.55 | 1136.55 | 1010.26 | 1010.26 | 505.13 | 505.13 | 378.85 | 378.85 | 378.85 | 378.85 | 315.71 | 252.57 | 252.57 | 252.57 | 252.57 | 252.57 | 126.28 | 126.28 | 126.28 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37884.88
D14072 | Haul road maintenance works, road sweeping and jet washing | LAB | Labour | BUDGET | Approved Early Budget | 8030.4 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | -8666.82 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44427.97
D14072 | Haul road maintenance works, road sweeping and jet washing | MAT | Materials | BUDGET | Approved Early Budget | 12380.71 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | -5763.85 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 366.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19484.63
D14072 | Haul road maintenance works, road sweeping and jet washing | MISC | Miscellaneous | BUDGET | Approved Early Budget | -470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -470
D14072 | Haul road maintenance works, road sweeping and jet washing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 185586.05 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 24234.4 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 5940.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345022.61
D14072 | Haul road maintenance works, road sweeping and jet washing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462
D14074 | Temporary works for Logistics and further site surveys (no utilities) | LAB | Labour | BUDGET | Approved Early Budget | 36273.46 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 18293.46 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 9000 | 9000 | 4800 | 4800 | 4800 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220739.95
D14074 | Temporary works for Logistics and further site surveys (no utilities) | MAT | Materials | BUDGET | Approved Early Budget | 46778.06 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | -15366.16 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 3800.61 | 3800.61 | 2026.56 | 2026.56 | 2026.56 | 2026.56 | 2421.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119238.79
D14074 | Temporary works for Logistics and further site surveys (no utilities) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944
D14074 | Temporary works for Logistics and further site surveys (no utilities) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 15277.84 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 6598.71 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 879.92 | 879.92 | 469.19 | 469.19 | 469.19 | 469.19 | 560.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45117.87
D14076 | Site supervision | LAB | Labour | BUDGET | Approved Early Budget | 480913.63 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 76513.18 | 66400 | 52800 | 52800 | 40400 | 40400 | 34000 | 34000 | 34000 | 34000 | 27200 | 27200 | 20800 | 20800 | 20800 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1516816.09
D14076 | Site supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 540.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540.5
D14078 | Assets Temporary Protection | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47040
D14078 | Assets Temporary Protection | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13440
D14078 | Assets Temporary Protection | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6720
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 9940 | 9940 | 6580 | 6580 | 6580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142660
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 2836.9 | 2836.9 | 1883.11 | 1883.11 | 1874.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40760.02
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1418.45 | 1418.45 | 941.56 | 941.56 | 937.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20379.98
D14666 | Small Plant | MAT | Materials | BUDGET | Approved Early Budget | 10.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.54
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | MAT | Materials | BUDGET | Approved Early Budget | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 246438.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246438.02
D24104 | Phase 2: Banham House | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650
D24104 | Phase 2: Banham House | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 121636.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121636.81
D24122 | General | LAB | Labour | BUDGET | Approved Early Budget | 11812.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11812.36
D24122 | General | MAT | Materials | BUDGET | Approved Early Budget | 1132.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132.17
D24122 | General | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 191.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.12
D24124 | Water Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
D24128 | Other Utilities | LAB | Labour | BUDGET | Approved Early Budget | 17327.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17327.26
D24128 | Other Utilities | MAT | Materials | BUDGET | Approved Early Budget | 9858.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9858.14
D24128 | Other Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 62681.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62681.98
D24128 | Other Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 279.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.2
D24128 | Other Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | MISC | Miscellaneous | BUDGET | Approved Early Budget | 317425.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3325 | 0 | 0 | 0 | 0 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 4754.63 | 4754.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415842.64
D24130 | Utilities Permanent Connections | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24132 | Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 25433.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25433.32
D24132 | Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1824
D34212 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 37067.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37067.12
D34212 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 71244.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71299.1
D34212 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 537154.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537154.11
D34214 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 441985.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -469.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441516.63
D34214 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 15303.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6423.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8880.13
D34214 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 377258.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171409.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548668.09
D34214 | Excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 29102.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29102.5
D34216 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 12807.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12807.74
D34216 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 3045857.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3048017.64
D34216 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4195.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4195.5
D34216 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5503.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5503.42
D34216 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 953127.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953127.76
D34222 | Piling | LAB | Labour | BUDGET | Approved Early Budget | 423227.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423227.5
D34222 | Piling | MAT | Materials | BUDGET | Approved Early Budget | 1535457.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535457.83
D34222 | Piling | MISC | Miscellaneous | BUDGET | Approved Early Budget | 35174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35174.5
D34222 | Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 338148.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6663.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344811.82
D34222 | Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17661220.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17661220.53
D34224 | Ground Floor Level | LAB | Labour | BUDGET | Approved Early Budget | 64081.97 | 0 | 33922.39 | 67844.77 | 56537.31 | 33922.39 | 33922.39 | 0 | -16352.54 | 10308.75 | 5154.38 | 5154.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294496.19
D34224 | Ground Floor Level | MAT | Materials | BUDGET | Approved Early Budget | 130027.37 | 0 | 68947.03 | 137894.05 | 114911.71 | 68947.03 | 68947.03 | 0 | 3545.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593219.27
D34224 | Ground Floor Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10855.24 | 0 | 10865.58 | 21731.16 | 18109.3 | 10865.58 | 10865.58 | 0 | 11530.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94822.72
D34226 | B1 Slab Level | LAB | Labour | BUDGET | Approved Early Budget | 224715.2 | 30043.65 | 40058.2 | 25036.38 | 5007.28 | 0 | 0 | 0 | -8827.8 | 12520.82 | 6260.41 | 6260.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341074.55
D34226 | B1 Slab Level | MAT | Materials | BUDGET | Approved Early Budget | 370950.64 | 28879.15 | 38505.53 | 24065.95 | 4813.19 | 0 | 0 | 0 | 41769.66 | 3982.2 | 1991.1 | 1991.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516948.52
D34226 | B1 Slab Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 50447.93 | 7048.17 | 9397.56 | 5873.48 | 1174.7 | 0 | 0 | 0 | 70251.12 | 3394.87 | 1697.44 | 1697.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150982.71
D34228 | B2 Slab Level | LAB | Labour | BUDGET | Approved Early Budget | 199788.68 | 30485.6 | 0 | 0 | 0 | 0 | 0 | 0 | 9899.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240173.74
D34228 | B2 Slab Level | MAT | Materials | BUDGET | Approved Early Budget | 327992.29 | 28685.23 | 0 | 0 | 0 | 0 | 0 | 0 | -25923.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330754.45
D34228 | B2 Slab Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23737.42 | 13653.26 | 0 | 0 | 0 | 0 | 0 | 0 | -3905.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33484.84
D34228 | B2 Slab Level | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2870
D34230 | Base Slabs | LAB | Labour | BUDGET | Approved Early Budget | 872782.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38462.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834320.03
D34230 | Base Slabs | MAT | Materials | BUDGET | Approved Early Budget | 2477882.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25985.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451896.88
D34230 | Base Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 102473.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115481.72
D34230 | Base Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900
D34232 | Roof Slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 90350.84 | 108421 | 95870.63 | 158446.94 | 79223.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532312.88
D34232 | Roof Slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 178274.57 | 213929.48 | 150572.54 | 190499.72 | 95249.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828526.17
D34232 | Roof Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 33103.49 | 39724.19 | 886.73 | 57737.61 | 28868.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160320.83
D34234 | Columns - all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 359124.46 | 34987.66 | 40818.94 | 29156.38 | 11662.55 | 0 | 0 | 0 | -20656.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455093.26
D34234 | Columns - all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 483596.01 | 24194.83 | 28227.31 | 20162.36 | 8064.94 | 0 | 0 | 0 | -12742.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551503.33
D34234 | Columns - all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 30118.26 | 16423.63 | 19160.91 | 13686.36 | 5474.54 | 0 | 0 | 0 | -29850.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55013.43
D34234 | Columns - all levels below ground | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | LAB | Labour | BUDGET | Approved Early Budget | 29856.96 | 30520.26 | 30520.26 | 35606.97 | 5086.71 | 0 | 0 | 0 | 61994.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193585.51
D34236 | Platform Level | MAT | Materials | BUDGET | Approved Early Budget | 146732 | 113348.48 | 113348.48 | 132239.9 | 18891.41 | 0 | 0 | 0 | -134777.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389782.43
D34236 | Platform Level | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 8437.5 | 8437.5 | 9843.75 | 1406.25 | 0 | 0 | 0 | -28125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9920.13 | 6260.42 | 6260.42 | 7303.82 | 1043.4 | 0 | 0 | 0 | 34692.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65480.77
D34238 | In situ walls - all levels below | LAB | Labour | BUDGET | Approved Early Budget | 73729.78 | 41109.29 | 41109.29 | 8221.86 | 32887.43 | 16443.72 | 24665.57 | 0 | 131674.16 | 36656.15 | 18328.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424825.32
D34238 | In situ walls - all levels below | MAT | Materials | BUDGET | Approved Early Budget | 101493.29 | 38127.96 | 38127.96 | 7625.59 | 30502.37 | 15251.19 | 22876.78 | 0 | 58610.24 | 10157.1 | 5078.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327851.03
D34238 | In situ walls - all levels below | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6520.44 | 27920.64 | 27920.64 | 5584.13 | 22336.51 | 11168.26 | 16752.38 | 0 | -88889 | 9982.01 | 4991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44287.01
D34240 | Capping beam | LAB | Labour | BUDGET | Approved Early Budget | 590891.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593612.15
D34240 | Capping beam | MAT | Materials | BUDGET | Approved Early Budget | 786517.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786517.54
D34240 | Capping beam | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7801.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7801.64
D34240 | Capping beam | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 272566.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4638.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277205.18
D34240 | Capping beam | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100
D34242 | Waling beam B1 | LAB | Labour | BUDGET | Approved Early Budget | 205481.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205809.86
D34242 | Waling beam B1 | MAT | Materials | BUDGET | Approved Early Budget | 286102.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288556.98
D34242 | Waling beam B1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 422.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.88
D34242 | Waling beam B1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 38070.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1617.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36453.29
D34242 | Waling beam B1 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1665.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665.63
D34244 | Waling beam B2 | LAB | Labour | BUDGET | Approved Early Budget | 213037.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213037.53
D34244 | Waling beam B2 | MAT | Materials | BUDGET | Approved Early Budget | 379818.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381365.96
D34244 | Waling beam B2 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 385.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667.22
D34246 | PCC beams including in-situ stitches – all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 486646.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486646.55
D34246 | PCC beams including in-situ stitches – all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 1773936.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1775741.65
D34246 | PCC beams including in-situ stitches – all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 80747.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8773.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89521.48
D34246 | PCC beams including in-situ stitches – all levels below ground | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3024.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3024.63
D34248 | PCC walls – all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 36649.81 | 12224.52 | 12224.52 | 12224.52 | 2037.42 | 2037.42 | 0 | 0 | 92583.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169982.17
D34248 | PCC walls – all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 101706.15 | 105535.38 | 105535.38 | 105535.38 | 17589.23 | 17589.23 | 0 | 0 | -137951.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315538.91
D34248 | PCC walls – all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6859.33 | 4589.21 | 4589.21 | 4589.21 | 764.87 | 764.87 | 0 | 0 | 4000.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26156.81
D34252 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 6332.99 | 6332.99 | 6332.99 | 6332.99 | 0 | 4221.99 | 6332.99 | 32083.2 | 16691.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84661.56
D34252 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 9543.87 | 51839.14 | 51839.14 | 51839.14 | 51839.14 | 0 | 34559.43 | 51839.14 | -24435.06 | 3840.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282704.51
D34252 | Staircases | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 10333.85 | 10333.85 | 10333.85 | 10333.85 | 0 | 6889.23 | 10333.85 | -54868.17 | 3690.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7380.62
D34252 | Staircases | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 483.92 | 483.92 | 483.92 | 483.92 | 0 | 322.62 | 483.92 | 16121.01 | 259.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19122.45
D34252 | Staircases | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11441.98 | 11441.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22883.96
D34254 | Above ground structure (Mezzanine Level) | LAB | Labour | BUDGET | Approved Early Budget | 875.85 | 0 | 38565.13 | 38565.13 | 38565.13 | 12855.04 | 38565.13 | 38565.13 | -40501.26 | 66638.08 | 14808.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247501.82
D34254 | Above ground structure (Mezzanine Level) | MAT | Materials | BUDGET | Approved Early Budget | 504.48 | 0 | 54588.32 | 54588.32 | 54588.32 | 18196.11 | 54588.32 | 54588.32 | 60342.59 | 106240.82 | 23609.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481834.67
D34254 | Above ground structure (Mezzanine Level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 13199.67 | 13199.67 | 13199.67 | 4399.89 | 13199.67 | 13199.67 | 15456.69 | 66780.03 | 14840.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167474.97
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 3250 | 3250 | 3250 | 3250 | 3250 | 3250 | 3250 | -22750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | MAT | Materials | BUDGET | Approved Early Budget | 7620.37 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | -10335.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7793.47
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | -40375.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | -9792.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34260 | Construction of Sainsburys ramp | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 16104.61 | 26841.01 | -5938.43 | 28622.3 | 32711.2 | 4088.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102429.59
D34260 | Construction of Sainsburys ramp | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 21029.5 | 35049.17 | -1072.26 | 25576.43 | 29230.2 | 3653.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113466.82
D34260 | Construction of Sainsburys ramp | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4855.72 | 8092.87 | -3463.41 | 14748.27 | 16855.17 | 2106.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43195.52
D34260 | Construction of Sainsburys ramp | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17092.47 | 29911.82 | 34184.93 | 4273.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85462.34
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | LAB | Labour | BUDGET | Approved Early Budget | 1132675.59 | 85262.71 | 59683.89 | 25578.81 | 0 | 0 | 0 | 0 | -72222.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230978.41
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | MAT | Materials | BUDGET | Approved Early Budget | 1043624.34 | 120210.39 | 84147.28 | 36063.12 | 0 | 0 | 0 | 0 | 34337.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318382.6
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5106.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5106.5
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 187720.44 | 11053.88 | 7737.71 | 3316.16 | 0 | 0 | 0 | 0 | 8177.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218005.33
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 12017.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12017.19
D34266 | In situ walls - all levels above ground | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 22615.02 | 33922.53 | 33922.53 | 22615.02 | 45230.04 | 22615.02 | 47271.53 | 30011.17 | 7502.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265705.65
D34266 | In situ walls - all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 8866.38 | 0 | 28757.35 | 43136.02 | 43136.02 | 28757.35 | 57514.69 | 28757.35 | 186603.55 | 25747.46 | 6436.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457713.04
D34266 | In situ walls - all levels above ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 1188.57 | 1782.85 | 1782.85 | 1188.57 | 2377.14 | 1188.57 | 62177.06 | 16182.11 | 4045.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91913.25
D34268 | In situ columns – all levels above ground | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 37407.04 | 56110.56 | 56110.56 | 37407.04 | 56110.56 | 56110.56 | 69424.48 | 18689.83 | 4672.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392043.09
D34268 | In situ columns – all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 18432.18 | 0 | 42329.08 | 63493.63 | 63493.63 | 42329.08 | 63493.63 | 63493.63 | 259272.06 | 8709.76 | 2177.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627224.12
D34268 | In situ columns – all levels above ground | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 4296 | 6444 | 6444 | 4296 | 6444 | 6444 | -31086.33 | 875.11 | 218.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375.56
D34268 | In situ columns – all levels above ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -10986.8 | 0 | 5941.21 | 8911.82 | 8911.82 | 5941.21 | 8911.82 | 8911.82 | -4182.58 | 1781.4 | 445.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34587.07
D34270 | PCC walls – all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34274 | Temporary Steel Propping | LAB | Labour | BUDGET | Approved Early Budget | 35379.39 | 0 | 0 | 0 | 15626.09 | 15626.09 | 0 | 0 | -30464.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36167.2
D34274 | Temporary Steel Propping | MAT | Materials | BUDGET | Approved Early Budget | 182252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182252.5
D34274 | Temporary Steel Propping | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 25768.25 | 0 | 0 | 0 | 2403.94 | 2403.94 | 0 | 0 | -2970.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27605.41
D34274 | Temporary Steel Propping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5584.8 | 5584.8 | 0 | 0 | -5411.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5758.48
D34276 | OSD Corridor Construction incl. sheet piling | LAB | Labour | BUDGET | Approved Early Budget | 62235.59 | 0 | 0 | 0 | 0 | 0 | 0 | 8401.61 | -8401.61 | 0 | 8695.48 | 12422.12 | 3726.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87079.82
D34276 | OSD Corridor Construction incl. sheet piling | MAT | Materials | BUDGET | Approved Early Budget | 305057.64 | 0 | 0 | 0 | 0 | 0 | 0 | 8689.92 | -3859.92 | 0 | 8719.26 | 12456.09 | 3736.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334799.82
D34276 | OSD Corridor Construction incl. sheet piling | MISC | Miscellaneous | BUDGET | Approved Early Budget | 425.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.94
D34276 | OSD Corridor Construction incl. sheet piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21364.34 | 0 | 0 | 0 | 0 | 0 | 0 | 3965.48 | -2555.62 | 0 | 5551.67 | 7930.96 | 2379.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38636.12
D34276 | OSD Corridor Construction incl. sheet piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446.63 | 4923.76 | 1477.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9847.52
D34278 | Track Slab (Mass Fill) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 16864.02 | 25296.03 | 14053.35 | 0 | 0 | 0 | 59188.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115402.07
D34278 | Track Slab (Mass Fill) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 105280.21 | 157920.31 | 87733.51 | 0 | 0 | 0 | -12648.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338285.08
D34278 | Track Slab (Mass Fill) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 18888 | 28332 | 15740 | 0 | 0 | 0 | -62960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 1334.66 | 2001.99 | 1112.22 | 0 | 0 | 0 | -4448.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 6000 | 9000 | 5000 | 0 | 0 | 0 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | LAB | Labour | BUDGET | Approved Early Budget | 316229.17 | 33470.56 | 50205.83 | 0 | 0 | 0 | 0 | 0 | -46314.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353591.08
D34280 | Head Walls Construction | MAT | Materials | BUDGET | Approved Early Budget | 166233.78 | 39513.31 | 59269.96 | 0 | 0 | 0 | 0 | 0 | -24740.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240276.26
D34280 | Head Walls Construction | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 3000 | 4500 | 0 | 0 | 0 | 0 | 0 | -7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 36999.34 | 8769.35 | 13154.03 | 0 | 0 | 0 | 0 | 0 | -24135.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34787.16
D34280 | Head Walls Construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9866.98 | 2090.24 | 3135.36 | 0 | 0 | 0 | 0 | 0 | -1193.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13898.98
D34282 | UMC slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 18084.9 | 18084.9 | 4018.87 | 0 | 0 | 0 | -8504.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684.56
D34282 | UMC slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 10687.53 | 10687.53 | 2375.01 | 0 | 0 | 0 | -12593.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11156.11
D34282 | UMC slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 8183.77 | 8183.77 | 1818.61 | 0 | 0 | 0 | -13653.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4532.8
D34284 | Allowance for piling works defects rectification | LAB | Labour | BUDGET | Approved Early Budget | 60489.51 | 14421.98 | 14421.98 | 14421.98 | 4807.33 | 0 | 0 | 0 | 8051.04 | 3176.44 | 3176.44 | 3176.44 | 3176.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129319.58
D34284 | Allowance for piling works defects rectification | MAT | Materials | BUDGET | Approved Early Budget | 14230.93 | 4365.4 | 4365.4 | 4365.4 | 1455.13 | 0 | 0 | 0 | 4165.98 | 460.56 | 460.56 | 460.56 | 460.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34790.48
D34284 | Allowance for piling works defects rectification | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8684.66 | 3323.8 | 3323.8 | 3323.8 | 1107.93 | 0 | 0 | 0 | -3341.63 | 182.13 | 182.13 | 182.13 | 182.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17150.88
D34284 | Allowance for piling works defects rectification | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091.67 | 4091.67 | 4091.67 | 4091.67 | 4091.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20458.35
D34286 | Allowance for remediation works to exposed concrete elements | LAB | Labour | BUDGET | Approved Early Budget | 56751.27 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 19694.52 | 109358.1 | 2566.8 | 2566.8 | 2566.8 | 2566.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255154.65
D34286 | Allowance for remediation works to exposed concrete elements | MAT | Materials | BUDGET | Approved Early Budget | 4431.93 | 398.55 | 398.55 | 398.55 | 398.55 | 398.55 | 398.55 | 797.1 | 28666.82 | 4940.4 | 4940.4 | 4940.4 | 4940.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56048.75
D34286 | Allowance for remediation works to exposed concrete elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10485.72 | 666.07 | 666.07 | 666.07 | 666.07 | 666.07 | 666.07 | 1332.13 | 5552.45 | 636.76 | 636.76 | 636.76 | 636.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23913.76
D34288 | Nine Elms Main Raised Access | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 2047.6 | 1365.06 | 3412.66 | 0 | 3424.21 | 4692.77 | 4692.77 | 4692.77 | 4692.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29020.61
D34288 | Nine Elms Main Raised Access | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5288.63 | 3525.75 | 8814.38 | 0 | -4538.25 | 13090.51 | 13090.51 | 13090.51 | 13090.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65452.55
D34288 | Nine Elms Main Raised Access | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 3387.94 | 2258.63 | 5646.57 | 0 | -5634.31 | 5658.83 | 5658.83 | 5658.83 | 5658.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28294.15
D34292 | Plant room plinths | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5293.14 | 5293.14 | 5293.14 | 5293.14 | 5293.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26465.7
D34292 | Plant room plinths | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6732.34 | 6732.34 | 6732.34 | 6732.34 | 6732.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33661.7
D34292 | Plant room plinths | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064.63 | 1064.63 | 1064.63 | 1064.63 | 1064.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5323.15
D34294 | Knock out panels | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5075.75 | 5075.75 | 5075.75 | 5075.75 | 5075.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25378.75
D34294 | Knock out panels | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4645.05 | 4645.05 | 4645.05 | 4645.05 | 4645.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23225.25
D34294 | Knock out panels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3134.1 | 3134.1 | 3134.1 | 3134.1 | 3134.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15670.5
D34294 | Knock out panels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4073.14 | 4073.14 | 4073.14 | 4073.14 | 4073.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20365.7
D44302 | Finishes to floors walls ceilings and entrances including matwells and the like | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44312 | External Cladding & Roofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44332 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 192197 | 119314.27 | 0 | 0 | 0 | 0 | 0 | 0 | 205637.13 | 0 | 0 | 0 | 0 | 129542.8 | 261356.24 | 174541.88 | 398855.12 | 361355.94 | 161814.87 | 163633.02 | 352720.06 | 68181.45 | 22500 | 22500 | 22500 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2671649.78
D44334 | Fire Suppression | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2731.69 | 0 | 0 | 767.96 | 1315.26 | 1262.29 | 1234.75 | 8983.16 | 208118.19 | 61620.24 | 63956.43 | 39950.11 | 17789.92 | 2013.95 | 1342.64 | 25872.58 | 34096.22 | 1121.1 | 0 | 12755.03 | 9398.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494329.97
D44336 | Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 8391.18 | 0 | 0 | 2359.01 | 4040.2 | 3877.5 | 3792.9 | 4934.96 | 29618.5 | 0 | 19379.1 | 75363.16 | 78951.88 | 54548.57 | 68544.59 | 108020.53 | 107302.79 | 45935.64 | 12560.53 | 41629.18 | 43782.41 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723032.63
D44338 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 30259.46 | 15129.73 | 18436.27 | 34752.23 | 34752.23 | 34752.23 | 34752.23 | 48443.92 | 215942 | 27665.35 | 65013.58 | 222706.08 | 381781.86 | 273886.98 | 280001.03 | 572797.28 | 426751.89 | 118961.01 | 12449.41 | 55330.7 | 40114.76 | 0 | 0 | 0 | 0 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2964603.73
D44340 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 5675.84 | 158923.43 | -153841.06 | 35132.43 | 76103.9 | 88664.74 | 209500.01 | 238256.94 | 173635.12 | 165507.52 | 48765.61 | 2586.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048910.53
D44340 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 14504.06 | 97329.63 | -111833.69 | 71868.54 | 128804.77 | 196248.11 | 375381.22 | 479526.1 | 323333.73 | 298095.78 | 127526.36 | 88205 | 39520.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2128509.77
D44342 | Escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 74131.48 | 0 | 0 | 0 | 0 | 0 | 741053.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175976.66 | 319957.56 | 159978.78 | 319957.56 | 319957.56 | 319957.56 | 287961.8 | 207972.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926904.57
D44344 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 46925.05 | 0 | 0 | 47631.29 | 62539.36 | 62539.36 | 68503.06 | -89311.72 | 0 | 0 | 0 | 183277.7 | 78547.59 | 44510.3 | 52365.06 | 52365.06 | 52365.06 | 26182.53 | 34037.29 | 261825.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984302.28
D44347 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 7121.87 | 15791.9 | 15791.9 | 39479.75 | 78959.5 | 78959.5 | 77111.1 | 241016.97 | 436542.58 | 330034.96 | 714595.29 | 710376.67 | 416702.65 | 428376.17 | 360947.05 | 202438.83 | 65184.38 | 67479.61 | 17443.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4304354.39
D44348 | M&E Plant | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44348 | M&E Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44348 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 888.97 | 888.97 | 888.97 | 1185.29 | 4444.84 | 4444.84 | 39780.71 | 10536.67 | 19084.57 | 14428.32 | 31240.34 | 31055.92 | 18217.21 | 18727.55 | 15779.72 | 8850.13 | 2849.7 | 2950.04 | 762.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227005.36
D44349 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 19378.62 | 12079.01 | 2796.51 | 6023.26 | 11232.95 | 26102.05 | 33723.24 | 155744.85 | 83840.93 | 122102.15 | 221157.81 | 167199.75 | 362022.72 | 359885.52 | 211106.67 | 406656.82 | 342646.47 | 192174.86 | 61879.43 | 64058.29 | 16559.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2878371.19
D44349 | M&E Material | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44349 | M&E Material | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44350 | M&E Subcontractor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44350 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 44251.03 | 0 | 0 | 0 | 0 | 6776.26 | 17233.68 | 25652.29 | 127953.23 | 49971.65 | 69697.29 | 78132.77 | 65213.29 | 106026.27 | 98238.51 | 125122.12 | 113690.9 | 117185.45 | 38404.16 | 52577.01 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186125.89
D44611 | Back of House BoH floor screeds | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41244.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41244.6
D44611 | Back of House BoH floor screeds | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29141.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29141.98
D44611 | Back of House BoH floor screeds | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006.7
D44611 | Back of House BoH floor screeds | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 29530.58 | 29530.58 | 68904.68 | 147652.88 | -192220.8 | 125096.88 | 125096.88 | 125096.88 | 125096.88 | 125096.88 | 0 | 0 | 41698.96 | 41698.96 | 41698.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833979.2
D44612 | Floor Epoxi coating | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 22063.36 | 44126.72 | 66190.08 | -132380.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26061.85 | 26061.85 | 15637.11 | 15637.11 | 0 | 10424.74 | 10424.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104247.4
D44613 | Soft flooring: vinyl and ceramic tiles | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 5999.38 | 11998.76 | -17998.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36486.59 | 20849.48 | 31274.22 | 15637.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104247.4
D44614 | Front of House FoH screeds for stone flooring | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19774.2 | 49435.51 | 29661.31 | 49435.51 | 39548.41 | 9887.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197742.04
D44615 | Front of House FoH Stone flooring and bedding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311.73 | 311.73 | 311.73 | 311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.92
D44615 | Front of House FoH Stone flooring and bedding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.39 | 249.39 | 249.39 | 249.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997.56
D44615 | Front of House FoH Stone flooring and bedding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.35 | 62.35 | 62.35 | 62.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.4
D44615 | Front of House FoH Stone flooring and bedding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159287.99 | 159287.99 | 159287.99 | 159287.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637151.96
D44616 | Waterproofing of internal areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533.72 | 1533.72 | 1533.72 | 1533.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6134.88
D44621 | Stainless steel cladding incl. grille 02, glazed frieze, stainless steel access panels to walls and | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 15646.15 | 15646.15 | 15646.15 | 46938.45 | 62584.6 | 48084.41 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 115663.39 | 115663.39 | 115663.39 | 57831.69 | 101205.46 | 72289.62 | 72289.62 | 72289.62 | 43373.77 | 14457.92 | 14457.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520216.94
D44622 | Glazed downstand panel 01 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 935.39 | 935.39 | 935.39 | 2806.16 | 3741.54 | -935.4 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 7483.08 | 7483.08 | 7483.08 | 3741.54 | 6547.7 | 4676.93 | 4676.93 | 4676.93 | 2806.16 | 935.39 | 935.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93538.54
D44623 | GFRC cladding to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 20001.62 | 20001.62 | 20001.62 | 20001.62 | 30002.43 | 118926.61 | 74562.72 | 111844.08 | 111844.08 | 111844.08 | 111844.08 | 111844.08 | 37281.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
D44624 | Platform edge OTE screen - support steel, cladding and louvres - North and South elevation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 8795.94 | 8795.94 | 8795.94 | 26387.82 | 35183.76 | 57967.75 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 64498.18 | 64498.18 | 64498.18 | 32249.09 | 56435.91 | 40311.36 | 40311.36 | 40311.36 | 24186.82 | 8062.27 | 8062.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879593.91
D44625 | FoH cladding trackside acoustic cladding 04 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 5014.66 | 5014.66 | 5014.66 | 15043.98 | 20058.64 | 51399.15 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 35157.82 | 35157.82 | 35157.82 | 17578.91 | 30763.09 | 21973.64 | 21973.64 | 21973.64 | 13184.18 | 4394.73 | 4394.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501465.99
D44626 | Glazed ballustrade and gates | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 27.53 | 27.53 | 27.53 | 82.59 | 110.12 | -27.53 | 165.18 | 165.18 | 165.18 | 165.18 | 165.18 | 165.18 | 220.24 | 220.24 | 220.24 | 110.12 | 192.71 | 137.65 | 137.65 | 137.65 | 82.59 | 27.53 | 27.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2753
D44627 | Escalator advertisement panels 01 incl. metal trim and grillages | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 410.48 | 410.48 | 410.48 | 1231.44 | 1641.92 | 16666.85 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1782.54 | 1782.54 | 1782.54 | 891.27 | 1559.72 | 1114.09 | 1114.09 | 1114.09 | 668.45 | 222.82 | 222.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41048.02
D44631 | Double coat of Paint to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 2040 | 2040 | 2040 | 2040 | 2040 | 1020 | 1020 | 1020 | 1020 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
D44631 | Double coat of Paint to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 713.71 | 713.71 | 713.71 | 713.71 | 713.71 | 356.85 | 356.85 | 356.85 | 356.85 | 356.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17842.7
D44631 | Double coat of Paint to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 475.81 | 475.81 | 475.81 | 475.81 | 475.81 | 237.9 | 237.9 | 237.9 | 237.9 | 237.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11895.15
D44631 | Double coat of Paint to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6935.85 | 16183.65 | -19386.33 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 2133.24 | 2133.24 | 2133.24 | 2133.24 | 2133.24 | 1066.62 | 1066.62 | 1066.62 | 1066.62 | 1066.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53331
D44632 | Concrete sealant to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 133.82 | 312.25 | 1338.93 | 1785 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500
D44632 | Concrete sealant to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 26.76 | 62.45 | 535.29 | 624.5 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 535.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8921.4
D44632 | Concrete sealant to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 17.84 | 41.63 | 356.86 | 416.33 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 356.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947.59
D44632 | Concrete sealant to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4869.69 | 4869.69 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 4174.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69567
D44633 | Acoustic Render and plaster to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 755.7 | 1763.3 | -2519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 480.9 | 1122.1 | -1603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 137.4 | 320.6 | -458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6635.18 | 15482.08 | -13924.43 | 8192.84 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 7022.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117040.5
D44634 | Windows 01 and 02 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 315.46 | 315.46 | 315.46 | 1892.75 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 2523.68 | 2523.68 | 2523.68 | 1261.84 | 2208.22 | 1577.3 | 1577.3 | 1577.3 | 946.38 | 315.46 | 315.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31545.99
D44635 | Wall ceramic tiles | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 845.59 | 1973.03 | -2818.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5046.54 | 7065.16 | 8074.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20186.17
D44636 | Acoustic wall lining Wall type in Vent shafts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 11866.85 | 11866.85 | 8000 | 32600.55 | 43467.4 | 54334.25 | 43467.4 | 21733.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227337
D44641 | Concrete sealant and paint to soffits | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570 | 3570 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
D44641 | Concrete sealant and paint to soffits | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44641 | Concrete sealant and paint to soffits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94
D44641 | Concrete sealant and paint to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4969.26 | 4969.26 | -6613.8 | 3324.72 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 2849.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47496
D44642 | Back of House BoH soffit insulation and grid ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2501.8 | 2501.8 | 4441.9 | 14168.25 | 18891 | 18891 | 14168.25 | 9445.5 | 9445.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94455
D44643 | Front of House FoH metal tube ceiling, including acoustic insulation to soffit | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 11298.38 | 11298.38 | 22596.76 | 33895.14 | 154169.2 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 78820.23 | 78820.23 | 78820.23 | 39410.12 | 68967.7 | 49262.64 | 49262.64 | 49262.64 | 29557.59 | 9852.53 | 9852.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129837.96
D44644 | Render / airtight to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2440.75 | 2440.75 | -4881.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44645 | Monorail | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | -15000 | 0 | 11864.7 | 11864.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94917.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118647
D44651 | Metalwork: handrail to stairs, railings; metal ladder; ship ladder; platform end barrier | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6032.2 | 6032.2 | -12064.4 | 0 | 0 | 8960.75 | 22401.87 | 22401.87 | 22401.87 | 67205.61 | 67205.61 | 67205.61 | 22401.87 | 44803.74 | 44803.74 | 22401.87 | 22401.87 | 13441.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448037.4
D44652 | Metalwork to risers and shafts: metal floor safety grillage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 12300 | 12300 | -24600 | 0 | 0 | 6272.41 | 15681.02 | 15681.02 | 15681.02 | 47043.07 | 47043.07 | 47043.07 | 15681.02 | 31362.05 | 31362.05 | 15681.02 | 15681.02 | 9408.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313620.45
D44653 | Spring doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691.34 | 3691.34 | 3691.34 | 3691.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14765.36
D44654 | Lifting beam, jacking points and lifting eyes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 768.7 | 768.7 | -1024.93 | 1537.4 | 2049.87 | 1537.4 | 1537.4 | 1537.4 | 1537.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10249.34
D44654 | Lifting beam, jacking points and lifting eyes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2890.28 | 2890.28 | -4817.13 | 2890.28 | 3853.71 | 2890.28 | 2890.28 | 2890.28 | 2890.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19268.54
D44654 | Lifting beam, jacking points and lifting eyes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 307.48 | 307.48 | -262.47 | 1057.48 | 1409.97 | 1057.48 | 1057.48 | 1057.48 | 1057.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7049.86
D44654 | Lifting beam, jacking points and lifting eyes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6710 | 20130 | 26840 | 20130 | 20130 | 20130 | 20130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134200
D44655 | Durasteel floors including raised flooring | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 2550 | 5100 | 7650 | 10200 | 10200 | 7650 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000
D44661 | Internal fit out to Sainsbury's ramp | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 683.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6838.8
D44661 | Internal fit out to Sainsbury's ramp | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439.64 | 439.64 | 439.64 | 439.64 | 439.64 | 439.64 | 293.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930.93
D44661 | Internal fit out to Sainsbury's ramp | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.55 | 146.55 | 146.55 | 146.55 | 146.55 | 146.55 | 97.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977
D44661 | Internal fit out to Sainsbury's ramp | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 6838.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68388
D44671 | Station Office Room SOR control desk | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11558.92 | 11558.92 | 11558.92 | 11558.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46235.68
D44672 | Front of House Signage and Wayfinding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 16668.71 | 50006.13 | 66674.84 | 83343.56 | 50006.13 | 16668.71 | 6667.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330040.44
D44673 | Back of House Signage and Wayfinding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 4580.57 | 13741.71 | 18322.28 | 22902.85 | 13741.71 | 4580.57 | 1832.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90695.3
D44674 | FoH office furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 4420 | 6630 | 6630 | 6630 | 6630 | 6630 | 2210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44200
D44675 | BoH office furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6909.67 | 6909.67 | 10364.5 | 10364.5 | 3454.83 | 10364.5 | 10364.5 | 6909.67 | 3454.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69096.67
D44676 | Defibrilators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562.66 | 3562.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7125.32
D44681 | Durasteel - Wal ltypes M1, M2, M3, Fire rated ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12666.71 | 25333.42 | 38000.12 | 38000.12 | 38000.12 | 25333.42 | 38000.12 | 38000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253334.15
D44682 | Drywall lining - Wall types D4, E1, E2, E5, E6, F3, F4, G4 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23675.5 | -23675.5 | 0 | 0 | 0 | 0 | 0 | 0 | 29164.2 | 29164.2 | 29164.2 | 19442.8 | 29164.2 | 29164.2 | 29164.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194428
D44683 | Internal blockwork & brickwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089.59
D44683 | Internal blockwork & brickwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 201446.05 | 201446.05 | 115112.03 | 259002.06 | 316558.07 | 559943.98 | 284730.43 | 237275.36 | 221457 | 94910.14 | 94910.14 | 94910.14 | 63273.43 | 47455.07 | 47455.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2839885.02
D44684 | Internal blockwork & brickwork fireproofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 25051.29 | 10020.52 | 35071.81 | 50102.58 | 37561.4 | 82372.39 | 68643.66 | 64067.42 | 27457.46 | 27457.46 | 27457.46 | 18304.98 | 13728.73 | 13728.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501025.89
D44691 | Internal metal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 30022.53 | 60045.06 | -90067.59 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 188352.8 | 258985.1 | 353161.5 | 188352.8 | 282529.2 | 282529.2 | 164808.7 | 117720.5 | 47088.2 | 23544.1 | 23544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2354410
D44692 | Internal access panels | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 213.45 | 426.9 | -640.35 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 1067.25 | 1067.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21345
D44692 | Internal access panels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 516 | -774 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 1290 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25800
D44693 | Intenal floor access hatches. | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 312 | -468 | 0 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 780 | 1560 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600
D44694 | Wall access panels with firestopping, pressurised, etc | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | -300 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 500 | 1000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
D44695 | Temporary Doors Installation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 2520 | 5040 | 7560 | 7560 | 7560 | 5040 | 7560 | 2520 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400
D44695 | Temporary Doors Installation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 1440 | 2160 | 2160 | 2160 | 1440 | 2160 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400
D44695 | Temporary Doors Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 720 | 1080 | 1080 | 1080 | 720 | 1080 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200
D44701 | Firestopping to penetrations, voids, lifts and escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 14073.79 | 28147.59 | -12733.86 | 32981.28 | 43975.03 | 54968.79 | 54968.79 | 54968.79 | 76956.31 | 76956.31 | 76956.31 | 76956.31 | 54968.79 | 76956.31 | 54968.79 | 54968.79 | 54968.79 | 54968.79 | 32981.28 | 32981.28 | 32981.28 | 21987.52 | 10993.76 | 10993.76 | 10993.76 | 10993.76 | 10993.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106875.86
D44702 | Fireproof mastic to doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.44 | -495.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4954.4 | 4954.4 | 2477.2 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 2477.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49544
D44703 | Firecurtains to lift doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 8500 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
D44704 | Diamond drilling to services | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.4 | 1898.4 | 2847.6 | 3796.8 | 4746 | 4746 | 4746 | 6644.4 | 6644.4 | 6644.4 | 4746 | 6644.4 | 6644.4 | 4746 | 4746 | 4746 | 4746 | 2847.6 | 2847.6 | 2847.6 | 1898.4 | 949.2 | 949.2 | 949.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94920
D44704 | Diamond drilling to services | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271.2 | 271.2 | 406.8 | 542.4 | 678 | 678 | 678 | 949.2 | 949.2 | 949.2 | 678 | 949.2 | 949.2 | 678 | 678 | 678 | 678 | 406.8 | 406.8 | 406.8 | 271.2 | 135.6 | 135.6 | 135.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13560
D44704 | Diamond drilling to services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.4 | 542.4 | 813.6 | 1084.8 | 1356 | 1356 | 1356 | 1898.4 | 1898.4 | 1898.4 | 1356 | 1898.4 | 1898.4 | 1356 | 1356 | 1356 | 1356 | 813.6 | 813.6 | 813.6 | 542.4 | 271.2 | 271.2 | 271.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27120
D44704 | Diamond drilling to services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2154.56 | 253.62 | 2408.18 | 3612.27 | 4816.36 | 6020.45 | 6020.45 | 6020.45 | 8428.63 | 8428.63 | 8428.63 | 6020.45 | 8428.63 | 8428.63 | 6020.45 | 6020.45 | 6020.45 | 6020.45 | 3612.27 | 3612.27 | 3612.27 | 2408.18 | 1204.09 | 1204.09 | 1204.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120409
D44711 | Eastern entrance envelope and canopy | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 46925.49 | 46925.49 | 46925.49 | 93850.97 | 93850.97 | -48575.41 | 110645 | 110645 | 110645 | 110645 | 110645 | 221290 | 287677 | 265548 | 265548 | 110645 | 177032 | 110645 | 66387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337900
D44712 | External louvres and metal cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 65799.32 | 65799.32 | 65799.32 | 131598.63 | 63906.41 | 155645 | 155645 | 155645 | 155645 | 155645 | 311290 | 404677 | 373548 | 373548 | 155645 | 249032 | 155645 | 93387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3287900
D44713 | External Reconstituted stone cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 44945.73 | 44945.73 | 44945.73 | 74909.55 | 74909.55 | -74550.07 | 96952.62 | 124653.37 | 166204.49 | 207755.61 | 138503.74 | 138503.74 | 96952.62 | 96952.62 | 69251.87 | 27700.75 | 69251.87 | 41551.12 | 13850.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498191.01
D44714 | External Metal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 21292.95 | 21292.95 | -42585.9 | 0 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 30786.6 | 46179.9 | 30786.6 | 46179.9 | 46179.9 | 15393.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307866
D44715 | External Sunray louvered doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11557.25 | 16180.15 | 18491.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46229
D44716 | External access hatches | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44717 | Bituminous painting to columns and blockwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | -4130 | 10800 | 13500 | 13500 | 13500 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000
D44717 | Bituminous painting to columns and blockwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126 | -1126 | 9007.99 | 11259.99 | 11259.99 | 11259.99 | 2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45039.96
D44717 | Bituminous painting to columns and blockwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.67 | -750.67 | 6005.33 | 7506.66 | 7506.66 | 7506.66 | 1501.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30026.64
D44718 | External waterproofing to roof and Pascal square | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 8259.99 | 24779.97 | -33039.96 | 0 | 0 | 13500 | 13500 | 13500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
D44718 | External waterproofing to roof and Pascal square | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2252 | 6755.99 | -9007.99 | 0 | 0 | 13511.99 | 13511.99 | 13511.99 | 4504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45039.97
D44718 | External waterproofing to roof and Pascal square | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 375.33 | 1126 | -1501.33 | 0 | 0 | 4504 | 4504 | 4504 | 1501.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15013.33
D44718 | External waterproofing to roof and Pascal square | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 17475.4 | 52426.2 | -69901.6 | 0 | 0 | 74914.2 | 74914.2 | 74914.2 | 24971.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249714
D44721 | Cleaning to Front of House areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108250
D44722 | Cleaning to Back of House areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11533 | 11533 | 5766.5 | 11533 | 11533 | 11533 | 11533 | 11533 | 11533 | 11533 | 5766.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115330
D44723 | Cleaning to External Envelope | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 2756.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27567
D44724 | FLO Cleaning works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758 | 16758 | 16758 | 16758 | 16758 | 16758 | 11172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111720
D44724 | FLO Cleaning works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788 | 4788 | 4788 | 4788 | 4788 | 4788 | 3192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31920
D44724 | FLO Cleaning works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394 | 2394 | 2394 | 2394 | 2394 | 2394 | 1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15960
D44725 | Outstanding Works / Final Snagging | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29169 | 29169 | 29169 | 29169 | 29169 | 29169 | 19446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194460
D44725 | Outstanding Works / Final Snagging | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8334 | 8334 | 8334 | 8334 | 8334 | 8334 | 5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55560
D44725 | Outstanding Works / Final Snagging | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27780
D54402 | Groundwork's, foundations and BWIC | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25348.93 | 11488.93 | 11488.93 | 11488.93 | 11488.93 | 11488.93 | 7659.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90452.86
D54402 | Groundwork's, foundations and BWIC | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 2687.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26876.87
D54402 | Groundwork's, foundations and BWIC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 2511.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25116.87
D54402 | Groundwork's, foundations and BWIC | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 11075.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110751
D54404 | Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5131.72 | 7697.58 | 7697.58 | 7697.58 | 7697.58 | 7697.58 | 5131.72 | 2565.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51317.2
D54404 | Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17151.27 | 25726.9 | 25726.9 | 25726.9 | 25726.9 | 25726.9 | 17151.27 | 8575.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171512.67
D54404 | Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1682.83 | 2524.25 | 2524.25 | 2524.25 | 2524.25 | 2524.25 | 1682.83 | 841.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16828.33
D54404 | Drainage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25997.26 | 38995.88 | 38995.88 | 38995.88 | 38995.88 | 38995.88 | 25997.26 | 12998.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259972.55
D54406 | Temporary surfaces | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | MAT | Materials | BUDGET | Approved Early Budget | 801.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801.4
D54406 | Temporary surfaces | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14122.84 | 21184.26 | 28245.68 | 35307.1 | 21184.26 | 14122.84 | 7061.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141228.4
D54408 | Feature Paving | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34444.8 | 51667.2 | 68889.6 | 68889.6 | 60278.4 | 34444.8 | 17222.4 | 8611.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344448
D54410 | Street Furniture | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54410 | Street Furniture | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54410 | Street Furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9044.25 | 18088.5 | 36177 | 54265.5 | 72354 | 72354 | 54265.5 | 36177 | 9044.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361770
D54412 | Soft Landscaping | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54412 | Soft Landscaping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7633.74 | 15267.48 | 17812.06 | 20356.64 | 20356.64 | 10178.32 | 5089.16 | 5089.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101783.2
D54414 | General Signage, Totems and Way finding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507.65 | 6761.47 | 9015.29 | 13522.94 | 9015.29 | 2253.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45076.46
D54416 | Power and Comms | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54418 | Arch 42 works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5361.5 | 8042.25 | 8042.25 | 8042.25 | 8042.25 | 8042.25 | 5361.5 | 2680.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53615
D54418 | Arch 42 works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.38 | 2822.07 | 2822.07 | 2822.07 | 2822.07 | 2822.07 | 1881.38 | 940.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18813.8
D54418 | Arch 42 works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1758.18 | 2637.27 | 2637.27 | 2637.27 | 2637.27 | 2637.27 | 1758.18 | 879.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17581.8
D54418 | Arch 42 works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10253.88 | 15380.82 | 15380.82 | 15380.82 | 15380.82 | 15380.82 | 10253.88 | 5126.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102538.8
D54420 | Cleaning to External Works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64504 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7316.48 | 7316.48 | 7316.48 | 7316.48 | 7316.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36582.4
D64506 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179311.14
D64508 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64508 | Station Ventilation | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265791.48
D64508 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E08500 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 773699.04 | 32546.1 | 32546.1 | 16273.05 | 0 | 0 | 0 | 0 | -29687.76 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851154.87
E15000 | General Management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 50352.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50352.32
E15000 | General Management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | -50352.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50352.32
E15002 | Tunnels Prelims - Running Tunnels (TBM) | LAB | Labour | BUDGET | Approved Early Budget | 121449.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121449.66
E15002 | Tunnels Prelims - Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | -18227.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18227.63
E15002 | Tunnels Prelims - Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200
E15002 | Tunnels Prelims - Running Tunnels (TBM) | STAFF | Staff | BUDGET | Approved Early Budget | 5226601.71 | 3713.79 | 3713.79 | 0 | 0 | 0 | 0 | 0 | -64970.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5169058.74
E15004 | SCL Prelims Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 355109.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71607.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426717.13
E15004 | SCL Prelims Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | -2159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2159
E15004 | SCL Prelims Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1722.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1722.32
E15004 | SCL Prelims Tunnels | STAFF | Staff | BUDGET | Approved Early Budget | 5718999.9 | 176601.07 | 169173.5 | 75925.76 | 0 | 0 | 0 | 0 | -9437.77 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6162062.46
E15004 | SCL Prelims Tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 24883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159
E15010 | Northbound Running Tunnels Plant | MAT | Materials | BUDGET | Approved Early Budget | 298221.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298221.42
E15010 | Northbound Running Tunnels Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 72206.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35910.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108117.74
E15010 | Northbound Running Tunnels Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8483986.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34021.03 | 0 | 0 | 0 | 0 | -1216059.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7233905.6
E15010 | Northbound Running Tunnels Plant | STAFF | Staff | BUDGET | Approved Early Budget | 24945.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1889.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23055.7
E15010 | Northbound Running Tunnels Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2143768.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2143768.6
E15011 | Northbound Running Tunnels Materials | LAB | Labour | BUDGET | Approved Early Budget | 58.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.67
E15011 | Northbound Running Tunnels Materials | MAT | Materials | BUDGET | Approved Early Budget | 1255210.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255210.48
E15011 | Northbound Running Tunnels Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 41027.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41027.79
E15011 | Northbound Running Tunnels Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 26014.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26014.15
E15011 | Northbound Running Tunnels Materials | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4
E15011 | Northbound Running Tunnels Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 535487.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1217.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534269.51
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | LAB | Labour | BUDGET | Approved Early Budget | 2394453.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2397209.52
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 89111.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89111.07
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | STAFF | Staff | BUDGET | Approved Early Budget | 139787.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139787.99
E15013 | Southbound Running Tunnels Plant | MAT | Materials | BUDGET | Approved Early Budget | 310154.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310154.95
E15013 | Southbound Running Tunnels Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 42629.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35910.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78540.39
E15013 | Southbound Running Tunnels Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8545746.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34020.92 | 0 | 0 | 0 | 0 | 0 | -1216059.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7295666.18
E15013 | Southbound Running Tunnels Plant | STAFF | Staff | BUDGET | Approved Early Budget | 24945.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1889.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23055.71
E15013 | Southbound Running Tunnels Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2116900.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116900.27
E15014 | Southbound Running Tunnels Materials | MAT | Materials | BUDGET | Approved Early Budget | 1140446.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140446.7
E15014 | Southbound Running Tunnels Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 48367.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48367.76
E15014 | Southbound Running Tunnels Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 166407.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166407.36
E15014 | Southbound Running Tunnels Materials | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4
E15014 | Southbound Running Tunnels Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 545238.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1217.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544020.75
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | LAB | Labour | BUDGET | Approved Early Budget | 2348574.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2348574.16
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | MAT | Materials | BUDGET | Approved Early Budget | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 114328.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114328.19
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | STAFF | Staff | BUDGET | Approved Early Budget | 139787.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139787.98
E15020 | Site Facilities & Logistics | MAT | Materials | BUDGET | Approved Early Budget | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390
E15020 | Site Facilities & Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1641.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1641.6
E15022 | Running Tunnels (TBM) | LAB | Labour | BUDGET | Approved Early Budget | 26311.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26311.86
E15022 | Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | 173673.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199803.87
E15022 | Running Tunnels (TBM) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 234.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.84
E15022 | Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 70589.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18120.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88709.48
E15022 | Running Tunnels (TBM) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4898434.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10972.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4909407.77
E15024 | SCL Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 827543.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848729.96
E15024 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | 1515776.06 | 32195.09 | 26448.23 | 18857.67 | 0 | 0 | 0 | 0 | -7400.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585876.24
E15024 | SCL Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | 465162.56 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 25427.14 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515089.7
E15024 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 339519.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15082.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354601.85
E15024 | SCL Tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 364305.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364305.6
E15024 | SCL Tunnels | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 1201.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201.1
E15031 | SCL PPE | MAT | Materials | BUDGET | Approved Early Budget | 12129.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12129.97
E15031 | SCL PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1420.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420.14
E15031 | SCL PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 195013.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198064.04
E15032 | TBM PPE | MAT | Materials | BUDGET | Approved Early Budget | 41648.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41648.68
E15032 | TBM PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2365.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365.44
E15032 | TBM PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 110751.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110751.13
E15042 | Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | 246.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.67
E15042 | Running Tunnels (TBM) | MISC | Miscellaneous | BUDGET | Approved Early Budget | -87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87
E15042 | Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87
E15042 | Running Tunnels (TBM) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15044 | SCL Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 178.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178.5
E15044 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | 1111.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111.27
E15044 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 20458.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20458.63
E25110 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | -88.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88.5
E25110 | SCL Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | -62999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62999.99
E25110 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 63286.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63286.39
E35010 | Construction of CP1 | LAB | Labour | BUDGET | Approved Early Budget | 1275837.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3604.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272233.17
E35010 | Construction of CP1 | MAT | Materials | BUDGET | Approved Early Budget | 347664.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326923.21
E35010 | Construction of CP1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 164956.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164956.22
E35010 | Construction of CP1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 42417.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42417.53
E35010 | Construction of CP1 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 449.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.78
E35020 | Construction of CP2 | LAB | Labour | BUDGET | Approved Early Budget | 834759.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835009.8
E35020 | Construction of CP2 | MAT | Materials | BUDGET | Approved Early Budget | 239688.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256760.49
E35020 | Construction of CP2 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 37813.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37813.98
E35020 | Construction of CP2 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 394.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394.78
E35030 | Construction of CP3 | LAB | Labour | BUDGET | Approved Early Budget | 1155491.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185415.39
E35030 | Construction of CP3 | MAT | Materials | BUDGET | Approved Early Budget | 257062.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65355.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322418.44
E35030 | Construction of CP3 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 39405.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18448.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57853.75
E35030 | Construction of CP3 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 394.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394.76
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 331.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331.75
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1635417.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636017.95
E35070 | Excavation and Primary lining (TBM Launch Galleries) | MAT | Materials | BUDGET | Approved Early Budget | 685.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685.44
E35070 | Excavation and Primary lining (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880
E35070 | Excavation and Primary lining (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1120381.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120381.57
E35080 | Waterproofing (TBM Launch Galleries) | LAB | Labour | BUDGET | Approved Early Budget | 11186.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11186.48
E35080 | Waterproofing (TBM Launch Galleries) | MAT | Materials | BUDGET | Approved Early Budget | 12.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.54
E35080 | Waterproofing (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 65.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.85
E35080 | Waterproofing (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 195948.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195598.44
E35090 | Secondary lining TBM Launch Galleries | LAB | Labour | BUDGET | Approved Early Budget | 492031.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3136.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488894.58
E35090 | Secondary lining TBM Launch Galleries | MAT | Materials | BUDGET | Approved Early Budget | 313486.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62603.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250883.3
E35090 | Secondary lining TBM Launch Galleries | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 18427.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5893.16
E35090 | Secondary lining TBM Launch Galleries | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 959686.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968689.19
E35100 | KP Secondary lining | LAB | Labour | BUDGET | Approved Early Budget | 327398.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327398.41
E35100 | KP Secondary lining | MAT | Materials | BUDGET | Approved Early Budget | 169796.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169796.21
E35100 | KP Secondary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6423.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6423.22
E35100 | KP Secondary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 308800.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308800.76
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | LAB | Labour | BUDGET | Approved Early Budget | 241436.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241436.76
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | MAT | Materials | BUDGET | Approved Early Budget | 105564.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106270.81
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11919.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11919.43
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 84271.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84271.42
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | LAB | Labour | BUDGET | Approved Early Budget | 2212084.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11996.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200088.26
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | MAT | Materials | BUDGET | Approved Early Budget | 838316.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838316.99
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14780.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14901.45
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 48881.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48881.65
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 95897.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18460.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114357.43
E35150 | KG Waterproofing (excl 1st stage concrete and drainage) | LAB | Labour | BUDGET | Approved Early Budget | 5192.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192.28
E35150 | KG Waterproofing (excl 1st stage concrete and drainage) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 219228.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223228.64
E35160 | KG Northbound Secondary lining | LAB | Labour | BUDGET | Approved Early Budget | 521048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521048.2
E35160 | KG Northbound Secondary lining | MAT | Materials | BUDGET | Approved Early Budget | 327562.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327562.61
E35160 | KG Northbound Secondary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5015.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5015.29
E35160 | KG Northbound Secondary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 494958.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494958.86
E35170 | KP Above ground & Enabling Works KP | LAB | Labour | BUDGET | Approved Early Budget | 221950.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221950.47
E35170 | KP Above ground & Enabling Works KP | MAT | Materials | BUDGET | Approved Early Budget | 138062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138062.5
E35170 | KP Above ground & Enabling Works KP | MISC | Miscellaneous | BUDGET | Approved Early Budget | 864.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864.68
E35170 | KP Above ground & Enabling Works KP | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 79280.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79280.33
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | LAB | Labour | BUDGET | Approved Early Budget | 1670352.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21347.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649005.19
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | MAT | Materials | BUDGET | Approved Early Budget | 375120.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375120.91
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 15379.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15379.13
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8557.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8557.17
E35190 | KP Waterproofing (excl 1st stage concrete and drainage) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.78
E35190 | KP Waterproofing (excl 1st stage concrete and drainage) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 89837.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92557.49
E35210 | Above ground & Enabling Works Overrun | LAB | Labour | BUDGET | Approved Early Budget | 491418.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68200.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423218.48
E35210 | Above ground & Enabling Works Overrun | MAT | Materials | BUDGET | Approved Early Budget | 31021.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31021.61
E35210 | Above ground & Enabling Works Overrun | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 808.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808.8
E35210 | Above ground & Enabling Works Overrun | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 37189.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37189.82
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | LAB | Labour | BUDGET | Approved Early Budget | 195625.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197966.03
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | MAT | Materials | BUDGET | Approved Early Budget | 100976.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100976.98
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5856.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9117.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14973.77
E35309 | Overrun Tunnels Waterproofing including CP4 & CP5 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 100315.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100846.03
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | LAB | Labour | BUDGET | Approved Early Budget | 119431.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26338.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93093.05
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | MAT | Materials | BUDGET | Approved Early Budget | 77790.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79155.51
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 992.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992.29
E35370 | Northbound Running Supply of PC Segment | LAB | Labour | BUDGET | Approved Early Budget | 181404.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180486.08
E35370 | Northbound Running Supply of PC Segment | MAT | Materials | BUDGET | Approved Early Budget | 4659188.64 | 12855.84 | 12855.84 | 0 | 0 | 0 | 0 | 0 | -25711.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4659188.64
E35370 | Northbound Running Supply of PC Segment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225
E35370 | Northbound Running Supply of PC Segment | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 59362.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55458.47 | 5000 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121921.37
E35380 | Northbound Running Power Consumption | LAB | Labour | BUDGET | Approved Early Budget | 2101.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101.43
E35380 | Northbound Running Power Consumption | MISC | Miscellaneous | BUDGET | Approved Early Budget | 336401.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336401.07
E35380 | Northbound Running Power Consumption | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35390 | Northbound Running Fuel Consumption | MAT | Materials | BUDGET | Approved Early Budget | 31544.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31544.14
E35410 | Northbound Running Grout Materials | LAB | Labour | BUDGET | Approved Early Budget | 11034.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11034.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35410 | Northbound Running Grout Materials | MAT | Materials | BUDGET | Approved Early Budget | 402771.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403925.97
E35410 | Northbound Running Grout Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8694.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8694.29
E35410 | Northbound Running Grout Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -4281.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4281.39
E35415 | Northbound General Plant Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3166
E35431 | Tunnel Labour below ground | LAB | Labour | BUDGET | Approved Early Budget | 3178768.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2906.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175861.25
E35431 | Tunnel Labour below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 284116.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284116.7
E35432 | Tunnel Labour Above Ground | LAB | Labour | BUDGET | Approved Early Budget | 2615256.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1306.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2613949.66
E35450 | Southbound Running Supply of PC Segments | MAT | Materials | BUDGET | Approved Early Budget | 4676741.57 | 12855.84 | 12855.84 | 0 | 0 | 0 | 0 | 0 | -25711.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4676741.57
E35450 | Southbound Running Supply of PC Segments | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35450 | Southbound Running Supply of PC Segments | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 59362.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55458.47 | 5000 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121921.37
E35460 | Southbound Running Power Consumption | LAB | Labour | BUDGET | Approved Early Budget | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
E35460 | Southbound Running Power Consumption | MISC | Miscellaneous | BUDGET | Approved Early Budget | 341425.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341425.63
E35460 | Southbound Running Power Consumption | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35470 | Southbound Running Fuel Consumption | MAT | Materials | BUDGET | Approved Early Budget | 16033.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16033.36
E35480 | Southbound Running Supply of SGI Rings | LAB | Labour | BUDGET | Approved Early Budget | 190160.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -873.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189286.96
E35480 | Southbound Running Supply of SGI Rings | MAT | Materials | BUDGET | Approved Early Budget | 426409.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426409.51
E35480 | Southbound Running Supply of SGI Rings | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3508.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3508.8
E35480 | Southbound Running Supply of SGI Rings | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 829.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829.45
E35490 | Northbound Running Supply of SGI RINGS | MAT | Materials | BUDGET | Approved Early Budget | 428150.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428150.54
E35490 | Northbound Running Supply of SGI RINGS | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075
E35490 | Northbound Running Supply of SGI RINGS | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1072.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072.6
E35511 | Tunnel Labour Below Ground | LAB | Labour | BUDGET | Approved Early Budget | 3212004.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2906.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3209097.67
E35511 | Tunnel Labour Below Ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 284116.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284116.7
E35512 | Tunnel Labour Above Ground | LAB | Labour | BUDGET | Approved Early Budget | 2562091.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1306.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560784.32
E35537 | TBM | MAT | Materials | BUDGET | Approved Early Budget | -28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28600
E35537 | TBM | MISC | Miscellaneous | BUDGET | Approved Early Budget | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28600
E35537 | TBM | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 370410.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370410.2
E35547 | Conveyor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 44147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44147
E35557 | Locomotives | MAT | Materials | BUDGET | Approved Early Budget | 4381.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4381.88
E35557 | Locomotives | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3603
E35557 | Locomotives | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10525.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525.33
E35567 | Other | LAB | Labour | BUDGET | Approved Early Budget | 19.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.22
E35567 | Other | MAT | Materials | BUDGET | Approved Early Budget | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618
E35567 | Other | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10028.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10028.55
E35567 | Other | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212.5
E35570 | Southbound Running Grout Materials | MAT | Materials | BUDGET | Approved Early Budget | 402354.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402354.32
E35570 | Southbound Running Grout Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5942.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5942.8
E35570 | Southbound Running Grout Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1263.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1263.69
E35577 | TBM | MAT | Materials | BUDGET | Approved Early Budget | -24475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24475
E35577 | TBM | MISC | Miscellaneous | BUDGET | Approved Early Budget | 24475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24475
E35577 | TBM | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 370410.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370410.19
E35587 | Conveyor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 57397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57397
E35597 | Locomotives | MAT | Materials | BUDGET | Approved Early Budget | 1780.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1780.32
E35597 | Locomotives | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2601.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601.51
E35597 | Locomotives | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 20232.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20232.03
E35607 | Other | LAB | Labour | BUDGET | Approved Early Budget | 19.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.22
E35607 | Other | MAT | Materials | BUDGET | Approved Early Budget | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618
E35607 | Other | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16227.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16227.6
E35607 | Other | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212.5
E35610 | North and South bound Ground treatment | MAT | Materials | BUDGET | Approved Early Budget | 491.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.88
E35620 | KG SCL pilot (26m) Excavation and Primary lining | LAB | Labour | BUDGET | Approved Early Budget | 783075.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783075.77
E35620 | KG SCL pilot (26m) Excavation and Primary lining | MAT | Materials | BUDGET | Approved Early Budget | 214252.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214252.87
E35620 | KG SCL pilot (26m) Excavation and Primary lining | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1202.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202.87
E35620 | KG SCL pilot (26m) Excavation and Primary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 77265.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77265.57
E35620 | KG SCL pilot (26m) Excavation and Primary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 68953.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68953.91
E35630 | KG SGI Rings Supply and Installation | LAB | Labour | BUDGET | Approved Early Budget | 3681565.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28458.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3710024.27
E35630 | KG SGI Rings Supply and Installation | MAT | Materials | BUDGET | Approved Early Budget | 1061736.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061736.24
E35630 | KG SGI Rings Supply and Installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 138997.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138997.69
E35630 | KG SGI Rings Supply and Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 54504.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6162.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60667.53
E35630 | KG SGI Rings Supply and Installation | STAFF | Staff | BUDGET | Approved Early Budget | 19888.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4613.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15275.93
E35630 | KG SGI Rings Supply and Installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 46809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50592.91
E35636 | KG SGI Rings Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 69786.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69786.24
E35636 | KG SGI Rings Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -38084.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38084.61
E35636 | KG SGI Rings Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 91016.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91016.58
E35636 | KG SGI Rings Purchased Plant | STAFF | Staff | BUDGET | Approved Early Budget | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62
E35637 | KG SGI Rings Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 6788.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6788.37
E35637 | KG SGI Rings Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197
E35637 | KG SGI Rings Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 294496.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294496.75
E35638 | KG SGI Rings Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 43605.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43605.3
E35638 | KG SGI Rings Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2796.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796.93
E35638 | KG SGI Rings Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 72660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72660.85
E35639 | KG SGI Rings Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 6825.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6825.7
E35639 | KG SGI Rings Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9312.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9312.61
E35650 | KP Dewatering | MISC | Miscellaneous | BUDGET | Approved Early Budget | 102229.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10383.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112613.08
E35660 | KP SCL pilot (26m) Excavation and Primary lining | LAB | Labour | BUDGET | Approved Early Budget | 717765.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717765.94
E35660 | KP SCL pilot (26m) Excavation and Primary lining | MAT | Materials | BUDGET | Approved Early Budget | 209297.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211967.44
E35660 | KP SCL pilot (26m) Excavation and Primary lining | MISC | Miscellaneous | BUDGET | Approved Early Budget | 6121.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6121.65
E35660 | KP SCL pilot (26m) Excavation and Primary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5790.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790.96
E35660 | KP SCL pilot (26m) Excavation and Primary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 14942.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14942.67
E35670 | KP SGI Rings Supply and Installation | LAB | Labour | BUDGET | Approved Early Budget | 3950232.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3951293.51
E35670 | KP SGI Rings Supply and Installation | MAT | Materials | BUDGET | Approved Early Budget | 778028.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780698.36
E35670 | KP SGI Rings Supply and Installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 112587.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112587.64
E35670 | KP SGI Rings Supply and Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22084.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22084.07
E35670 | KP SGI Rings Supply and Installation | STAFF | Staff | BUDGET | Approved Early Budget | 19444.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4168.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15275.92
E35670 | KP SGI Rings Supply and Installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 23952.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3339.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27291.7
E35676 | KP SGI Rings Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 63402.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63402.68
E35676 | KP SGI Rings Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -47654.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47654.31
E35676 | KP SGI Rings Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 126964.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126964.96
E35676 | KP SGI Rings Purchased Plant | STAFF | Staff | BUDGET | Approved Early Budget | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62
E35677 | KP SGI Rings Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 5315.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5315.5
E35677 | KP SGI Rings Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571
E35677 | KP SGI Rings Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 207420.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207420.74
E35678 | KP SGI Rings Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 36186.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36186.97
E35678 | KP SGI Rings Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3267.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3267.61
E35678 | KP SGI Rings Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 78404.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78404.63
E35679 | KP SGI Rings Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 9058.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9058.49
E35679 | KP SGI Rings Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1568.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568.25
E35679 | KP SGI Rings Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2800.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800.72
E35680 | Tunnelling incl. junctions to existing platform tunnels | LAB | Labour | BUDGET | Approved Early Budget | 3411361.94 | 814410.52 | 255968.56 | 122430.14 | 0 | 0 | 0 | 0 | -55848.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4548322.57
E35680 | Tunnelling incl. junctions to existing platform tunnels | MAT | Materials | BUDGET | Approved Early Budget | 591792.17 | 41918.17 | 44246.13 | 22170.67 | 0 | 0 | 0 | 0 | -2796.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697330.91
E35680 | Tunnelling incl. junctions to existing platform tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5338.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19588.88
E35680 | Tunnelling incl. junctions to existing platform tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 61611.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26079.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87690.31
E35680 | Tunnelling incl. junctions to existing platform tunnels | STAFF | Staff | BUDGET | Approved Early Budget | 16316.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16316.55
E35680 | Tunnelling incl. junctions to existing platform tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 221640.77 | 146432.27 | 123653.92 | 30913.48 | 0 | 0 | 0 | 0 | -318193.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204446.84
E35686 | KStation CP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 2029.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303.58
E35686 | KStation CP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23961.79 | 47165.89 | 34382.77 | 36951.12 | 0 | 0 | 0 | 0 | -115963.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26497.79
E35687 | KStation CP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1551.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3331.1
E35687 | KStation CP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 57795.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290046.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347841.95
E35687 | KStation CP Hire Plant | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602
E35687 | KStation CP Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 497150 | 16270.25 | 6508.1 | 1627.03 | 0 | 0 | 0 | 0 | 191675.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713231.35
E35688 | KStation CP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 1882.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575.68
E35688 | KStation CP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 974.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 974.6
E35689 | KStation CP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 65.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135.88
E35690 | Southbound General Plant Materials | LAB | Labour | BUDGET | Approved Early Budget | 3805.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805.01
E35690 | Southbound General Plant Materials | MAT | Materials | BUDGET | Approved Early Budget | 654009.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654801.83
E35690 | Southbound General Plant Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 105397.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105397.45
E35690 | Southbound General Plant Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 920943.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920943.2
E35690 | Southbound General Plant Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 82098.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82098.98
E35705 | Running CP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 2875.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875.49
E35705 | Running CP Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 10985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10985
E35705 | Running CP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 13465.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13465.21
E35706 | Running CP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 992.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.38
E35706 | Running CP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 329450.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145262.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474712.63
E35707 | Running CP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 564.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20139.27
E35707 | Running CP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 860.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860.57
E35708 | Running CP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 5754.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6239.57
E35708 | Running CP Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 535.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535.15
E35715 | Launch Galleries Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 578.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578.63
E35715 | Launch Galleries Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2227.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2227.32
E35716 | Launch Galleries Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 832.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832.25
E35716 | Launch Galleries Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 230561.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27741.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202820.91
E35716 | Launch Galleries Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 385556.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385556.06
E35717 | Launch Galleries Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 1218.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218.2
E35717 | Launch Galleries Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5
E35718 | Launch Galleries Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 803.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803.57
E35720 | KG plant | MAT | Materials | BUDGET | Approved Early Budget | 12446.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12446.5
E35720 | KG plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -33213.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33213.44
E35720 | KG plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14079.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14079.61
E35725 | KG Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 81918.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81798.78
E35725 | KG Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 43723.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43723.85
E35725 | KG Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 560070.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554670.35
E35726 | KG Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1058.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058.71
E35726 | KG Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 21800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21800
E35726 | KG Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 296523.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26665.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269858.18
E35726 | KG Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 20909.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20909.26
E35727 | KG Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 43120.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43120.58
E35727 | KG Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5539.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5539.95
E35727 | KG Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 115801.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115801.53
E35728 | KG Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 10649.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10649.86
E35728 | KG Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 727.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727.32
E35728 | KG Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 348.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348.6
E35730 | KP Plant | LAB | Labour | BUDGET | Approved Early Budget | 5914.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5914.25
E35730 | KP Plant | MAT | Materials | BUDGET | Approved Early Budget | 217.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217.63
E35730 | KP Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -21983.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21983.8
E35730 | KP Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 39692.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39692.78
E35735 | KP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 45894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45774.66
E35735 | KP Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 22711.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22711.39
E35735 | KP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 357272.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351872.48
E35736 | KP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1804.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804.59
E35736 | KP Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 21800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21800
E35736 | KP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 293854.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26665.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267189.37
E35736 | KP Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 13777.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13777.5
E35737 | KP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 33185.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33185.2
E35737 | KP Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5540
E35737 | KP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 94144.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94144.59
E35738 | KP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 7507.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7507.51
E35738 | KP Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 727.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727.32
E35738 | KP Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4586.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4586.6
E35765 | Overrun tunnels Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 1356.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356.48
E35765 | Overrun tunnels Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5129
E35766 | Overrun tunnels Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397.52
E35766 | Overrun tunnels Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 31401.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60923.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92325.11
E35766 | Overrun tunnels Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991.25
E35767 | Overrun tunnels Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1434.7
E35767 | Overrun tunnels Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9075.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9075.64
E35768 | Overrun tunnels Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 5756.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5756.31
E35800 | Northbound Running Consumables | MAT | Materials | BUDGET | Approved Early Budget | 805964.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805964.85
E35800 | Northbound Running Consumables | MISC | Miscellaneous | BUDGET | Approved Early Budget | 49718.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49718.82
E35800 | Northbound Running Consumables | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 348331.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348331.29
E35800 | Northbound Running Consumables | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 104639.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104639.64
E35890 | Southbound Running Consumables | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1760
E35890 | Southbound Running Consumables | MAT | Materials | BUDGET | Approved Early Budget | 814143.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814143.63
E35890 | Southbound Running Consumables | MISC | Miscellaneous | BUDGET | Approved Early Budget | 64873.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64873.85
E35890 | Southbound Running Consumables | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 319329.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319329.94
E35890 | Southbound Running Consumables | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 104639.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104639.64
E45318 | Fit Out | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.71
E45318 | Fit Out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | LAB | Labour | BUDGET | Approved Early Budget | 1061.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41153.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42215.05
E45352 | Tunnel Fit Out - M&E | MAT | Materials | BUDGET | Approved Early Budget | 21678.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -231.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21446.49
E45352 | Tunnel Fit Out - M&E | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14699.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14699.76
E45352 | Tunnel Fit Out - M&E | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2344.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8903.43
E45352 | Tunnel Fit Out - M&E | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1034478.43 | 522006.48 | 134228.09 | 184925.42 | 462701.75 | 449836.1 | 395757.93 | 416993.44 | 659472.61 | 250365.23 | 330191.82 | 1041718.92 | 909152.35 | 787017.66 | 599969.43 | 239733.78 | 192309.52 | 79826.59 | 0 | 0 | 101597.48 | 14513.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8806796.96
E45354 | SCL Tunnel Fit Out | MAT | Materials | BUDGET | Approved Early Budget | 2075.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2356.47
E45374 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 472.52 | 0 | 6355.72 | 542.69 | 542.69 | 542.69 | 0 | 0 | -6668.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787.67
E45381 | M&E Material (CP) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.84
E45385 | Kennington Station cross passages Fit Out | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 131000 | 35000 | 9000 | 9000 | 9000 | -175759 | 25000 | 25000 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142241
E45385 | Kennington Station cross passages Fit Out | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7621
E45385 | Kennington Station cross passages Fit Out | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 16059.73 | 16059.65 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63119.38
E45385 | Kennington Station cross passages Fit Out | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5390.2 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17390.2
E45385 | Kennington Station cross passages Fit Out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 339000 | 173000 | 94000 | 46000 | 62000 | -190848.94 | 126091.2 | 160602.65 | 119538.05 | 97927.88 | 56235.27 | 60656.46 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194202.57
E45910 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 479.3 | 229.48 | 0 | 550.46 | 550.46 | 550.46 | 550.46 | 27217.83 | -18376.1 | 0 | 0 | 0 | 0 | 1075.97 | 10829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23657.32
E45920 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 258112.9 | 0 | 0 | 0 | 0 | 255876.51 | 311907.53 | 848759.12 | -68188.4 | 0 | 169587.26 | 425838.59 | 1179421.19 | 1894327.09 | 2273633.1 | 1930509.86 | 1197813.93 | 881188.7 | 374089.54 | 523725.36 | 282645.43 | 409939.79 | 74817.91 | 63200.38 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13484706.99
E65505 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 217251.3 | 217251.3 | 217251.3 | 217251.3 | 217251.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1477308.84
E65542 | SPJ Tunnel Fit Out - T&C | MAT | Materials | BUDGET | Approved Early Budget | 3468.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3468.15
E65568 | T&C Material (CP) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.94
F08600 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 167960.56 | 1491 | 8397.25 | 9014.13 | 9746.94 | 9571.94 | 9659.44 | 9484.44 | 5118.14 | 14294.46 | 14774.76 | 15777.26 | 16213.26 | 16213.26 | 16508.26 | 16184.26 | 16191.76 | 16540.76 | 14771.67 | 14891.67 | 13539.17 | 13039.17 | 13375.32 | 10765.82 | 10765.82 | 9939.23 | 8150.73 | 7650.73 | 7400.73 | 7225.73 | 7225.73 | 7225.73 | 7225.73 | 6656.69 | 6656.69 | 5756.69 | 5496.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550901.62
F08610 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181.84 | 1761.96 | 3568.54 | 7647.89 | 9384.7 | 2823.47 | 3585.32 | 1531.93 | 3796.94 | 4156.19 | 4643.93 | 3713.31 | 2173.5 | 887.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49857.29
F16002 | K.Shafts Prelims Kennington - PHASE 1 | LAB | Labour | BUDGET | Approved Early Budget | 270704.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270704.04
F16002 | K.Shafts Prelims Kennington - PHASE 1 | MAT | Materials | BUDGET | Approved Early Budget | 38797.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38797.07
F16002 | K.Shafts Prelims Kennington - PHASE 1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | -140.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140.54
F16002 | K.Shafts Prelims Kennington - PHASE 1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 444.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444.01
F16002 | K.Shafts Prelims Kennington - PHASE 1 | STAFF | Staff | BUDGET | Approved Early Budget | 1349152.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349152.73
F16004 | K.Shafts Prelims Kennington - PHASE II | MISC | Miscellaneous | BUDGET | Approved Early Budget | -23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16004 | K.Shafts Prelims Kennington - PHASE II | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16004 | K.Shafts Prelims Kennington - PHASE II | STAFF | Staff | BUDGET | Approved Early Budget | 299170.82 | 55424.7 | 111116.11 | 55306.69 | 59880 | 79310 | 79987.5 | 80352.5 | 68107.22 | 67726.87 | 61700 | 61700 | 61700 | 61700 | 61700 | 72060 | 50010 | 47810 | 47810 | 47810 | 43410 | 43410 | 41210 | 23285 | 23285 | 20210 | 12560 | 12560 | 12560 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845752.41
F16020 | K.Shafts Prelims Site Facilities & Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16020 | K.Shafts Prelims Site Facilities & Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | -56683.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5320 | 5320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46043.93
F16022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 99510.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100289.06
F16022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 400067.55 | 22325 | 15947 | 22325 | 22325 | 22325 | 19250 | 18500 | -110042.63 | 13324.99 | 14074.99 | 13324.99 | 13324.99 | 13324.99 | 8412.5 | 7662.5 | 7662.5 | 7662.5 | 8412.5 | 7662.5 | 7662.5 | 7662.5 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623665.62
F16022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 53798.13 | 0 | 0 | 0 | 5248 | 2624 | 5248 | 2624 | -15744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5248 | 5248 | 5248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69542.13
F16022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 292035.89 | 3828 | 4794.41 | 6368.1 | 12274.57 | 6334.82 | 13307.33 | 4877 | 76043.97 | 5040 | 5040 | 8971.87 | 14555.6 | 14555.6 | 15315.6 | 14555.6 | 11383.73 | 5800 | 5040 | 5040 | 4870 | 3040 | 3040 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536872.09
F16024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 260993.49 | 0 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 5828.98 | 14252.54 | 14284.73 | 14284.73 | 14284.73 | 14284.73 | 14284.73 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 21853.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611365.91
F16024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 135636.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.98 | 222 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 406.25 | 0 | 0 | 2096.5 | 0 | 0 | 1048.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139837.03
F16024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 800869.39 | 0 | 925 | 75 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852645.39
F16024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23998.31 | 97 | 661.25 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 470.73 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 303.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45315.12
F16024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4301.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12414.96 | 6436.3 | 8406.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31558.88
F16024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2987.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2987.79
F16026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 63371.23 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | -12770.35 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75003.34
F16026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 213.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12708.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12922.58
F16026 | IT Equipment & running costs | STAFF | Staff | BUDGET | Approved Early Budget | 2760.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2771.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5531.82
F16026 | IT Equipment & running costs | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2711.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59.13
F16028 | Environmental Control | LAB | Labour | BUDGET | Approved Early Budget | 145754.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148950.87
F16028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 762616.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23991.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786608.52
F16028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 130284.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131284.2
F16028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 35898.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24189.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11708.22
F16028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 182631.92 | 11555.08 | 29876.18 | -21905.02 | 2055.08 | 3211.08 | 3939.08 | 1411.08 | -12415.38 | 2171 | 2171 | 2171 | 2171 | 2171 | 2152 | 2152 | 2152 | 11256 | 2152 | 2152 | 2627 | 2652 | 2652 | 2152 | 125 | 125 | 125 | 125 | 125 | 17.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243956.05
F16028 | Environmental Control | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794
F16030 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 4800.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800.54
F16030 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1144.19 | 3084.33 | 4539.99 | 3140 | 2806 | 2806 | 2806 | 1485.33 | 2541.2 | 1858.85 | 1858.85 | 1858.85 | 2408.85 | 550 | 550 | 550 | 550 | 0 | 0 | 6903 | 2408.85 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44400.29
F16030 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 15801.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4059.9 | 176.6 | 176.6 | 176.6 | 176.6 | 176.6 | 176.6 | 130.2 | 130.2 | 130.2 | 130.2 | 176.6 | 176.6 | 176.6 | 130.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22101.6
F16030 | H&S Quality Environmental | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 23031.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683.6 | 1683.6 | 1683.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4368 | 3290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35740.08
F16030 | H&S Quality Environmental | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 909.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909.25
F16031 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 445.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695.79
F16031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 24951.44 | 2450 | 6356.84 | 1982.93 | 1122.31 | 1982.93 | 1440.81 | 1982.93 | 12937.52 | 5619.9 | 1982.93 | 1982.93 | 1982.93 | 1982.93 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78517.49
F16032 | Liaison and Coordination with others | LAB | Labour | BUDGET | Approved Early Budget | 22370.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22370.87
F16032 | Liaison and Coordination with others | MAT | Materials | BUDGET | Approved Early Budget | 13534.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13534.2
F16032 | Liaison and Coordination with others | MISC | Miscellaneous | BUDGET | Approved Early Budget | 75822.63 | 5248 | 78 | 672 | 500 | 750 | 0 | 0 | -2123.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82946.71
F16032 | Liaison and Coordination with others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 18334.12 | 3362 | 0 | 0 | 416 | 0 | 0 | 416 | 15173.41 | 0 | 1889 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41670.53
F16034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770
F16034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 12651.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6823.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5828.32
F16034 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1776.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776.5
F16034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14342.5 | 5116 | 21307.95 | 2976.37 | 1512.79 | 2976.37 | 2976.37 | 2976.37 | 31539.84 | 7476.84 | 3511.6 | 4790.92 | 3593.19 | 3593.19 | 4789.87 | 6625.11 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4188.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157800.78
F16034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 910.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910.67
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | LAB | Labour | BUDGET | Approved Early Budget | 244922.54 | 3666.6 | 7179.9 | 9809.9 | 9993.9 | 9993.9 | 25760.7 | 27167.7 | -47049.35 | 29978.34 | 29978.34 | 29978.34 | 29978.34 | 27164.34 | 23472.02 | 16292.12 | 15413.79 | 15413.79 | 15413.79 | 12603.15 | 16408.35 | 16408.35 | 16408.35 | 15457.05 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765655.2
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | MAT | Materials | BUDGET | Approved Early Budget | 380481.36 | 87343.28 | 97568.56 | 71365.09 | 25885.2 | 11040.81 | 0 | 0 | -417903.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255780.65
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 187687.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12227.09 | 16081.85 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222296.19
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 71474.93 | 2646 | 2646 | 2646 | 2646 | 3646 | 2646 | 2646 | 593015.48 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 508.72 | 508.72 | 1508.72 | 508.72 | 508.72 | 3154.72 | 3154.72 | 3154.72 | 5292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715286.25
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 135767.76 | -1205.56 | 4920.87 | 331.44 | 331.44 | 331.44 | 331.44 | 331.44 | -5372.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35689.21 | 35689.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207146.18
F16038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 893972.6 | 42131 | 26869.53 | 26119.53 | 26119.53 | 18826.5 | 26357.1 | 26357.1 | 56014.25 | 27107.1 | 26357.1 | 26357.1 | 26607.1 | 26357.1 | 18826.5 | 12045.9 | 11295.9 | 11295.9 | 11295.9 | 19154.7 | 11295.9 | 12045.9 | 11795.9 | 11295.9 | 11295.9 | 12795.9 | 11295.9 | 11295.9 | 11795.9 | 7530.6 | 7530.6 | 7530.6 | 7530.6 | 3765.3 | 3765.3 | 3765.3 | 3765.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509564.14
F16038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 22309.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22309.27
F16038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 19012.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24012.75
F16038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3503.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3503.62
F16038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 65205 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74195
F16042 | Materials Handling Plant | LAB | Labour | BUDGET | Approved Early Budget | 13956.5 | 0 | 3024 | 3024 | 3024 | 1512 | 3024 | 3024 | -16632 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 1512 | 3024 | 3024 | 3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51756.5
F16042 | Materials Handling Plant | MAT | Materials | BUDGET | Approved Early Budget | 1267.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267.99
F16042 | Materials Handling Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11705.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11705.11
F16042 | Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 19289.54 | 0 | 0 | 1386 | 1386 | 753 | 1386 | 1386 | -2755.3 | 1326 | 1386 | 1386 | 753 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1299.2 | 839.2 | 839.2 | 839.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45359.04
F16042 | Materials Handling Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16044 | Cranage | LAB | Labour | BUDGET | Approved Early Budget | 16269.84 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | -29489.73 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 4775.4 | 0 | 0 | 0 | 0 | 0 | 4775.4 | 4775.4 | 4775.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110940.51
F16044 | Cranage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16044 | Cranage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 58486.26 | 21539.81 | 21666.23 | 16818.01 | 18997.2 | 10195.62 | 20206.2 | 18839.7 | 141615.17 | 18500 | 6312.88 | 5689.88 | 2463.07 | 1517.81 | 0 | 0 | 0 | 0 | 0 | 2463.07 | 2463.07 | 2463.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370237.05
F16046 | Passenger/Goods Hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5888.89 | -5546.89 | 13732.33 | 18322.83 | 5347.63 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54768.06
F16048 | General Plant | LAB | Labour | BUDGET | Approved Early Budget | 12325.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12325.69
F16048 | General Plant | MAT | Materials | BUDGET | Approved Early Budget | 23958.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25081.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49039.69
F16048 | General Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 6550.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6550.78
F16048 | General Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 132426.13 | 8768.68 | 8440.87 | 6817.15 | 6498.34 | 2676 | 3437 | 3237 | 60474.02 | 16403.58 | 3955 | 3055 | 2335 | 960 | 960 | 960 | 960 | 960 | 960 | 7023.36 | 7023.36 | 5173 | 4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288266.49
F16050 | Small Plant & PPE | MAT | Materials | BUDGET | Approved Early Budget | 8808.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7666.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16474.93
F16050 | Small Plant & PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16050 | Small Plant & PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 84939.62 | 2363.2 | 4467.36 | 1796.04 | 1806 | 1675 | 2447.2 | 2447.2 | 21590.97 | 7427.6 | 3011.2 | 3011.2 | 3064 | 984 | 0 | 0 | 0 | 0 | 0 | 4989.6 | 4989.6 | 3453.6 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154763.39
F16052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 17196.77 | 9960.3 | 9960.3 | 9960.3 | 9960.3 | 4980.15 | 9960.3 | 7470.23 | 24641.87 | 4980.15 | 4980.15 | 4980.15 | 4980.15 | 4980.15 | 2490.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131481.35
F16052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | 7667.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8945.18 | 0 | 0 | 0 | 1942.8 | 1942.8 | 1942.8 | 3885.6 | 3885.6 | 1942.8 | 1942.8 | 1942.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36040.85
F16052 | Scaffolding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 387 | 3478.96 | 1665.5 | 1390 | 695 | 1390 | 2403.96 | 13807.19 | 3437.32 | 3437.32 | 3437.32 | 695 | 695 | 347.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37267.07
F16052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21898.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24472.72
F26100 | Utilities | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26100 | Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26100 | Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26110 | Kennington Park | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26110 | Kennington Park | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26111 | KP-Trials Pits & Utilities Surveys | LAB | Labour | BUDGET | Approved Early Budget | 4432.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8428.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12861.2
F26111 | KP-Trials Pits & Utilities Surveys | MAT | Materials | BUDGET | Approved Early Budget | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745
F26111 | KP-Trials Pits & Utilities Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1423.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8428.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9852.44
F26111 | KP-Trials Pits & Utilities Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7946.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7946.98
F26112 | KP - Water Works (TW) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 127506.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43628.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83878.26
F26112 | KP - Water Works (TW) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17122.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17122.82
F26113 | KP-Gas works | MISC | Miscellaneous | BUDGET | Approved Early Budget | 929026.82 | 0 | 0 | 0 | 18970.25 | 0 | 0 | 0 | -18970.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184929.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113956.52
F26114 | KP - Cabling Works (UKPN-Comms) | MISC | Miscellaneous | BUDGET | Approved Early Budget | -18724.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18724.19
F26114 | KP - Cabling Works (UKPN-Comms) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16695.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16695.19
F26114 | KP - Cabling Works (UKPN-Comms) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26115 | KP-Permanent Connections (UKPN-Water) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 58800.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568.02 | 9568.02 | 0 | 0 | 0 | 0 | 9568.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87504.18
F26115 | KP-Permanent Connections (UKPN-Water) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26116 | KP-Surveys for UXO | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800
F26120 | Kennington Green | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26120 | Kennington Green | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26121 | KG-Trials Pits & Utilities Surveys | LAB | Labour | BUDGET | Approved Early Budget | 37163.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7060.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44224.42
F26121 | KG-Trials Pits & Utilities Surveys | MAT | Materials | BUDGET | Approved Early Budget | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340
F26121 | KG-Trials Pits & Utilities Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 18235.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18235.26
F26121 | KG-Trials Pits & Utilities Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1996.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996.85
F26122 | KG - Water Works (TW) | MAT | Materials | BUDGET | Approved Early Budget | 17545.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17545.76
F26122 | KG - Water Works (TW) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 574749.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574749.69
F26122 | KG - Water Works (TW) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17706.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17706.79
F26123 | KG-Gas works (SGN-NG) | MAT | Materials | BUDGET | Approved Early Budget | 6552.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6552.21
F26123 | KG-Gas works (SGN-NG) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 251341.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251341.66
F26123 | KG-Gas works (SGN-NG) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2411.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2411.9
F26124 | KG - Cabling Works (UKPN-Comms) | MAT | Materials | BUDGET | Approved Early Budget | 1579.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.28
F26124 | KG - Cabling Works (UKPN-Comms) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 915217.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915217.04
F26124 | KG - Cabling Works (UKPN-Comms) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -16695.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16695.19
F26124 | KG - Cabling Works (UKPN-Comms) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26125 | KG-Permanent Connections (UKPN-Water) | MAT | Materials | BUDGET | Approved Early Budget | 1071.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.12
F26125 | KG-Permanent Connections (UKPN-Water) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 65235.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9519.24 | 9519.24 | 0 | 0 | 0 | 0 | 0 | 9519.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93793.58
F26125 | KG-Permanent Connections (UKPN-Water) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 80.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.94
F26125 | KG-Permanent Connections (UKPN-Water) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26126 | KG-Surveys for UXO | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550
F36212 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 8760.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13137.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37242.19
F36212 | Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 19622.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19622.4
F36212 | Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 332.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332.5
F36212 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2759.3 | 4973 | 4872 | 0 | 0 | 0 | 0 | 0 | -12345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9125.03
F36212 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 23343.79 | 22195 | 15347 | 0 | 0 | 0 | 0 | 0 | 25268.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86154.34
F36213 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 502.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -319.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182.5
F36213 | Excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 252831.79 | 4620 | 4620 | 8830 | 0 | 0 | 0 | 0 | 14635.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285537.56
F36213 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 52341.33 | 10597.13 | 5298.57 | 0 | 0 | 0 | 0 | 0 | -24395.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43841.33
F36213 | Excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012
F36214 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 193901.64 | 103418.44 | 27009.96 | 4023.59 | 0 | 0 | 0 | 0 | 13779.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342133.44
F36214 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3700 | 0 | 1233.33 | 1233.33 | 1233.33 | 0 | 0 | 0 | 0 | 0 | 0 | 34028.55 | 38258.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72287.09
F36214 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38455
F36214 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 67059.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67059.9
F36216 | Piling ( Including Ring Beam) | LAB | Labour | BUDGET | Approved Early Budget | 148429.98 | 5563.43 | 10724.85 | 402 | 0 | 0 | 0 | 0 | 1573.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166694.16
F36216 | Piling ( Including Ring Beam) | MAT | Materials | BUDGET | Approved Early Budget | 356651.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13195.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369846.82
F36216 | Piling ( Including Ring Beam) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5519.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5519.38
F36216 | Piling ( Including Ring Beam) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 104956.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105609.93
F36216 | Piling ( Including Ring Beam) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1426299 | 1934.12 | 23484 | 15000 | 15000 | 0 | 0 | 0 | 259.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481976.26
F36217 | Slabs (Base intermediate) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 27812.26 | 25089.51 | 33664.76 | 46890.2 | 28855.51 | 24046.26 | 50497.14 | 225007.01 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479112.65
F36217 | Slabs (Base intermediate) | MAT | Materials | BUDGET | Approved Early Budget | 14748.44 | 15264.38 | 64424.53 | 91950.37 | 67999.47 | 93212.58 | 34337.57 | 30444.66 | 95841.05 | 20805.79 | 11273.4 | 28702.45 | 28702.45 | 2682.05 | 0 | 0 | 0 | 0 | 175 | 17728.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618292.88
F36217 | Slabs (Base intermediate) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -123600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -123600
F36217 | Slabs (Base intermediate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 526.29 | 1072.43 | 0 | 4289.71 | 4289.71 | 4289.71 | 4289.71 | 4289.71 | -8414.47 | 0 | 0 | 4660.85 | 4660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23954.5
F36217 | Slabs (Base intermediate) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36218 | Walls (Including Internal walls and finishes) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 9205.26 | 11200.42 | 16401 | 22956.39 | 15304.26 | 24231.73 | 15304.26 | 143021.43 | 52900 | 52900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363424.75
F36218 | Walls (Including Internal walls and finishes) | MAT | Materials | BUDGET | Approved Early Budget | 91273.91 | 11566.4 | 39377.86 | 7687.64 | 21487.64 | 68990.26 | 75393.67 | 61121.39 | -36.6 | 30151.99 | 13364.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420379.04
F36218 | Walls (Including Internal walls and finishes) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2853.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7297.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10150.88
F36219 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 4766.01 | 0 | 6310.79 | 2864.75 | 16277.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30219.06
F36219 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 10976.89 | 37571.12 | 17533.93 | -4129.9 | 7416.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69368.89
F36219 | Staircases | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 11129 | 11129 | 0 | 0 | 0 | -22258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 13977.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16810.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43925.2
F36222 | Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 7061.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7061.79
F36222 | Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 12487.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12487.21
F36222 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 32540.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11442.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29964.4
F36222 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5368.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5368.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36223 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 65554.69 | -199 | 199 | 0 | 0 | 0 | 0 | 0 | 10184.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75738.78
F36223 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 2355.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -542.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813.72
F36223 | Excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 53440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53440
F36223 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 28283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18641
F36224 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 338970 | 4930 | 280 | 0 | 0 | 0 | 0 | 0 | 7995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352175
F36224 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15288.43 | 15568.43 | 13158.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44015.29
F36224 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22955
F36224 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 67059.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67059.9
F36226 | Piling ( Including Ring Beam) | LAB | Labour | BUDGET | Approved Early Budget | 200057.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74767.82 | 0 | 6900 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286325.25
F36226 | Piling ( Including Ring Beam) | MAT | Materials | BUDGET | Approved Early Budget | 469999.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470345.91
F36226 | Piling ( Including Ring Beam) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 10992.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10992.85
F36226 | Piling ( Including Ring Beam) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -95350.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91850.33
F36226 | Piling ( Including Ring Beam) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1880949.34 | 13732 | -957.06 | 17225.06 | 0 | 0 | 0 | 0 | -61688.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1849260.79
F36227 | Slabs (Base intermediate) | LAB | Labour | BUDGET | Approved Early Budget | 105867.83 | 46796.58 | 39003.43 | 51963.38 | 41087.33 | 20543.66 | 42295.78 | 0 | 57850.05 | 3877 | 3877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413162.04
F36227 | Slabs (Base intermediate) | MAT | Materials | BUDGET | Approved Early Budget | 118526.32 | 67580.31 | 90186.77 | 30307.49 | 77527.18 | 49252.77 | 16205.23 | 23906.63 | 31213.15 | 10450 | 32904.38 | 32904.38 | 3120.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10392.24 | 10392.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604869.59
F36227 | Slabs (Base intermediate) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11575.05 | 1866.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13441.81
F36227 | Slabs (Base intermediate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7605.01 | 4289.71 | 8579.41 | 2144.85 | 2144.85 | 4289.71 | 2144.85 | 3977.06 | 75653.25 | 0 | 4660.85 | 4660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120150.4
F36227 | Slabs (Base intermediate) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36228 | Walls | LAB | Labour | BUDGET | Approved Early Budget | 37439.07 | 17155.62 | 45317.86 | 7645.55 | 1220.59 | 0 | 0 | 0 | 271773.97 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438052.66
F36228 | Walls | MAT | Materials | BUDGET | Approved Early Budget | 146131.55 | 38252.46 | 25901.4 | 49919.71 | 58973.47 | 55524.71 | 30844.47 | 17957.42 | -32246.11 | 17957.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409216.5
F36228 | Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4134.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30655.71 | 15282.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50072.37
F36229 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33324 | -59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33265
F36229 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58921.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58921.38
F36229 | Staircases | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 11361.5 | 33993.17 | 19399.75 | 15913.15 | 14241.83 | -94909.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36259 | K.Shafts Main Works Columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | -2128 | 2505.62 | 1888.08 | 1699.27 | 755.23 | 849.63 | 0 | 61946.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67516.75
F36259 | K.Shafts Main Works Columns | MAT | Materials | BUDGET | Approved Early Budget | 18064.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20678.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38742.91
F36259 | K.Shafts Main Works Columns | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 6530.25 | 37948.7 | 18472.49 | 3168.22 | 10165.55 | 0 | -76285.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36261 | Head House Structure (including External Roofing and Cladding) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36261 | Head House Structure (including External Roofing and Cladding) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170756.69 | -170756.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2
F36270 | K.Shafts Main Works Columns | LAB | Labour | BUDGET | Approved Early Budget | 15026.16 | 1636.33 | 0 | 1455.39 | 3044.52 | 1132.85 | 1132.85 | 0 | 41941.57 | 314.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65684.43
F36270 | K.Shafts Main Works Columns | MAT | Materials | BUDGET | Approved Early Budget | 17981.05 | 10629.23 | 17048.11 | 19777.39 | 15811.17 | 6066.69 | 18984.96 | 0 | -40404.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65893.81
F36270 | K.Shafts Main Works Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1510.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1510.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36272 | K.Shafts Main Works Head House Structure (including External Roofing and Cladding) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4734.43 | 21612.72 | -26347.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36272 | K.Shafts Main Works Head House Structure (including External Roofing and Cladding) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 82576.62 | 246120.7 | 338620.69 | -667318.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2
F46304 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 25152.13 | 0 | 0 | 0 | 0 | 0 | 0 | 117942.3 | 0 | 0 | 0 | 0 | 37892.45 | 134345.97 | 34447.69 | 13779.07 | 241133.8 | 48226.76 | 27558.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680478.32
F46306 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2076.27 | 0 | 0 | 583.7 | 999.68 | 959.43 | 938.5 | 1221.08 | 7348.52 | 0 | 0 | 0 | 0 | 24387.52 | 14467.17 | 26454.26 | 56996.52 | 44488.62 | 12094.56 | 21547.82 | 8266.96 | 880.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223711.04
F46308 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 6345.64 | 2459.69 | 4579.38 | 6741.81 | 6741.81 | 6741.81 | 6741.81 | 9397.95 | 20950.24 | 0 | 0 | 0 | 0 | 0 | 10162.63 | 80509.04 | 94342.95 | 67740.99 | 22205.31 | 0 | 0 | 0 | 0 | 0 | 0 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353443.96
F46310 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12959.1 | 0 | 0 | 3782.73 | 5455.87 | 65834.12 | 12803.1 | 67798.23 | 46265.74 | 35499.5 | 11639.18 | 29388.93 | 8729.39 | 0 | 3782.73 | 1745.88 | 581.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306266.46
F46310 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89230.69 | 232587.54 | 170365.48 | 84890.42 | 37038.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614112.26
F46312 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 15596.98 | 0 | 0 | 0 | 0 | 0 | 0 | 10106.19 | 0 | 0 | 0 | 0 | 24012.66 | 96050.65 | 0 | 0 | 0 | 0 | 68261.99 | 108285.1 | 28238.89 | 25417.4 | 9887.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385857.07
F46315 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24773.06 | 86824.82 | 162120.63 | 129737 | 66568.07 | 60098.49 | 32514.64 | 48116.91 | 13339.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624092.96
F46316 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112.65 | 0 | 0 | 0 | 1228.68 | 4306.29 | 8040.76 | 6434.62 | 3301.6 | 2980.73 | 1612.64 | 2386.47 | 661.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33066.04
F46317 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 3860.97 | 4029.32 | -2014.8 | 0 | 0 | 0 | 12126.71 | 42501.79 | 79360 | 91788.12 | 47096.5 | 42519.31 | 23003.91 | 34042.41 | 9437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387751.74
F46318 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80472.02 | 23961.98 | 18783.38 | 175.55 | 3686.46 | 3510.91 | 351.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130941.39
F46322 | Internal walls and finishes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27293.86 | 27293.86 | 27293.86 | 13133.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95015.04
F46322 | Internal walls and finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.33 | 41610.5 | 10045.23 | 96678.47 | 91882.25 | 46186.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287967.68
F46322 | Internal walls and finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17427.79 | 44687.5 | 114545.3 | 126819.39 | 60085.54 | 72777.09 | 91816.23 | 119729.74 | 199812.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847700.96
F46324 | Headhouse structure | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46324 | Headhouse structure | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153362.6 | 100641.98 | 160034.29 | 160034.29 | 114633.46 | 101145.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789851.76
F46332 | Internal walls and finishes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25989.63 | 25989.63 | 25989.63 | 14176.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92145.6
F46332 | Internal walls and finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81709.2 | 8763.73 | 154914.01 | 100200.71 | 100200.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445788.36
F46332 | Internal walls and finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13245.65 | 70954.74 | 110036.39 | 135658.33 | 95483.37 | 65689.49 | 118416.83 | 170469.42 | 87392.31 | 41138.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908485.44
F46334 | Headhouse structure | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46334 | Headhouse structure | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153362.6 | 100911.54 | 100776.76 | 190563.86 | 145028.26 | 144352.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834995.61
F46354 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 108029.59 | 25152.13 | 0 | 0 | 0 | 0 | 0 | 0 | 45558.28 | 0 | 0 | 0 | 0 | 0 | 0 | 85717.29 | 70132.33 | 0 | 0 | 0 | 58443.61 | 136368.42 | 140264.66 | 7792.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677458.79
F46356 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2076.27 | 0 | 0 | 615.3 | 1053.8 | 1011.36 | 989.3 | 1287.18 | 7972.57 | 0 | 0 | 0 | 1011.14 | 8748.63 | 3701.34 | 18254.35 | 30872.56 | 5720.26 | 0 | 14637.13 | 32721.55 | 39116.46 | 29190.13 | 18001.98 | 6729.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223711.02
F46358 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5870.22 | 3648.24 | 2863.46 | 7287.82 | 7287.82 | 7287.82 | 7287.82 | 10159.08 | 19007.86 | 0 | 0 | 0 | 1862.32 | 774.68 | 13789.26 | 15958.36 | 8574.13 | 13584.75 | 774.68 | 50973.78 | 23550.2 | 47549.71 | 60750.22 | 28910.97 | 2850.81 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347764.91
F46360 | Tunnel Vent | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57091.64 | 136842.9 | 95418.27 | 5142.67 | 256.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294752.17
F46360 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5647.69 | 8145.7 | 98291.49 | 35171.87 | 140473.45 | 92268.46 | 53001.38 | 17377.5 | 44110.12 | 66341.1 | 24976.96 | 9215.83 | 2606.63 | 868.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598497.06
F46362 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 15596.98 | 0 | 0 | 0 | 0 | 0 | 0 | 10249.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42604.97 | 85209.94 | 76696.19 | 80953.07 | 76696.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388006.72
F46365 | M&E Labour (KG) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8241.74 | 28915.36 | 10060.47 | 49174.81 | 136179.91 | 13602.34 | 42635.44 | 7341.38 | 61293.64 | 109566.7 | 114317.83 | 122614.98 | 83110.01 | 31858.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818913.45
F46366 | M&E Plant (KG) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112.65 | 0 | 0 | 415.98 | 1459.43 | 507.78 | 2481.97 | 6873.32 | 686.54 | 2151.91 | 370.54 | 3093.63 | 5530.09 | 5769.89 | 6188.67 | 4194.76 | 1607.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43445.15
F46367 | M&E Material (KG) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2153.96 | 10051.81 | -4335.85 | 0 | 0 | 3731.29 | 13090.88 | 4554.68 | 22262.96 | 79122.37 | 7903.14 | 24771.77 | 4265.44 | 35612.43 | 63659.74 | 66420.2 | 71240.96 | 48288.04 | 18510.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471304.24
F46368 | M&E Subcontractor (KG) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46368 | M&E Subcontractor (KG) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 54974.03 | 0 | 0 | 6116.85 | 10094.33 | 0 | 20699.63 | 12478.85 | 15849.79 | 0 | 0 | 0 | 23129.76 | 138368.6 | 0 | 15419.84 | 0 | 5806.42 | 18908.01 | 32757.59 | 3317.95 | 14516.05 | 9124.37 | 4147.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385709.51
F56420 | K.Shafts External Works Kennington Park | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7635.6 | 30542.4 | 30542.4 | 7635.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76356
F56420 | K.Shafts External Works Kennington Park | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64876.03 | 127126.87 | 125758.12 | 61911.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379672.8
F56420 | K.Shafts External Works Kennington Park | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032.6 | 4130.4 | 4130.4 | 1032.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10326
F56420 | K.Shafts External Works Kennington Park | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56440 | K.Shafts External Works Kennington Green | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7635.6 | 30542.4 | 30542.4 | 7635.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76356
F56440 | K.Shafts External Works Kennington Green | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64876.03 | 127126.87 | 125758.12 | 61911.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379672.8
F56440 | K.Shafts External Works Kennington Green | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032.6 | 4130.4 | 4130.4 | 1032.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10326
F56440 | K.Shafts External Works Kennington Green | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F66502 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46697.4
F66552 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42965.64
G08700 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 27302.67 | 1214.85 | 8914.07 | 6108.24 | 5981.13 | 5514.89 | 5357.25 | 5468.1 | 78252.4 | 11419.42 | 11069.67 | 8910.2 | 5907.66 | 5490.04 | 3931.4 | 135.25 | 62.13 | 62.13 | 62.13 | 4.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191168.07
G17000 | R.Systems Prelims General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 227350.2 | 38481.31 | 59681.31 | 59681.31 | 46941.18 | 37783.85 | 37783.85 | 37783.85 | 73107.38 | 62958.84 | 62958.84 | 29399.08 | 12975.79 | 12975.79 | 6024.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805887.05
G17000 | R.Systems Prelims General management & Supervision | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17000 | R.Systems Prelims General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 38.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.61
G17000 | R.Systems Prelims General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 1114860.91 | 87348.23 | 119522.59 | 95022.59 | 79653.89 | 131096.01 | 131096.01 | 131096.01 | -31604.89 | 69602.43 | 69602.43 | 60413.63 | 50519.67 | 42113.63 | 23433.17 | 1399.43 | 1399.43 | 1399.43 | 1149.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2179124.13
G17031 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190.4 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 933.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13356.58
G17031 | PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 13048.78 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | -4369.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41120.3
G17040 | Plant and Equipment | MAT | Materials | BUDGET | Approved Early Budget | 4312.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4312.6
G17040 | Plant and Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 362693.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363188.92
G37210 | Trackbed construction | MAT | Materials | BUDGET | Approved Early Budget | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850
G37210 | Trackbed construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -850
G37211 | Cleaning invert and crack repairs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11910.75 | 0 | 15124.93 | 27224.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54260.56
G37211 | Cleaning invert and crack repairs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 0 | 1783.27 | 3209.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12517.16
G37212 | Crainage blocks from BCO and lay down in the tunnels | LAB | Labour | BUDGET | Approved Early Budget | 55530.8 | 20220.9 | 48524.15 | 15408.43 | 9749.2 | 10995.86 | 10995.86 | 5783.14 | -112583.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64625.16
G37212 | Crainage blocks from BCO and lay down in the tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 37754.2 | 7654.52 | 16609.09 | 9377.72 | 9688.89 | 14903.26 | 14903.26 | 8434.11 | 29197.56 | 4087.24 | 302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152912.61
G37214 | Flash Welding and Distribution running rails | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 8134.05 | 32536.2 | 8134.05 | 0 | 0 | 0 | -34558.09 | 0 | 0 | 6833.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21079.41
G37214 | Flash Welding and Distribution running rails | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861.5
G37214 | Flash Welding and Distribution running rails | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37214 | Flash Welding and Distribution running rails | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 38440.81 | 153763.25 | 45137.52 | 0 | 0 | 0 | -25014.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242326.8
G37215 | Second Stage Trackbed Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46310.02 | 29063.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75373.62
G37215 | Second Stage Trackbed Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 10415.5 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | -75223.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4552e-11
G37215 | Second Stage Trackbed Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | -2855.18 | 1326.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7871.33
G37216 | Track assembly and 2nd stage concrete NB | LAB | Labour | BUDGET | Approved Early Budget | 296797.29 | 144557.73 | 115058.47 | 291694.51 | 200480.82 | 7918.58 | 7918.58 | 128692.27 | -60708.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132409.83
G37216 | Track assembly and 2nd stage concrete NB | MAT | Materials | BUDGET | Approved Early Budget | 1400.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364.78
G37216 | Track assembly and 2nd stage concrete NB | MISC | Miscellaneous | BUDGET | Approved Early Budget | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -204.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.8
G37216 | Track assembly and 2nd stage concrete NB | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4051.41 | 25510.19 | 20304.44 | 51475.5 | 35378.97 | 1397.4 | 1397.4 | 22710.4 | -84042.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78183.54
G37216 | Track assembly and 2nd stage concrete NB | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2399.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949.96
G37217 | Track assembly and 2nd stage concrete SB | LAB | Labour | BUDGET | Approved Early Budget | 232102.23 | 0 | 205771.94 | 8142.27 | 86481.96 | 282331.18 | 282331.18 | 106066.88 | 231073.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1434301.51
G37217 | Track assembly and 2nd stage concrete SB | MAT | Materials | BUDGET | Approved Early Budget | 952.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3239.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4192.54
G37217 | Track assembly and 2nd stage concrete SB | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 36312.69 | 1436.87 | 15261.52 | 49823.15 | 49823.15 | 18717.68 | -72383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98991.37
G37217 | Track assembly and 2nd stage concrete SB | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2399.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949.96
G37218 | Thermit Welding NB&SB (only FLO labour and plant) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 550.2 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | -11502.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35264.48
G37218 | Thermit Welding NB&SB (only FLO labour and plant) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 209.63 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | -14565.32 | 665.75 | 1509.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5428.61
G37219 | Materials, Special plant and other Equipment for trackbed construction | LAB | Labour | BUDGET | Approved Early Budget | 0 | 2856.74 | 3664.28 | 5102.48 | 4547.55 | 4168.8 | 4168.8 | 3536.72 | -28045.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | MAT | Materials | BUDGET | Approved Early Budget | 209950.12 | 44500.86 | 65856.12 | 102902.79 | 92898.44 | 84853.94 | 84853.94 | 69948.17 | 112141.51 | 325.58 | 23.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868254.73
G37219 | Materials, Special plant and other Equipment for trackbed construction | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | -10479.42 | 1005.75 | 1005.75 | 1005.75 | 1005.75 | 215.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6590.17
G37219 | Materials, Special plant and other Equipment for trackbed construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 46822.41 | 18722.99 | 18633.58 | 18633.58 | 13309.64 | 12422.31 | 12422.31 | 12422.31 | -70536.48 | 5986.15 | 3678.46 | 2909.23 | 2909.23 | 1573.33 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 993.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120246.15
G37219 | Materials, Special plant and other Equipment for trackbed construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67891.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67891.2
G37220 | Running rail and baseplates | MAT | Materials | BUDGET | Approved Early Budget | 347.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347.17
G37221 | Buffer Stops | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6514.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6514.4
G37221 | Buffer Stops | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747.62 | -747.62 | 0 | 0 | 21745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21745
G37221 | Buffer Stops | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35288.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35288.14
G37222 | Materials, Special plant and other Equipment for running rails and base plates | LAB | Labour | BUDGET | Approved Early Budget | 103280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4531.76 | 1982.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109794.4
G37222 | Materials, Special plant and other Equipment for running rails and base plates | MAT | Materials | BUDGET | Approved Early Budget | 513661.99 | 187415.64 | 252143.14 | 455570.88 | 30411.92 | 40200.78 | 99575.78 | 80825.78 | 15803.54 | 3417.25 | 53835.76 | 12668.63 | 2896.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748427.62
G37222 | Materials, Special plant and other Equipment for running rails and base plates | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29102.11 | 29102.11 | 12472.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150676.55
G37222 | Materials, Special plant and other Equipment for running rails and base plates | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 216351 | 12055.56 | 12055.56 | 12055.56 | 12055.56 | 12055.56 | 35443 | 12055.56 | -65124.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259003.06
G37222 | Materials, Special plant and other Equipment for running rails and base plates | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 52880 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | -28627.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100945
G37231 | Materials 3rd and 4th Rail | MAT | Materials | BUDGET | Approved Early Budget | 84942.59 | 0 | 0 | 0 | 0 | 0 | 195542.04 | 1244336.33 | -97588.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427232.24
G37231 | Materials 3rd and 4th Rail | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1029.05 | 0 | 0 | 0 | 0 | 0 | 20430.03 | 0 | -13700.14 | 6729.89 | 3124.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17613.42
G37232 | Installation 3rd and 4th Rail | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 10369.45 | 15554.17 | 32383.41 | 100748.4 | -87032.82 | 478900.11 | 105639.83 | 36164.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692727.24
G37232 | Installation 3rd and 4th Rail | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18553.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18553.25
G37232 | Installation 3rd and 4th Rail | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 2900 | 16046.81 | 193485.26 | 56691.73 | 13736.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284310.64
G37232 | Installation 3rd and 4th Rail | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5610.95 | 8416.42 | 49177 | 54515.34 | -85634.96 | 48913.4 | 14232.68 | 3419.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98650.02
G37232 | Installation 3rd and 4th Rail | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 22014.71 | 374250.09 | -372954.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23310.6
G37240 | Maintenance walkway, handrails etc. | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37240 | Maintenance walkway, handrails etc. | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37240 | Maintenance walkway, handrails etc. | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4087.24 | 302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390
G37241 | Tunnel temporary services and general maintenance | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3490.14 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 3034.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.96
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | STAFF | Staff | BUDGET | Approved Early Budget | 491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.03
G37251 | Materials Crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5601.71 | 6110.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11712.66
G37251 | Materials Crossover box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 1027755.82 | 0 | 0 | 0 | 0 | 0 | -6746.2 | 123181.89 | 51208.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1195400.15
G37251 | Materials Crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3799.3 | 17730.09 | 17785.57 | 11113.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50428
G37251 | Materials Crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095.65 | 5113.04 | 2837.19 | 704.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9750.48
G37252 | Installation Crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88474.96 | 173904.74 | 144598.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406977.8
G37252 | Installation Crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22339.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22339.33
G37252 | Installation Crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 23049 | 0 | 0 | 0 | 0 | 0 | 16967.43 | 41172.4 | 19413.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100601.89
G37252 | Installation Crossover box | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136.8
G37252 | Installation Crossover box | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 15827.54 | 8181.65 | 1332.63 | 1332.63 | 2040.63 | 1332.63 | -30047.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.276e-12
G37261 | FLO Pre&Post works SPJ | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179573.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179573.99
G37261 | FLO Pre&Post works SPJ | MAT | Materials | BUDGET | Approved Early Budget | 3669.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669.75
G37261 | FLO Pre&Post works SPJ | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205
G37261 | FLO Pre&Post works SPJ | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466
G37261 | FLO Pre&Post works SPJ | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 7062.03 | 7062.03 | 7062.03 | 7062.03 | 7062.03 | 62764 | 7062.03 | -105136.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 10075 | -10850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15686.31 | 4278.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19964.4
G37262 | Materials SPJ | MAT | Materials | BUDGET | Approved Early Budget | 507824.02 | 0 | 0 | 0 | 0 | 0 | 6577.8 | 18571.43 | -20910.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23192.05 | 6325.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541580.16
G37262 | Materials SPJ | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86052.21 | 23468.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109521
G37262 | Materials SPJ | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3365.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3365.77
G37262 | Materials SPJ | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 38000 | 0 | 5149.23 | 28320.77 | -71470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | LAB | Labour | BUDGET | Approved Early Budget | 353413.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354491.78
G37263 | Installation SPJ (Subcontract) | MAT | Materials | BUDGET | Approved Early Budget | 43608.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6659.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36948.86
G37263 | Installation SPJ (Subcontract) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22233.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.64
G37263 | Installation SPJ (Subcontract) | STAFF | Staff | BUDGET | Approved Early Budget | 68383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2335258.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137914.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2473172.95
G37271 | FSC Northbound | LAB | Labour | BUDGET | Approved Early Budget | 693212.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11229.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681983.13
G37271 | FSC Northbound | MAT | Materials | BUDGET | Approved Early Budget | 797291.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798163.29
G37271 | FSC Northbound | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3267.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -102.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3165.6
G37271 | FSC Northbound | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 201120.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7115.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208236.06
G37272 | FSC Southbound | LAB | Labour | BUDGET | Approved Early Budget | 493391.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496516.78
G37272 | FSC Southbound | MAT | Materials | BUDGET | Approved Early Budget | 833725.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14695.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848421.54
G37272 | FSC Southbound | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151
G37272 | FSC Southbound | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 206597.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186596.61
G37273 | SCL tunnels NB | LAB | Labour | BUDGET | Approved Early Budget | 8414.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8414.04
G37281 | Cross passages 1, 2 & 3 fit out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58962.26 | 66037.74 | 66037.74 | 58962.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
G37282 | Tunnel signage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21226.42 | 23773.58 | 23773.58 | 21226.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
G47302 | Traction Sub | MAT | Materials | BUDGET | Approved Early Budget | 3168.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3168.37
G47302 | Traction Sub | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 829.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829.84
G47302 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 371548.19 | 162823.61 | 0 | 0 | 40983.84 | 368854.56 | 255105 | 147795 | 93455.65 | 927.86 | 0 | 0 | 513833.14 | 713833.14 | 715431.14 | 515431.14 | 359874.35 | 0 | 0 | 0 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4299896.61
G47307 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 4499.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4499.78
[5 empty] | Subtotal | 407233236.92 | 9541393.12 | 10214880.39 | 9341616.61 | 8090487.67 | 8353283.6 | 10886579.26 | 13966844.23 | 8734379.28 | 11553372.3 | 12230487.88 | 14128167.51 | 16172454.46 | 15682489.25 | 14622688.3 | 16372430.68 | 14411609.45 | 11024311.77 | 7251976.67 | 7730345.8 | 9443805.39 | 8180722.85 | 6872745.65 | 6263488.95 | 5399148.42 | 4668484.67 | 4402504.71 | 4385771.24 | 3349311.82 | 1669182.45 | 1630205.32 | 1617738.23 | 1316966.83 | 1017364.87 | 930845.77 | 1477326.27 | 1201734.6 | 691380.18 | 130687.24 | 82910.15 | 95257.77 | 12605.54 | 6105.54 | 18105.54 | 0 | 0 | 0 | 0 | 692407435.15 | 0
|  |  |  | Summary ALL Sites | STAFF | 61996906.23 | 1619296.13 | 1739867.28 | 1585869.82 | 1533063.08 | 1622389.64 | 1548821.22 | 1553370.03 | 1462973.69 | 1716649.69 | 1673863.73 | 1660869.93 | 1614661.97 | 1515305.92 | 1484325.46 | 1461357.92 | 1426424.15 | 1381804.59 | 1365139.69 | 1272404.07 | 1274154.07 | 1310037.26 | 1271051.72 | 1232005.81 | 1218054.29 | 1121069.01 | 1034282.52 | 900176.96 | 834871.42 | 731400.42 | 692305.42 | 637541.21 | 580567.4 | 459079.58 | 434789.58 | 398989.58 | 394729.03 | 376209.03 | 87376.82 | 52244.82 | 45185 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 70889568.12 | 2343592.99 | 2220711.84 | 2102519.28 | 1705028.72 | 1470506.31 | 1763420.63 | 1891835.75 | 1656084.53 | 2623259.26 | 2247400.91 | 2313728.22 | 2275336.86 | 2435825.82 | 1886721.06 | 1809026.62 | 1246206.09 | 1021924.07 | 496200.97 | 959277.32 | 949580.66 | 848161.25 | 776089.12 | 683323.1 | 631958.73 | 573451.33 | 636226.81 | 690627.84 | 480957.38 | 358586.28 | 264527.24 | 246126.93 | 242237.73 | 236472.43 | 229512.43 | 229512.43 | 266664 | 79240.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 40109596.09 | 755415.47 | 871200.95 | 780682.75 | 701011.22 | 632783.61 | 867084.28 | 731161.57 | 809648.55 | 755284.16 | 455794.8 | 383426.28 | 299744.53 | -906544.73 | -1123110.01 | 285438.22 | 319835.13 | 168643.9 | 80747.15 | 255761.71 | 269164.32 | 251006.88 | 207034.09 | 189741.11 | 169425.34 | 180791.76 | 190011.8 | 240732.54 | 76745.88 | 66164.78 | 57812.15 | 53292.29 | 43887.88 | 37555.27 | 40025.38 | 40025.38 | 56292.36 | 21226.07 | 4000 | 0 | 0 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0
[5 empty] | MAT | 64910805.34 | 1780494.46 | 3201181.68 | 2291725.65 | 1475114.18 | 1343491.92 | 1811438.08 | 3137695.3 | -908296.5 | 1577457.01 | 1581315.67 | 1579491.77 | 1713162.73 | 1742549.71 | 1375723.96 | 1761277.53 | 1005033.37 | 680494.9 | 286684.65 | 524646.58 | 430424.54 | 289315.44 | 272558.68 | 208837.1 | 193968.05 | 201341.51 | 228963.02 | 182750.41 | 29533.77 | 21290.5 | 25694.74 | 42973.23 | 15340.48 | 21340.48 | 14356.69 | 15256.69 | 14512.78 | 30540.42 | 0 | 0 | 0 | 193.02 | 193.02 | 12193.02 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 146702707.91 | 2756376.29 | 1822637.54 | 2260285.45 | 2349615.13 | 2967623.43 | 4565265.74 | 6334455.18 | 5847091.53 | 4391722.74 | 5895491.7 | 7848123.44 | 9990041.86 | 10575850.64 | 10724876.68 | 10816529.07 | 10217311.22 | 7437030.66 | 4862355.84 | 4331454.68 | 6006725.71 | 5031741.64 | 4061473.53 | 3799978.77 | 2952887.05 | 2435370.29 | 2187547.19 | 2250488.66 | 1808750.24 | 376266.2 | 486515.69 | 551966.54 | 354482.66 | 194173.71 | 147210.52 | 726292.59 | 282212.92 | 140288.78 | 16122.34 | 10199.54 | 7500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 18008329.89 | 136398.22 | 144280.04 | 173002.77 | 186957.06 | 165210.42 | 175365.83 | 162514.68 | -90768.55 | 341734.15 | 228109.12 | 184651.82 | 123042.91 | 162111.3 | 125821.51 | 95805.06 | 69735.29 | 210866.75 | 66428.67 | 273931.9 | 402755.41 | 344939.42 | 182152.44 | 54193.2 | 136447.7 | 72114.28 | 49395.49 | 49503.86 | 44233.84 | 42483.84 | 34233.84 | 31673.57 | 30836.21 | 25921.21 | 25077.25 | 20992.35 | 150468.35 | 12907.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 4615323.34 | 149819.56 | 215001.06 | 147530.89 | 139698.28 | 151278.27 | 155183.48 | 155811.72 | -42353.97 | 147265.29 | 148511.95 | 157876.05 | 156463.6 | 157390.59 | 148329.64 | 142996.26 | 127064.2 | 123546.9 | 94419.7 | 112869.54 | 111000.68 | 105520.96 | 102386.07 | 95409.86 | 96407.26 | 84346.49 | 76077.88 | 71490.97 | 74219.29 | 72990.43 | 69116.24 | 54164.46 | 49614.47 | 42822.19 | 39873.92 | 46257.25 | 36855.16 | 30968.47 | 23188.08 | 20465.79 | 42572.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 407233236.92 | 9541393.12 | 10214880.39 | 9341616.61 | 8090487.67 | 8353283.6 | 10886579.26 | 13966844.23 | 8734379.28 | 11553372.3 | 12230487.88 | 14128167.51 | 16172454.46 | 15682489.25 | 14622688.3 | 16372430.68 | 14411609.45 | 11024311.77 | 7251976.67 | 7730345.8 | 9443805.39 | 8180722.85 | 6872745.65 | 6263488.95 | 5399148.42 | 4668484.67 | 4402504.71 | 4385771.24 | 3349311.82 | 1669182.45 | 1630205.32 | 1617738.23 | 1316966.83 | 1017364.87 | 930845.77 | 1477326.27 | 1201734.6 | 691380.18 | 130687.24 | 82910.15 | 95257.77 | 12605.54 | 6105.54 | 18105.54 | 0 | 0 | 0 | 0 | 692407435.15
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Summary Total | STAFF | 106321485.19
[5 empty] | LAB | 113781431.2
[5 empty] | PLANT | 49446278.47
[5 empty] | MAT | 95123065.58
[5 empty] | SUBCON | 296531541.3
[5 empty] | MISC | 22653858.37
[5 empty] | WAO | 8549775.04
[5 empty] | Subtotal | 692407435.15
[5 empty] | CTD @ P11 | 463661477.57
[5 empty] | CTG | 228745957.58
[5 empty] | EF8 | 692407435.15

## A
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
A08100 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 1038208.71 | 39908 | 91795 | 39278 | 38928 | 38578 | 37843 | 37843 | -43499.54 | 49381.67 | 44865 | 45215 | 45915 | 42765 | 42415 | 42415 | 46581.67 | 42240 | 41190 | 38565 | 38915 | 36815 | 36465 | 36465 | 40631.67 | 34015 | 31915 | 29990 | 29640 | 27640 | 29006.67 | 24490 | 23150 | 22450 | 20700 | 27983.33 | 19475 | 19085 | 15033.33 | 17616.67 | 42366.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | MAT | Materials | BUDGET | Approved Early Budget | -18205.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 9762.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21647.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -891.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09999 | Overhead Temporary code (to be reconciled periodically) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 678492.04 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 1573.5 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 6150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1449972.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92180.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2287.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8564.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 20295634.95 | 387859.66 | 385757.66 | 378107.66 | 373707.66 | 373707.66 | 348253.66 | 348253.66 | 160889.07 | 360888.66 | 346838.66 | 346838.66 | 346838.66 | 331638.66 | 322588.66 | 322588.66 | 322588.66 | 335088.66 | 335088.66 | 304738.66 | 304738.66 | 304738.66 | 295688.66 | 295688.66 | 295688.66 | 295688.66 | 258238.66 | 254413.66 | 250013.66 | 245613.66 | 242903.66 | 247303.66 | 233243.66 | 233243.66 | 233243.66 | 225593.66 | 223393.66 | 221633.66 | 20200 | 20200 | 20200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 167998.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11002 | OH Prelims HHRR - Springboard | MISC | Miscellaneous | BUDGET | Approved Early Budget | 181175 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | -3810 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11004 | OH Prelims H&S - Park Health | MAT | Materials | BUDGET | Approved Early Budget | 1897.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11004 | OH Prelims H&S - Park Health | MISC | Miscellaneous | BUDGET | Approved Early Budget | 929873.93 | 27330 | 27330 | 27330 | 27330 | 27330 | 28705 | 27330 | -23121.68 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 28705 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 27330 | 26580 | 26580 | 26580 | 25330 | 24580 | 15580 | 13820 | 13740 | 13660 | 13280 | 12980 | 12680 | 12680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11004 | OH Prelims H&S - Park Health | STAFF | Staff | BUDGET | Approved Early Budget | -44519.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11006 | OH Prelims Engineering - Obsolete | MAT | Materials | BUDGET | Approved Early Budget | 372.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11006 | OH Prelims Engineering - Obsolete | MISC | Miscellaneous | BUDGET | Approved Early Budget | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11006 | OH Prelims Engineering - Obsolete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11010 | ME, Testing and Commissioning | LAB | Labour | BUDGET | Approved Early Budget | 8685.92 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | -17316.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11010 | ME, Testing and Commissioning | STAFF | Staff | BUDGET | Approved Early Budget | 3362961.01 | 229523.74 | 254517.74 | 257148.74 | 270322.74 | 270322.74 | 271322.74 | 291300.74 | 882998.87 | 552183 | 543133 | 551133 | 553764 | 451264 | 443614 | 443614 | 443614 | 429706 | 429706 | 378206 | 384356 | 335556 | 325006 | 325006 | 325006 | 266306 | 266306 | 243636 | 213186 | 142260 | 114100 | 100050 | 93900 | 77472 | 53182 | 47032 | 47032 | 42632 | 35132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11010 | ME, Testing and Commissioning | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45781 | 0 | 0 | 0 | 77109.5 | 77109.5 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11011 | Labour Redundancy Cost | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13048 | 15000 | 15000 | 15000 | 15000 | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11012 | LUL16 Management | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17700 | 17700 | 17700 | 17700 | 30000 | 61160 | 65560 | 65560 | 65560 | 65560 | 53260 | 53260 | 53260 | 57660 | 57660 | 57660 | 57660 | 57660 | 52010 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 44900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11030 | Site Facilities & Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1149.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11030 | Site Facilities & Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -8838.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3425.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11034 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 11364.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11034 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 319467.25 | 1800 | 1000 | 1000 | 1000 | 1800 | 1000 | 1000 | -7600 | 1900 | 1000 | 1000 | 1000 | 1900 | 1000 | 1000 | 1000 | 1000 | 1900 | 1000 | 500 | 500 | 1150 | 250 | 250 | 250 | 1150 | 250 | 250 | 250 | 1150 | 250 | 250 | 250 | 250 | 1150 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11034 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 361968.63 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 4375.91 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11034 | Temporary Accommodation | STAFF | Staff | BUDGET | Approved Early Budget | 2640.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11036 | IT Equipment & running costs | MAT | Materials | BUDGET | Approved Early Budget | 9821.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11036 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 130656.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11036 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2136.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11036 | IT Equipment & running costs | STAFF | Staff | BUDGET | Approved Early Budget | 62786.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11038 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 1477.35 | 0 | 0 | 5760 | 0 | 0 | 0 | 0 | -5760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11038 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11620.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11038 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2478.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11038 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11040 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 28147.2 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | -6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
A11040 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 76869.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11040 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5487.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11040 | H&S Quality Environmental | STAFF | Staff | BUDGET | Approved Early Budget | 67025.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11199.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11042 | Liaison and co ordination with others | MAT | Materials | BUDGET | Approved Early Budget | 12396.55 | 2000 | 0 | 0 | 0 | 4000 | 0 | 0 | -723 | 2000 | 5940 | 2000 | 2000 | 2000 | 4000 | 2000 | 2000 | 2000 | 26000 | 2000 | 2000 | 4000 | 2000 | 2000 | 5940 | 2000 | 2000 | 800 | 800 | 800 | 800 | 27400 | 800 | 800 | 800 | 800 | 800 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11042 | Liaison and co ordination with others | MISC | Miscellaneous | BUDGET | Approved Early Budget | 139062.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71926.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11042 | Liaison and co ordination with others | STAFF | Staff | BUDGET | Approved Early Budget | 93536.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11042 | Liaison and co ordination with others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 18500 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | -30500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11044 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11044 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2269.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11044 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11044 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | LAB | Labour | BUDGET | Approved Early Budget | 398299.19 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 39984.56 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 3600 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | MAT | Materials | BUDGET | Approved Early Budget | 2594.61 | 600 | 600 | 600 | 600 | 600 | 600 | 540 | 2386.52 | 122020 | 1960 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1900 | 1840 | 1840 | 1840 | 1720 | 1720 | 1720 | 1660 | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 830 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 281564.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 293572.83 | 2613 | 2866 | 2866 | 2866 | 2866 | 2866 | 2866 | 11217.76 | 2866 | 2866 | 2866 | 2866 | 2186 | 2186 | 2186 | 2986 | 2986 | 2986 | 2673 | 2673 | 2673 | 2673 | 2673 | 2673 | 2673 | 1953 | 1893 | 1893 | 1833 | 1833 | 1833 | 1833 | 1833 | 4780 | 4780 | 4780 | 4780 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | STAFF | Staff | BUDGET | Approved Early Budget | 4114.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4114.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11046 | Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 8100 | 1600 | 1600 | 1600 | 1600 | 13855 | 13855 | -29955 | 12255 | 12255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11048 | Security & Access Control (Servest) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 32490.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11048 | Security & Access Control (Servest) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 134381.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11048 | Security & Access Control (Servest) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2319371.5 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 77515.52 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11070 | Small Plant & PPE | LAB | Labour | BUDGET | Approved Early Budget | 6323.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11070 | Small Plant & PPE | MAT | Materials | BUDGET | Approved Early Budget | 4.8 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | -4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11070 | Small Plant & PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1676.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11070 | Small Plant & PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 125319.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11072 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11072 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 33025230.17 | 802912.4 | 858144.4 | 800368.4 | 803032.4 | 807482.4 | 791123.4 | 809666.4 | 1232050.53 | 1243990.49 | 1095133.66 | 1131229.82 | 1102859.66 | 1006609.82 | 991839.66 | 1067544.32 | 1072675.83 | 1002276.82 | 995606.66 | 884138.82 | 891858.66 | 851578.82 | 826058.66 | 817108.82 | 826995.33 | 755208.82 | 712808.66 | 673419.46 | 632749.3 | 552833.46 | 555009.97 | 525003.46 | 476310.3 | 454987.46 | 423664.3 | 415967.79 | 430089.3 | 479759.46 | 74365.33 | 37816.67 | 62566.67 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
|  |  |  | A Breakdown | STAFF | 23844179.77 | 617383.4 | 640275.4 | 635256.4 | 644030.4 | 644030.4 | 619576.4 | 639554.4 | 1073107.56 | 930771.66 | 907671.66 | 915671.66 | 930602.66 | 844062.66 | 831762.66 | 831762.66 | 831762.66 | 830354.66 | 818054.66 | 736204.66 | 742354.66 | 697954.66 | 678354.66 | 678354.66 | 678354.66 | 619654.66 | 576554.66 | 542949.66 | 508099.66 | 432773.66 | 401903.66 | 392253.66 | 372043.66 | 355615.66 | 331325.66 | 317525.66 | 315325.66 | 309165.66 | 55332 | 20200 | 20200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 1103165.67 | 28500 | 28500 | 28500 | 28500 | 28500 | 28500 | 28500 | 37289.61 | 38100 | 38100 | 38100 | 38100 | 33100 | 28100 | 23100 | 23100 | 23100 | 23100 | 23100 | 23100 | 23100 | 23100 | 16950 | 16950 | 16950 | 13350 | 15350 | 15350 | 15350 | 15350 | 15350 | 15350 | 13350 | 9750 | 9750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 583039.58 | 2613 | 2866 | 2866 | 2866 | 2866 | 2866 | 2866 | 3802.35 | 3466 | 3466 | 3466 | 3466 | 2786 | 2786 | 2786 | 3586 | 3586 | 3586 | 3273 | 3273 | 3273 | 3273 | 3273 | 3273 | 3273 | 4053 | 3993 | 3993 | 3933 | 9933 | 3933 | 5433 | 3933 | 6880 | 6880 | 6880 | 12880 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 359140.27 | 5000 | 8200 | 7960 | 2200 | 7000 | 2200 | 2140 | -20986.48 | 131920 | 8900 | 4900 | 4900 | 5800 | 6900 | 10900 | 10660 | 4900 | 29800 | 4900 | 4340 | 12340 | 4990 | 3970 | 7910 | 3970 | 4810 | 7910 | 1910 | 1910 | 8810 | 28510 | 1910 | 7910 | 1880 | 2780 | 2130 | 28130 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 2319371.5 | 76600 | 53600 | 53600 | 53600 | 53600 | 65855 | 65855 | 17060.52 | 57443.16 | 59223 | 90969.16 | 46968 | 45188.16 | 46968 | 122297.66 | 124077.5 | 65188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 46968 | 45188.16 | 49968 | 41068.8 | 42848.64 | 41068.8 | 68848.64 | 41068.8 | 39848.64 | 38068.8 | 39848.64 | 38068.8 | 39848.64 | 64068.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 3610126.42 | 32908 | 32908 | 32908 | 32908 | 32908 | 34283 | 32908 | 165276.51 | 32908 | 32908 | 32908 | 32908 | 32908 | 32908 | 34283 | 32908 | 32908 | 32908 | 32908 | 32908 | 32908 | 32908 | 32908 | 32908 | 32158 | 32158 | 32158 | 30908 | 30158 | 21158 | 19398 | 18575 | 13660 | 13280 | 12980 | 12680 | 12680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 1206206.96 | 39908 | 91795 | 39278 | 38928 | 38578 | 37843 | 37843 | -43499.54 | 49381.67 | 44865 | 45215 | 45915 | 42765 | 42415 | 42415 | 46581.67 | 42240 | 41190 | 38565 | 38915 | 36815 | 36465 | 36465 | 40631.67 | 34015 | 31915 | 29990 | 29640 | 27640 | 29006.67 | 24490 | 23150 | 22450 | 20700 | 27983.33 | 19475 | 19085 | 15033.33 | 17616.67 | 42366.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 33025230.17 | 802912.4 | 858144.4 | 800368.4 | 803032.4 | 807482.4 | 791123.4 | 809666.4 | 1232050.53 | 1243990.49 | 1095133.66 | 1131229.82 | 1102859.66 | 1006609.82 | 991839.66 | 1067544.32 | 1072675.83 | 1002276.82 | 995606.66 | 884138.82 | 891858.66 | 851578.82 | 826058.66 | 817108.82 | 826995.33 | 755208.82 | 712808.66 | 673419.46 | 632749.3 | 552833.46 | 555009.97 | 525003.46 | 476310.3 | 454987.46 | 423664.3 | 415967.79 | 430089.3 | 479759.46 | 74365.33 | 37816.67 | 62566.67 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 63012076.76
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## B
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
B08200 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 759625.69 | 16288.4 | 16726.5 | 17737.5 | 17165 | 17165 | 14627.55 | 14290.55 | -19534.49 | 12092.75 | 12061.35 | 11747.35 | 10032.85 | 9852.85 | 9852.85 | 9821.45 | 9507.45 | 9476.05 | 9476.05 | 9162.05 | 8848.05 | 7460.05 | 6786.05 | 6763.05 | 6583.05 | 6144.55 | 5752.05 | 5438.05 | 4652.2 | 4356.5 | 3537 | 1997.5 | 1619.1 | 1619.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 206.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 267002.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21257.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 9471592.33 | 201805 | 207175 | 222125 | 219415 | 219415 | 190835 | 184685 | -95274.26 | 190395 | 190395 | 190395 | 179395 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 173370 | 161070 | 149560 | 146850 | 142450 | 130150 | 130150 | 130150 | 105370 | 82125 | 73900 | 44705 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 19585 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 541.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12050 | CP Health & Safety Services Ltd (Chris Purslow) | STAFF | Staff | BUDGET | Approved Early Budget | 56100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12060 | OTB Engineering Limited (Jon Austin) | STAFF | Staff | BUDGET | Approved Early Budget | 98469.75 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | -9393 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12060 | OTB Engineering Limited (Jon Austin) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12070 | Matchtech (Paul Kick) | STAFF | Staff | BUDGET | Approved Early Budget | 304816.81 | 37000 | 37000 | 37000 | 37000 | 37000 | 37000 | 37000 | 13850.94 | 45900 | 45900 | 45900 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12080 | Aspects (John Bailey) | STAFF | Staff | BUDGET | Approved Early Budget | 266625 | 10800 | 10800 | 10800 | 10800 | 10800 | 8100 | 8100 | 15862.5 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 10800 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 8100 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12090 | Protechning | STAFF | Staff | BUDGET | Approved Early Budget | 447441.09 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 3512.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | LAB | Labour | BUDGET | Approved Early Budget | 5934.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3552.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | MAT | Materials | BUDGET | Approved Early Budget | 274560.19 | 3000 | 3000 | 3000 | 3000 | 3000 | -105713 | 3000 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 62791.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 274177.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15607.47 | 40000 | 3000 | 3000 | -38000 | 3000 | -149000 | 3000 | 130000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | STAFF | Staff | BUDGET | Approved Early Budget | 49620.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2728.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17763.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9512.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22136 | Equipment supply and installation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 192061.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22600 | Geotechnical Observations Ltd (Automated Monitoring) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2143051.81 | 22510 | 22510 | 22210 | 15560 | 0 | 0 | 0 | 23484.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22610 | Amey (SW Storm Sewer Temp works) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1271618.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22611 | Geotechnical Consulting Group | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22620 | Thames Water Utilities Limited | MISC | Miscellaneous | BUDGET | Approved Early Budget | 284643.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22630 | EDF Cable Tunnel (Monitoring and protection) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 142556.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22660 | London Ring Main (Monitoring and protection) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22670 | ESG (Boreholes) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 56021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22680 | DI Harris (Geotechnical Monitoring) | STAFF | Staff | BUDGET | Approved Early Budget | 295101.92 | 6812.31 | 6812.31 | 6812.31 | 6812.31 | 4732.31 | 4732.31 | 4732.31 | 27969.98 | 6000 | 3692 | 3692 | 3692 | 3692 | 3692 | 3692 | 3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22680 | DI Harris (Geotechnical Monitoring) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1722.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22710 | CPM Surveys (Dilapidation Surveys) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 388130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32810 | Mott MacDonald (Permanent Design to RIBA4) | STAFF | Staff | BUDGET | Approved Early Budget | 1166126.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32810 | Mott MacDonald (Permanent Design to RIBA4) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 39653685.57 | 240143.1 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 294610.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32811 | Mott MacDonald (Post RIBA4) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 773638.28 | 25000 | 25000 | 25000 | 25000 | 10000 | 10000 | 10000 | -27597.92 | 55000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32812 | Mott MacDonald (BPSDC Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 8148.69 | 20000 | 20000 | 10000 | 0 | 0 | 0 | 0 | 127684.55 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32813 | Mott MacDonald (Defect Correction) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | -46346.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46346.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32816 | Mott MacDonald Site Support | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4358081.78 | 293768.19 | 301613.66 | 298503.6 | 283416.29 | 277725.45 | 284405.53 | 268666.84 | 970118.53 | 446830.77 | 403925.37 | 391402.57 | 355604.37 | 312111.09 | 223144.49 | 170064.16 | 152565.1 | 150185.62 | 127005.6 | 103770.58 | 103860.64 | 102460.48 | 91328.32 | 89845.44 | 64875.84 | 41871.08 | 38680.65 | 2436.16 | 0 | 0 | 0 | 0 | 0 | 3505.28 | 11097.41 | 10427.81 | 8622.34 | 7952.74 | 8622.34 | 2699.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32817 | FLO support to Mott MacDonald | STAFF | Staff | BUDGET | Approved Early Budget | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853986.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32817 | FLO support to Mott MacDonald | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 242152.51 | 95280 | 73280 | 73280 | 73280 | 73280 | 73280 | 61280 | -818840.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32820 | OTB Engineering Limited (Tunnel Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 710667.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2417.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32825 | OTB Engineering Limited Site Support | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1154584.67 | 58412 | 20000 | 0 | 0 | 0 | 0 | 0 | -77714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32830 | Firstco (Comms Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1614688.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5927.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32840 | York (Electro Magnetic Consultant) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 26290.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 16701.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32860 | Explore (DFMA Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 30718.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32870 | Epofore (Rebar Detailing) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 241692.5 | 7000 | 7000 | 7000 | 7000 | 7000 | 6450 | 0 | 9017.5 | 2000 | 2000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32875 | Computer and Design Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 52658 | 4000 | 4000 | 4000 | 2000 | 2000 | 0 | 0 | -3284 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32880 | Gal Ziedler (CAT 3 checking of Tunnel Design) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 269215.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32890 | RUL (Geotechnical analysis and Report) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 42820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32900 | Clancy Docwra (Tunnel Intrusive Surveys) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 60972.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32911 | OTB (Various TW Designs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 99896 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | -4112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32912 | RMP (Various TW Designs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 75420 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | -7205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32913 | Tony Gee (Various TW Designs) | STAFF | Staff | BUDGET | Approved Early Budget | 1437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32914 | Steer Davies & Gleave Limited (TM Design) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32915 | Testing and Consultancy Services Ltd (Tunnel Vent Design) | STAFF | Staff | BUDGET | Approved Early Budget | 2810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32916 | Campbell Reith Hill LLP (BCDH Pile Design) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32920 | Building Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 53792.69 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 333.63 | 8000 | 10000 | 10000 | 10000 | 10000 | 10000 | 8000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0
B32921 | Small Works Orders | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 50625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1723 | 0 | 25000 | 25000 | 30000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 67847930 | 1054594 | 777692.47 | 755243.41 | 714098.6 | 670767.76 | 529367.39 | 597404.7 | 1378345.05 | 846668.52 | 783423.72 | 773586.92 | 645824.22 | 557125.94 | 316159.34 | 411397.61 | 487384.55 | 354281.67 | 338001.65 | 321253.82 | 321029.88 | 305941.72 | 282625.56 | 278409.68 | 248860.08 | 213116.82 | 201883.89 | 165325.4 | 120622.2 | 94381.5 | 85337 | 54602.5 | 34104.1 | 37609.38 | 44887.51 | 44217.91 | 42412.44 | 41742.84 | 42412.44 | 36489.64 | 32691.1 | 6500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | B | STAFF | 12205141.34 | 262192.31 | 267562.31 | 282512.31 | 275677.31 | 273597.31 | 242317.31 | 236167.31 | 807786.67 | 254745 | 252437 | 252437 | 203187 | 197162 | 197162 | 195512 | 192812 | 189120 | 189120 | 189120 | 189120 | 176820 | 165310 | 162600 | 158200 | 145900 | 138250 | 138250 | 113470 | 87525 | 79300 | 50105 | 24985 | 24985 | 24985 | 24985 | 24985 | 24985 | 24985 | 24985 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 272936.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24810.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 274267.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15607.47 | 40000 | 3000 | 3000 | -38000 | 3000 | -149000 | 3000 | 130000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 274560.19 | 3000 | 3000 | 3000 | 3000 | 3000 | -105713 | 3000 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 51592718.78 | 773113.29 | 490403.66 | 451993.6 | 418256.29 | 377005.45 | 378135.53 | 343946.84 | 537733.98 | 539830.77 | 515925.37 | 506402.57 | 470604.37 | 347111.09 | 258144.49 | 203064.16 | 155065.1 | 152685.62 | 139405.6 | 122971.77 | 123061.83 | 121661.67 | 110529.51 | 109046.63 | 84077.03 | 61072.27 | 57881.84 | 21637.35 | 2500 | 2500 | 2500 | 2500 | 7500 | 11005.28 | 18597.41 | 17927.81 | 16122.34 | 15452.74 | 16122.34 | 10199.54 | 7500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 2276077.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 952228.09 | 16288.4 | 16726.5 | 17737.5 | 17165 | 17165 | 14627.55 | 14290.55 | -19534.49 | 12092.75 | 12061.35 | 11747.35 | 10032.85 | 9852.85 | 9852.85 | 9821.45 | 9507.45 | 9476.05 | 9476.05 | 9162.05 | 8848.05 | 7460.05 | 6786.05 | 6763.05 | 6583.05 | 6144.55 | 5752.05 | 5438.05 | 4652.2 | 4356.5 | 3537 | 1997.5 | 1619.1 | 1619.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 1305.1 | 206.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 67847930 | 1054594 | 777692.47 | 755243.41 | 714098.6 | 670767.76 | 529367.39 | 597404.7 | 1378345.05 | 846668.52 | 783423.72 | 773586.92 | 645824.22 | 557125.94 | 316159.34 | 411397.61 | 487384.55 | 354281.67 | 338001.65 | 321253.82 | 321029.88 | 305941.72 | 282625.56 | 278409.68 | 248860.08 | 213116.82 | 201883.89 | 165325.4 | 120622.2 | 94381.5 | 85337 | 54602.5 | 34104.1 | 37609.38 | 44887.51 | 44217.91 | 42412.44 | 41742.84 | 42412.44 | 36489.64 | 32691.1 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 82895754.93
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## C
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
C08300 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 797208.65 | 26651 | 26651 | 27836.76 | 35500.61 | 45447.69 | 45479.1 | 40166.81 | -142860.24 | 20192.08 | 22071.43 | 23994.19 | 23662.96 | 22956.96 | 20300.34 | 20615.09 | 17372.68 | 20290.01 | 1024.45 | 21170.61 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20949.54 | 20728.48 | 20065.27 | 25065.27 | 26307.11 | 21885.75 | 15474.77 | 14148.36 | 9727 | 8842.73 | 8842.73 | 8842.73 | 8842.73 | 5747.77 | 442.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C08310 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 2842.82 | 1530.75 | 2842.82 | 3717.54 | 3936.22 | 11152.61 | 14214.11 | 8283.85 | 3954.21 | 6073.75 | 16326.4 | 10486.32 | 13882.43 | 10174.58 | 8241.19 | 3636.51 | 3884.11 | 1307.6 | 1702.2 | 1895.63 | 773.73 | 143.14 | 212.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | LAB | Labour | BUDGET | Approved Early Budget | -0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | MISC | Miscellaneous | BUDGET | Approved Early Budget | -60.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 172.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09999 | Battersea Temporary code (just to be used if the cost will be relocated before every period cost rep | STAFF | Staff | BUDGET | Approved Early Budget | 1439.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 1449984.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355226.74 | 65235 | 70725.87 | 71384.78 | 71384.78 | 68834.49 | 55780.55 | 53723.39 | 51690.54 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 44688.97 | 43941.03 | 37293.57 | 26527.37 | 15494.49 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 11101.42 | 3171.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13000 | General management & Supervision | MAT | Materials | BUDGET | Approved Early Budget | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2042.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23811.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5868.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 7233352.5 | 254552.63 | 262808.58 | 274341.07 | 302876.48 | 323410.92 | 303149 | 293504.81 | -493315.55 | 209932 | 209932 | 198127 | 196132 | 196132 | 196132 | 196132 | 193186 | 159927 | 155812 | 155812 | 155812 | 158887 | 158887 | 158887 | 158887 | 157063.9 | 152810 | 152938 | 152938 | 152938 | 152938 | 152938 | 150938 | 52938 | 52938 | 30938 | 32938 | 30938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | 62293.59 | 0 | 0 | 0 | 0 | 0 | 0 | 908.37 | -1476.06 | 0 | 723.32 | 0 | 0 | 752.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 517096.28 | 14840.56 | 14965.36 | 14965.36 | 14965.36 | 14965.36 | 14965.36 | 19536.75 | -86544.46 | 13554.76 | 17721.17 | 14849.7 | 14795.68 | 18327.77 | 12825.36 | 13838.73 | 32628.94 | 14084.84 | 869.18 | 27009 | 27009 | 27009 | 27009 | 27009 | 26815.98 | 26815.98 | 26815.98 | 22985.13 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 193.02 | 0 | 0 | 0 | 0 | 193.02 | 193.02 | 193.02 | 0 | 0 | 0 | 0
C13022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 646818.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 467830.73 | 23050.42 | 27195.82 | 27195.82 | 27195.82 | 27195.82 | 27195.82 | 27400.22 | -138125.87 | 19449.95 | 20304.52 | 18187.3 | 18121.14 | 15918.31 | 7442.4 | 11002.48 | 9375 | 11198.15 | 691.04 | 21473.51 | 21473.51 | 21473.51 | 21473.51 | 21473.51 | 15560.98 | 15560.98 | 15560.98 | 13337.98 | 5912.52 | 5912.52 | 7482.35 | 14703.58 | 8738.22 | 5912.52 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0
C13022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1422087.75 | 59086.21 | 56406.34 | 54018.64 | 54018.64 | 54018.64 | 54018.64 | 54018.64 | -37181.69 | 50198.26 | 51789.35 | 52604.75 | 52413.38 | 51379.29 | 45433.59 | 48673.07 | 46082.35 | 49538.69 | 3057.05 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 94995.07 | 102449.38 | 60762.46 | 53888 | 61840.5 | 155342.49 | 72887.23 | 33829.47 | 33829.47 | 33829.47 | 33829.47 | 9665.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13022 | Temporary Services | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 787.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 577758.41 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 10098.64 | 6792.94 | 14239.78 | 14754.45 | 15712.45 | 15655.29 | 15346.42 | 13570.5 | 14538.1 | 12387.63 | 14796.65 | 913.11 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 28373.96 | 37301.57 | 23218.8 | 14934.87 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 10332.69 | 2952.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 49467.19 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | 4715.01 | -24877.39 | 3122.35 | 3651.99 | 4273.79 | 4258.24 | 4174.23 | 3691.18 | 3954.36 | 3369.44 | 4024.69 | 248.37 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 7717.72 | 10171.83 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 7316.85 | 2090.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1109448.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12538.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 152185.55 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | 4316.96 | -5858.19 | 4694.97 | 4864.66 | 5180.52 | 5161.67 | 5059.84 | 4474.3 | 4793.33 | 4084.3 | 4878.57 | 301.06 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9355.12 | 9751.59 | 15480.02 | 12130.39 | 11761.15 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 11096.5 | 3170.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 563.64 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | 1776.74 | -11113.59 | 1482.51 | 1536.1 | 1635.83 | 1629.88 | 1597.73 | 1412.84 | 1513.57 | 1289.69 | 1540.49 | 95.06 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 2954.03 | 101641.21 | 165458.47 | 2954.03 | 16677.78 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 1027.22 | 293.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 6881.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 41278.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3701.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 3203.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1041.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 29869.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 12413 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | 143.87 | -1589.39 | 142.38 | 147.52 | 157.1 | 156.53 | 153.44 | 135.68 | 145.36 | 123.86 | 147.94 | 9.13 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 283.69 | 243.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 118100.59 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 1623.02 | 260.11 | 1606.13 | 1664.18 | 1772.24 | 1765.79 | 1730.95 | 1530.65 | 1639.78 | 1397.23 | 1668.95 | 102.99 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 3200.36 | 2743.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13030 | H&S Quality Environmental | LAB | Labour | BUDGET | Approved Early Budget | 9153.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13030 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 2762.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | 12144.26 | -46263.35 | 8975.82 | 9300.23 | 9904.09 | 9868.07 | 9673.37 | 8553.95 | 9163.86 | 7808.35 | 9326.84 | 575.56 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 17885.08 | 15330.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13030 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 290640.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66061.74 | 8892.7 | 9214.1 | 9812.37 | 9776.68 | 9583.79 | 8474.73 | 8457.58 | 323.1 | 385.94 | 23.82 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 740.07 | 634.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13030 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 692776.89 | 8972.32 | 8972.32 | 8972.32 | 8972.32 | 9408.85 | 11416.86 | 11416.86 | 76696.36 | 10017.84 | 10379.91 | 11053.88 | 11013.67 | 10796.37 | 9547 | 10227.71 | 8714.83 | 10409.6 | 642.38 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 19961.39 | 17406.15 | 2074.7 | 1333.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13030 | H&S Quality Environmental | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | 11726.91 | -88457.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 7049.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 27831.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8129.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13034 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1435.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 241762.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58332.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 9182.85 | 9182.85 | 13646.18 | 19597.29 | 19597.29 | 19597.29 | 19597.29 | -95824.59 | 16326.62 | 16916.71 | 18015.1 | 17949.57 | 16316.81 | 10282.89 | 11016.07 | 9386.58 | 11211.99 | 691.9 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 21500.04 | 74405.56 | 170942.94 | 170942.94 | 66741.08 | 17382.31 | 17382.31 | 17382.31 | 17382.31 | 4966.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | LAB | Labour | BUDGET | Approved Early Budget | 1143039.89 | 52141.82 | 52141.82 | 52141.82 | 52141.82 | 52141.82 | 55910.03 | 78519.29 | -45619.64 | 76611.15 | 79380.08 | 84534.19 | 84226.68 | 82564.92 | 73010.36 | 78216.1 | 66646.41 | 53858.94 | 3323.66 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 103279.55 | 158862.57 | 103279.55 | 91164.57 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 84434.02 | 24124.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | MAT | Materials | BUDGET | Approved Early Budget | 408802.38 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 830.79 | 23514.82 | 630.18 | 652.96 | 695.35 | 692.82 | 679.16 | 600.56 | 643.38 | 548.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7350.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | MISC | Miscellaneous | BUDGET | Approved Early Budget | 37944.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 422325.88 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | 10114.91 | -48235.51 | 7823.46 | 8106.22 | 8632.55 | 8601.15 | 7659.38 | 4269.69 | 4574.12 | 3897.52 | 2978.48 | 183.8 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 5711.51 | 81572.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | STAFF | Staff | BUDGET | Approved Early Budget | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13036 | Access, temporary roads and walkways | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 126144.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13644.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 694331.4 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | 13813.44 | -12880.91 | 10631.99 | 11016.26 | 11731.54 | 11688.87 | 11458.25 | 10132.28 | 10854.73 | 9249.1 | 11047.77 | 681.76 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 21185.14 | 20438.79 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 21281.02 | 10538.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 4140.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 29376.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4928.08 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | 675.57 | -4264.75 | 519.98 | 538.77 | 573.75 | 571.67 | 560.39 | 495.54 | 530.87 | 452.35 | 540.31 | 33.34 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 1036.1 | 888.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | STAFF | Staff | BUDGET | Approved Early Budget | 7661.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | -64415.24 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | 1822.19 | -8333.62 | 1502.8 | 8635.06 | 1658.22 | 1652.19 | 1619.59 | 1432.17 | 1534.29 | 1307.33 | 1561.57 | 96.37 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 16605.89 | 2994.46 | 78395.44 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 2994.46 | 855.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13040 | Plant & Equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3673.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13040 | Plant & Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -2689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13042 | Battersea Prelims Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | LAB | Labour | BUDGET | Approved Early Budget | 961341.94 | 71681.84 | 66679.04 | 66679.04 | 66679.04 | 66679.04 | 68966.86 | 88003.22 | -186335.09 | 55480.09 | 70465.54 | 83785.45 | 81383.25 | 82068.59 | 67337.16 | 72138.4 | 53638.61 | 53893.79 | 3325.81 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 103346.39 | 98939.37 | 72497.29 | 48464.63 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 16463.32 | 4703.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | MAT | Materials | BUDGET | Approved Early Budget | 38039.17 | 3134.66 | 2336.06 | 2336.06 | 2733.51 | 2781.2 | 3771.72 | 6161.25 | -20412.29 | 4288.61 | 5242.2 | 5777.84 | 4906.86 | 4718.71 | 3337.09 | 3575.03 | 2840.07 | 2953.43 | 182.26 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5663.47 | 5110.71 | 1794.17 | 1553.25 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 1119.61 | 319.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4793.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1958145.72 | 161808.56 | 154469.36 | 154469.36 | 164571.55 | 165783.81 | 254955.44 | 205270.72 | -310212.34 | 83284.06 | 30915.74 | 48627.79 | 43936.36 | 44124.35 | 31479.67 | 87183.5 | 21232.41 | 23426.2 | 1445.64 | 44921.94 | 71006.02 | 71006.02 | 44921.94 | 44921.94 | 44921.94 | 55355.57 | 44921.94 | 41928.98 | 23971.27 | 19417.06 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 9268.09 | 2648.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13044 | Craneage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 158749.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19913.85 | 38117.8 | 39495.48 | 37997.94 | 29315.65 | 25263.78 | 17737.43 | 15706.75 | 15863.16 | 19222.08 | 979.23 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 30428.55 | 36860.14 | 30428.55 | 26081.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13045 | Tower cranes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13046 | Mobile cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13046 | Mobile cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13047 | Crawler cranes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13048 | Operatives support | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13049 | Material Handling plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13050 | Passenger/good hoists | LAB | Labour | BUDGET | Approved Early Budget | 21411.29 | 10784.94 | 10784.94 | 15346.46 | 15733.21 | 15733.21 | 15733.21 | 15733.21 | -27029.36 | 24555.43 | 25442.93 | 27094.93 | 26996.36 | 26463.73 | 23401.3 | 25069.85 | 21361.53 | 25515.7 | 1574.59 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 48928.75 | 25761.07 | 9207.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13050 | Passenger/good hoists | MAT | Materials | BUDGET | Approved Early Budget | 18.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13050 | Passenger/good hoists | MISC | Miscellaneous | BUDGET | Approved Early Budget | -14111.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13050 | Passenger/good hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 29873.06 | 3366.9 | 3366.9 | 22883.19 | 14894 | 6594 | 6594 | 6594 | -23557.32 | 6052.93 | 6271.7 | 12683.7 | 6654.63 | 6523.33 | 5768.44 | 6179.74 | 5265.63 | 6289.64 | 388.14 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 12060.98 | 22904.57 | 22904.57 | 12060.98 | 12060.98 | 12060.98 | 10398.9 | 6243.71 | 2006.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 369438.73 | 25363.44 | 25363.44 | 25363.44 | 25363.44 | 25363.44 | 14931.64 | 12663.85 | -27772.17 | 19299.6 | 19997.14 | 21295.54 | 21218.08 | 20799.45 | 18392.5 | 19703.91 | 16789.32 | 10050.84 | 620.24 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 19273.42 | 12390.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | -217.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13052 | Scaffolding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 20503.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 167483.38 | 21290.12 | 21290.12 | 21290.12 | 3201.04 | 1809.57 | 4527.04 | 5614.03 | -76954.93 | 7673.35 | 8928.49 | 11117.48 | 11077.04 | 10858.49 | 5540.44 | 3874.44 | 3301.33 | 3943.34 | 243.35 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 7561.73 | 6707 | 2378.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13054 | Surveyor and monitoring | LAB | Labour | BUDGET | Approved Early Budget | 1904.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13054 | Surveyor and monitoring | MAT | Materials | BUDGET | Approved Early Budget | 63.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13054 | Surveyor and monitoring | MISC | Miscellaneous | BUDGET | Approved Early Budget | 326.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13054 | Surveyor and monitoring | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 12277.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13056 | Communication and radios | MAT | Materials | BUDGET | Approved Early Budget | 25311.6 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | 3013.54 | -21094.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13056 | Communication and radios | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8995.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13056 | Communication and radios | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2072.96 | 2321.86 | 2405.77 | 2561.98 | 2552.66 | 2502.3 | 2212.73 | 2370.5 | 2019.85 | 2412.65 | 148.89 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 4626.49 | 1321.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13058 | Hoarding and fences | LAB | Labour | BUDGET | Approved Early Budget | 47513.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -965.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13058 | Hoarding and fences | MAT | Materials | BUDGET | Approved Early Budget | 21279.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13058 | Hoarding and fences | MISC | Miscellaneous | BUDGET | Approved Early Budget | 64.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13058 | Hoarding and fences | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14393.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13058 | Hoarding and fences | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 60834.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54014.1 | 0 | 9409.08 | 40080.02 | 0 | 0 | 0 | 3119.78 | 37216.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10570.15 | 42280.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114751.24 | 41727.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13061 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13061 | PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13061 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13062 | Collective protective equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13064 | Training | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13065 | Maintenance of protective equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13065 | Maintenance of protective equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13066 | Laboratory | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13067 | Quality equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | LAB | Labour | BUDGET | Approved Early Budget | 57639.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3895.68 | 46472.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | MAT | Materials | BUDGET | Approved Early Budget | 238193.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 3293.16 | 39284.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7053.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 25913.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286.17 | 17348.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13077 | Set-up of assembly and store areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798.27 | 21451.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | LAB | Labour | BUDGET | Approved Early Budget | 81602.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718.81 | 0 | 0 | 0 | 0 | 0 | 3920.9 | 20022.24 | 20043.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60509.37 | 80679.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | MAT | Materials | BUDGET | Approved Early Budget | 1121730.31 | 10145.72 | 25749.41 | 22350.79 | 22802.83 | 22802.83 | 54695.87 | 112517.55 | -218849.94 | 84255.93 | 53390.71 | 45202.94 | 29330.46 | 26387.17 | 27094.74 | 16783.76 | 24733.03 | 17082.25 | 2592.05 | 32756.81 | 32756.81 | 32756.81 | 56651.2 | 26255.94 | 26255.94 | 74044.73 | 101301.1 | 90706.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 338941.53 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6153.76 | 6360.39 | 3224.36 | 3340.9 | 3557.82 | 3544.88 | 3474.94 | 3072.82 | 3291.91 | 2804.97 | 3350.46 | 206.76 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 6424.81 | 26402.09 | 32143.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 565826.41 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | 2475.69 | -17329.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13080 | Temporary Works | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 162.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13081 | Temporary works for D-Walls and piling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13082 | Sheet Piling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13082 | Sheet Piling | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13084 | Temporary propping crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13085 | Anchors for the sheet piles | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13086 | Interface with duchess bridge | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13087 | Watertight/Dewatering | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13088 | Other temporary works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | LAB | Labour | BUDGET | Approved Early Budget | 17808.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | MAT | Materials | BUDGET | Approved Early Budget | 4594.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14777.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3782.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23112 | General | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794.35 | 3524.77 | 3753.63 | 3739.98 | 3666.19 | 3241.93 | 3473.08 | 2959.35 | 3534.85 | 218.14 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 6778.41 | 1936.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23114 | Sewer Utilities | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23114 | Sewer Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23114 | Sewer Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23116 | Water Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 313071.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23118 | Gas Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 84015.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23118 | Gas Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23118 | Gas Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46110.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23120 | Other Utilities | LAB | Labour | BUDGET | Approved Early Budget | 40874.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23120 | Other Utilities | MAT | Materials | BUDGET | Approved Early Budget | 32786.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23120 | Other Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 247366.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.91 | 413.63 | 440.48 | 438.88 | 430.22 | 380.44 | 407.56 | 347.27 | 414.81 | 25.6 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 227.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23120 | Other Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4436.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23122 | Utilities Permanent Connections | MAT | Materials | BUDGET | Approved Early Budget | 32.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23122 | Utilities Permanent Connections | MISC | Miscellaneous | BUDGET | Approved Early Budget | 271549.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23122 | Utilities Permanent Connections | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 100.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23122 | Utilities Permanent Connections | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55706.52 | 43115.14 | 0 | 151799.73 | 182109.92 | 269022.95 | 200234.92 | 757669.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23124 | UXO Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23140 | Work to existing Jetty for river traffic use and other river facilities | MAT | Materials | BUDGET | Approved Early Budget | 563483.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40638.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23140 | Work to existing Jetty for river traffic use and other river facilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 273.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23140 | Work to existing Jetty for river traffic use and other river facilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 11055.17 | 0 | 3406.73 | 0 | 0 | 0 | 0 | 0 | -3406.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23140 | Work to existing Jetty for river traffic use and other river facilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 95715.68 | 26415.1 | 42264.17 | 0 | 0 | 0 | 0 | 0 | -19333.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23150 | Haulage of the spoil from the overrun tunnels to muck bin area | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23161 | Conveyor maintenance before and after TBM excavation | LAB | Labour | BUDGET | Approved Early Budget | 586633.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23161 | Conveyor maintenance before and after TBM excavation | MAT | Materials | BUDGET | Approved Early Budget | 51586.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23161 | Conveyor maintenance before and after TBM excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23161 | Conveyor maintenance before and after TBM excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 89784.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23161 | Conveyor maintenance before and after TBM excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 728600.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -240.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23162 | Conveyor maintenance - TBM period | LAB | Labour | BUDGET | Approved Early Budget | 1048282.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23162 | Conveyor maintenance - TBM period | MAT | Materials | BUDGET | Approved Early Budget | -670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23162 | Conveyor maintenance - TBM period | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23162 | Conveyor maintenance - TBM period | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 24606.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1530.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23162 | Conveyor maintenance - TBM period | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 174823.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23163 | Dismantling of the outside conveyors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 356922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | MAT | Materials | BUDGET | Approved Early Budget | 111552.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63424.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 102610.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23164 | Manufacture supply and installation of the outside conveyors (reclaim main conveyor and tripper) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2486365.81 | 0 | 0 | 0 | -150000 | 0 | 0 | 0 | 149999.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -149757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31101 | Battersea Station D-Walls | LAB | Labour | BUDGET | Approved Early Budget | 408837.48 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | 5014.57 | -31271.09 | 2968.37 | 3075.66 | 3275.36 | 3263.44 | 3199.05 | 2828.85 | 3030.56 | 1383.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31101 | Battersea Station D-Walls | MAT | Materials | BUDGET | Approved Early Budget | 245573.83 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | 2988.38 | -19309.63 | 1802.23 | 1867.36 | 1988.61 | 1981.38 | 1942.29 | 1717.52 | 1839.98 | 839.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31101 | Battersea Station D-Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31101 | Battersea Station D-Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 469772.51 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | 893.55 | -6521.36 | 530.07 | 549.23 | 584.89 | 582.76 | 571.26 | 505.15 | 541.17 | 247.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31101 | Battersea Station D-Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 19047032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31102 | Battersea Station Demobilisation of d-wall grabs and bentonite plant (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31103 | Battersea Station Diaphragm wall prelims and Project management (Station Box) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31103 | Battersea Station Diaphragm wall prelims and Project management (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31104 | Battersea Station Guide Wall install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31105 | Battersea Station Guide Wall remove | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31106 | Battersea Station Install diaghram wall panels 1200 mm thick including excavation concrete reinforce | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31107 | Battersea Station Install and supply plunge columns twin 356x406x634UC fixing and connections | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31107 | Battersea Station Install and supply plunge columns twin 356x406x634UC fixing and connections | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31108 | Battersea Station Cropping d-walls to the cuff-off level and bar straighten | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31109 | Battersea Station Cleaning d-walls surface | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31110 | Battersea Station Inclinometers & sonic loggin tubes and tests D-walls (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31111 | Battersea Station Install and supply B40 female coupler with starter bar set into box-out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31112 | Battersea Station Slab box-out 50 mm deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31112 | Battersea Station Slab box-out 50 mm deep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31150 | Battersea Station Piling | LAB | Labour | BUDGET | Approved Early Budget | 88566.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31150 | Battersea Station Piling | MAT | Materials | BUDGET | Approved Early Budget | 274041.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31150 | Battersea Station Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 40679.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31150 | Battersea Station Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4622918.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31151 | Battersea Station Piling prelims & demobilise Piling Rig #1 & 2100m and 2400mm piling equipment | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31152 | Battersea Station Bore Piles excavation concrete reinforcement and backfilling (Station Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31152 | Battersea Station Bore Piles excavation concrete reinforcement and backfilling (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31153 | Battersea Station Install and supply plunge columns in bore piles fittings and connections included | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31153 | Battersea Station Install and supply plunge columns in bore piles fittings and connections included | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31154 | Battersea Station Cropping Bore piles and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31155 | Battersea Station Sonic loggin tubes install grouting & tests piles (Station Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31156 | Battersea Station Pile Mat install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31157 | Battersea Station Pile Mat remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31157 | Battersea Station Pile Mat remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | LAB | Labour | BUDGET | Approved Early Budget | 1357262.74 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 20833.6 | 8184.63 | -34243.63 | 8393.51 | 8696.88 | 9261.56 | 9227.87 | 9045.81 | 7999.01 | 8569.35 | 3911.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | MAT | Materials | BUDGET | Approved Early Budget | 2465267.29 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 21963.05 | 8628.34 | -48478.87 | 8393.51 | 8696.88 | 9261.56 | 9227.87 | 9045.81 | 7999.01 | 8569.35 | 3911.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11810.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 211716.89 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 2553.61 | 1003.2 | 37212.96 | 585.59 | 606.76 | 646.15 | 643.8 | 631.1 | 558.07 | 597.86 | 272.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31200 | Battersea Station Lower Mall (Basement Level -1) Beams | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9011.3 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 7458.44 | 2930.1 | -45763.74 | 2147.17 | 2224.78 | 2369.23 | 2360.61 | 2314.04 | 2046.26 | 2192.16 | 1000.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31201 | Battersea Station Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31201 | Battersea Station Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31202 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31203 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31204 | Battersea Station Reinforcement in situ beams over to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31205 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31206 | Battersea Station Precast beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31208 | Battersea Station Standard coupler to connect beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31208 | Battersea Station Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31209 | Waterproofing system back side capping beam, including breaking blinding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31210 | Earthing and bonding protection in Level B1 and B2 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31212 | Installation of temporary props in Level B1 - (Top down) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31214 | Battersea Station lower mall (basement level -1) beams: Lattice plank prep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31214 | Battersea Station lower mall (basement level -1) beams: Lattice plank prep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31215 | Plint on top of beams in Level B1 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | LAB | Labour | BUDGET | Approved Early Budget | 363435.99 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 12298.69 | 209258.75 | 6941.3 | 7192.18 | 7659.17 | 7631.3 | 7480.74 | 6615.06 | 7086.72 | 3234.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | MAT | Materials | BUDGET | Approved Early Budget | 1075265.89 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | 64557.63 | -218377.37 | 52671.54 | 54575.23 | 58118.77 | 57907.35 | 56764.86 | 50195.94 | 49332.15 | 21206.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2021.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 184721.43 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | 16011.41 | -88969.76 | 10026.33 | 10388.71 | 11063.24 | 11022.99 | 10805.51 | 9555.08 | 10236.37 | 4672.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31240 | Battersea Station Lower Mall (Basement Level -1) Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | 32444.9 | -11127.75 | 14653.86 | 15183.49 | 16169.35 | 16110.53 | 15792.67 | 13965.12 | 14960.85 | 6829.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31241 | Battersea Main Works Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31242 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31242 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31243 | Battersea Main Works Formwork vertical to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31244 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31245 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31246 | Battersea Main Works Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31247 | Battersea Station Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31247 | Battersea Station Exposure of couplers in beams and slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31249 | Precast soffits slabs ticket hall | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31250 | Battersea Station 75mm Pre Cast planks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31251 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31254 | Battersea Station Additional propping/falsework required to support 3m thick slabs due to increased | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31255 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31255 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31256 | Removal of temporary Props | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31258 | Bulkheads in the Western and Eastern entrances | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31258 | Bulkheads in the Western and Eastern entrances | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31259 | Making Good Prior to handover to MEP/Fitout and BPSDC | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | LAB | Labour | BUDGET | Approved Early Budget | 632854.55 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 47949.92 | 18837.47 | -178866.32 | 17918.65 | 18566.27 | 19771.77 | 19699.85 | 19311.18 | 17076.45 | 7186.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | MAT | Materials | BUDGET | Approved Early Budget | 1312314.11 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 31084.86 | 12211.91 | -63621.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7501.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31260 | Battersea Station Ticket Hall (Basement Level -2) Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 88487.68 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 9078.46 | 3566.54 | -48998.53 | 2481.04 | 2570.71 | 2737.63 | 2727.67 | 2673.85 | 2364.43 | 995.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31261 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31262 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31263 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31264 | Battersea Station Reinforcement in situ beams up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31266 | Battersea Station Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31267 | Battersea Station Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31268 | Permanent steel proppoing beams 700x700x60 SHS - NEW ACTIVITY | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31270 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | LAB | Labour | BUDGET | Approved Early Budget | 476867.92 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | 17109.63 | -24168.88 | 16910.02 | 17521.2 | 18658.84 | 18590.97 | 18224.17 | 16115.24 | 6782.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | MAT | Materials | BUDGET | Approved Early Budget | 1008631.12 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | 13762.38 | -59739.7 | 8182.27 | 8478 | 9028.47 | 8995.63 | 8818.15 | 7797.7 | 3281.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 148907.16 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 9025.56 | 13055.35 | 6000.33 | 6217.2 | 6620.88 | 6596.79 | 6466.64 | 5718.31 | 2406.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31290 | Battersea Station Ticket Hall (Basement Level -2) Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | 24565.32 | -151015.8 | 23455.84 | 24303.6 | 25881.62 | 25787.47 | 25278.69 | 22353.4 | 9407.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31291 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31291 | Battersea Station Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31292 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31293 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31294 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31295 | Battersea Station 75mm Pre Cast planks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31297 | Battersea Station Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31300 | Waterproofing system base slab (Ticket Hall) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31300 | Waterproofing system base slab (Ticket Hall) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31301 | Internal structure Western and Eastern escalator pits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31302 | Falsework for in situ slabs (bottom-up slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31303 | Jacking Points | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31304 | Removal of Temp Props | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31308 | Extra Penetrations for B02 Gantry Slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31310 | Battersea Station Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 469085.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31310 | Battersea Station Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 1747487.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67604.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31310 | Battersea Station Base Slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31310 | Battersea Station Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 98174.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7677.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31311 | Battersea Station Provision of mass concrete mix. G and blinding (Base level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31312 | Battersea Station Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31313 | Battersea Station Reinforcement RC Slabs (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31314 | Battersea Station Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31317 | Waterproofing system for base slab (Station) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31318 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31319 | Standard coupler | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31330 | Battersea Station West Core (Roof Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 18176.39 | 18176.39 | 18176.39 | 18176.39 | 18176.39 | 16878.07 | 0 | -7881.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31330 | Battersea Station West Core (Roof Slab) | MAT | Materials | BUDGET | Approved Early Budget | 14423.48 | 39758.62 | 39758.62 | 39758.62 | 39758.62 | 39758.62 | 36918.72 | 0 | -23424.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31330 | Battersea Station West Core (Roof Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1751.9 | 7270.7 | 7270.7 | 7270.7 | 7270.7 | 7270.7 | 6751.37 | 0 | -44509.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31330 | Battersea Station West Core (Roof Slab) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 3526.22 | 3526.22 | 3526.22 | 3526.22 | 3526.22 | 3274.35 | 0 | 9770.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31331 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31332 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31333 | Battersea Station Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31336 | Battersea Station Additional propping/falsework to 1.5 m thick roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31337 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31339 | Protection of waterproofing with red concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31340 | Couplers | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31370 | Battersea Station Ticket Hall Columns | LAB | Labour | BUDGET | Approved Early Budget | 139316.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -507.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31370 | Battersea Station Ticket Hall Columns | MAT | Materials | BUDGET | Approved Early Budget | 119313.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31370 | Battersea Station Ticket Hall Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 33941.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2442.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31371 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31374 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31375 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31378 | Making good columns (embedded sockets,...) between B2 and B1 for cladding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31380 | Battersea Station Platform Columns | LAB | Labour | BUDGET | Approved Early Budget | 104759.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32104.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31380 | Battersea Station Platform Columns | MAT | Materials | BUDGET | Approved Early Budget | 83464.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -654.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31380 | Battersea Station Platform Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7160.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -381.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31381 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31382 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31383 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31386 | Making good columns (embedded sockets,...) between B3 and B2 for cladding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31390 | Battersea Station Base Slab Columns | LAB | Labour | BUDGET | Approved Early Budget | 87124.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31390 | Battersea Station Base Slab Columns | MAT | Materials | BUDGET | Approved Early Budget | 16929.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31968.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31390 | Battersea Station Base Slab Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16524.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12477.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31391 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31391 | Battersea Station Concrete Mix C50/60 primary structures Platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31393 | Battersea Station Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31394 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31395 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31400 | Battersea Station Platform Construction | LAB | Labour | BUDGET | Approved Early Budget | 362617.26 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | 6337.49 | -20319.34 | 7817.63 | 8100.18 | 8626.12 | 8594.74 | 8425.17 | 5587.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31400 | Battersea Station Platform Construction | MAT | Materials | BUDGET | Approved Early Budget | 1228667.28 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | 8214.12 | -301.56 | 3127.05 | 3240.07 | 3450.45 | 3437.9 | 3370.07 | 2235.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31400 | Battersea Station Platform Construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 92380.44 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 952.09 | 47111.12 | 781.76 | 810.02 | 862.61 | 859.47 | 842.52 | 558.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31400 | Battersea Station Platform Construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1631.8 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | 30124.89 | -186445.65 | 27361.69 | 28350.61 | 30191.4 | 30081.57 | 29488.08 | 19556.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31401 | Provision of mass concrete Grade C30/40 (First Stage Concrete) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31402 | Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31403 | Concrete Mix C50/60 primary structures B4 level (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31403 | Concrete Mix C50/60 primary structures B4 level (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31404 | Formwork for slabs up to 1500 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31405 | Reinforcement for estructural "in situ" elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31405 | Reinforcement for estructural "in situ" elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31407 | 700mmm x 700mm Linear Insert to form channel in mass concrete at | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31408 | Precast concrete wall for precast platforms | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31409 | Precast concrete slab for precast platform (including in situ stitches in the rate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31410 | Construction of connection between box, headwall and tunnels inc | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31410 | Construction of connection between box, headwall and tunnels inc | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31411 | Reinforcement for estructural "in situ" elements (walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31411 | Reinforcement for estructural "in situ" elements (walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31412 | PC Beams 650x650 mm & 1000x1000 mm (under slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31416 | Waterproofing D Wall before first stage concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31420 | Battersea Station Mezzanine | LAB | Labour | BUDGET | Approved Early Budget | 60110.73 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | 1575.17 | -11380.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31420 | Battersea Station Mezzanine | MAT | Materials | BUDGET | Approved Early Budget | 59935.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26133.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31420 | Battersea Station Mezzanine | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22051.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31420 | Battersea Station Mezzanine | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | 2024.79 | -12805.61 | 1532.16 | 1587.54 | 1690.62 | 1684.47 | 1651.23 | 1460.15 | 1564.26 | 1332.88 | 1592.08 | 28.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31421 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31421 | Battersea Station Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31422 | Battersea Station Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31423 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31423 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31424 | Battersea Station 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31424 | Battersea Station 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31425 | PC Beams 650x650 mm & 1000x1000 mm (under slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31426 | Falsework to install beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31427 | Precast Walls - 300mm wide | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31427 | Precast Walls - 300mm wide | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31440 | Battersea Station Walls Platform | LAB | Labour | BUDGET | Approved Early Budget | 906.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31440 | Battersea Station Walls Platform | MAT | Materials | BUDGET | Approved Early Budget | 2082.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31445 | Precast Walls - 250mm (Platform) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31445 | Precast Walls - 250mm (Platform) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31450 | Battersea Station STAIRCASES | LAB | Labour | BUDGET | Approved Early Budget | 5427.93 | 8235.38 | 8235.38 | 8235.38 | 8235.38 | 8235.38 | 2647.09 | 0 | 19002.72 | 225.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31450 | Battersea Station STAIRCASES | MAT | Materials | BUDGET | Approved Early Budget | 65853.66 | 9304.08 | 9304.08 | 9304.08 | 9304.08 | 9304.08 | 2990.6 | 0 | 213683.52 | 1801.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31450 | Battersea Station STAIRCASES | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 3559.07 | 3559.07 | 3559.07 | 3559.07 | 3559.07 | 1143.99 | 0 | -13925.53 | 450.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31450 | Battersea Station STAIRCASES | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 72213.15 | 72213.15 | 72213.15 | 72213.15 | 72213.15 | 23211.37 | 0 | -358010.78 | 3152.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31451 | Stairs Flight | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31451 | Stairs Flight | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31451 | Stairs Flight | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31452 | Stairs landing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31452 | Stairs landing | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31453 | Making good staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31464 | Mass fill concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31464 | Mass fill concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31465 | Banagher Quotation - Landing Beam | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31466 | In-Situ Mass Fill Stairs Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31467 | Central Dividing Wall for East & West Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31467 | Central Dividing Wall for East & West Core | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31469 | Fireproofing - MITIE or ANOTHER | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | LAB | Labour | BUDGET | Approved Early Budget | 796341.65 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 11497.47 | 33319.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | MAT | Materials | BUDGET | Approved Early Budget | 687410.87 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 9936.49 | 54635.56 | 8028.45 | 1485.46 | 5874.96 | 5853.59 | 5738.1 | 5074.08 | 5435.87 | 4631.8 | 5532.54 | 48.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 355.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 397784.95 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | 6616.8 | -17912.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31470 | Battersea Station West Core (in situ walls and precast walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 15600.92 | 54603.22 | 54603.22 | 54603.22 | 231891.07 | 0 | 0 | 111624.28 | 111218.22 | 109023.92 | 96407.49 | 103281.48 | 88004.12 | 105118.28 | 636000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31471 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31472 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31473 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31474 | Battersea Station Precast Walls between 200-400 mm wide including connections to RC columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31474 | Battersea Station Precast Walls between 200-400 mm wide including connections to RC columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31475 | Battersea Station GL B/C 2-3 406mm x 16mm thick Dia. CHS Diagonal Bracing to Western Core Walls from | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31476 | Precast Walls - 250 mm thick (lift shaft) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31476 | Precast Walls - 250 mm thick (lift shaft) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31477 | Falserwork to construct walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31479 | KILNBRIDGE structural steel work | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31480 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31490 | Battersea Station East Core (in situ walls and precast walls) | LAB | Labour | BUDGET | Approved Early Budget | 256995.88 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 19575.6 | 232044.48 | 17001.42 | 3145.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31490 | Battersea Station East Core (in situ walls and precast walls) | MAT | Materials | BUDGET | Approved Early Budget | 306203.15 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 14044.88 | 150692.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31490 | Battersea Station East Core (in situ walls and precast walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 105436.19 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 10257.6 | 110684.1 | 3778.09 | 699.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31490 | Battersea Station East Core (in situ walls and precast walls) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | 4623.85 | -15923.13 | 18418.2 | 3407.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31491 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31492 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31493 | Battersea Station Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31496 | Precast Walls - 250mm wide | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31497 | Falsework to construct walls in East Core | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31498 | Scabbling downstand kickers | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31500 | Battersea Station West & East Cores (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 94430.87 | 13717.84 | 13717.84 | 13717.84 | 13717.84 | 8638.28 | 4828.61 | 4828.61 | 95452.34 | 1195.98 | 1239.21 | 1319.67 | 1314.87 | 1288.93 | 1139.77 | 1221.04 | 1040.42 | 1242.76 | 21.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31500 | Battersea Station West & East Cores (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 111253.24 | 13301.95 | 13301.95 | 13301.95 | 13301.95 | 8376.39 | 4682.22 | 4682.22 | 145244.2 | 1025.14 | 1062.19 | 1131.15 | 1127.04 | 1104.8 | 976.95 | 1046.61 | 891.8 | 1065.23 | 18.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31500 | Battersea Station West & East Cores (Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 81812.27 | 4188.09 | 4188.09 | 4188.09 | 4188.09 | 2637.29 | 1474.19 | 1474.19 | -114529.64 | 341.71 | 354.06 | 377.05 | 375.68 | 368.27 | 325.65 | 348.87 | 297.27 | 355.08 | 6.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31500 | Battersea Station West & East Cores (Slabs) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 30191.73 | 30191.73 | 30191.73 | 30191.73 | 19012.08 | 10627.34 | 10627.34 | -139857.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31501 | Battersea Station Concrete Mix C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31502 | Battersea Station Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31503 | Battersea Station Reinforcement for estructural in situ elements (Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31508 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31508 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31509 | Battersea Main M3 Falsework | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | LAB | Labour | BUDGET | Approved Early Budget | 45792.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16603.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | MAT | Materials | BUDGET | Approved Early Budget | 56461.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12638.89 | 4422.33 | 9869.28 | 10510.09 | 10471.85 | 10265.25 | 9077.33 | 9724.56 | 4438.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1597.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31520 | Battersea Station Drainage (Sumps fittings power and connection to the existing system) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12965.92 | 14522.72 | 15047.61 | 16024.64 | 15966.35 | 15651.34 | 13840.14 | 14826.96 | 12633.76 | 15090.65 | 266.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31547 | Installation of drainage Channel | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31547 | Installation of drainage Channel | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31547 | Installation of drainage Channel | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | LAB | Labour | BUDGET | Approved Early Budget | 97401.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3998.73 | 209.67 | 217.24 | 231.35 | 230.51 | 225.96 | 199.81 | 214.06 | 97.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | MAT | Materials | BUDGET | Approved Early Budget | 95910.38 | 693.47 | 693.47 | 693.47 | 693.47 | 693.47 | 693.47 | 272.44 | -3734.87 | 358.46 | 371.41 | 395.53 | 394.09 | 386.32 | 341.61 | 365.97 | 167.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 92.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 149682.96 | 207.35 | 207.35 | 207.35 | 207.35 | 207.35 | 207.35 | 81.46 | -1228.95 | 108.21 | 112.13 | 119.41 | 118.97 | 116.62 | 103.13 | 110.48 | 50.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31601 | Battersea Crossover D-Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 7118782.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31602 | Battersea Crossover Mobilisation of d-wall grabs & set up bentonite plant (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31603 | Battersea Crossover Diaphragm wall prelims and Project management (Xover Box) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31603 | Battersea Crossover Diaphragm wall prelims and Project management (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31604 | Battersea Crossover Guide Wall install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31604 | Battersea Crossover Guide Wall install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31605 | Battersea Crossover Guide Wall remove | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31606 | Battersea Crossover Install diaghram wall panels 1200 mm thick including excavation concrete reinfor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31607 | Battersea Crossover Cropping d-walls to the cuff-off level and bar straighten | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31608 | Battersea Crossover Cleaning d-walls surface | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31608 | Battersea Crossover Cleaning d-walls surface | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31609 | Battersea Crossover Inclinometers & sonic loggin tubes and tests D-walls (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31610 | Battersea Crossover B40 female coupler with starter bar set into box-out (h above) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31611 | Battersea Crossover Slab Box-out - 50mm deep | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31640 | Battersea Crossover Piling | LAB | Labour | BUDGET | Approved Early Budget | 21718.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31640 | Battersea Crossover Piling | MAT | Materials | BUDGET | Approved Early Budget | 5036.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31640 | Battersea Crossover Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2454.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31640 | Battersea Crossover Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1613698.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31641 | Battersea Crossover Piling prelims & Mobilise Piling Rig #1 & equipment (Xover Box) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31641 | Battersea Crossover Piling prelims & Mobilise Piling Rig #1 & equipment (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31642 | Battersea Crossover Bore Piles excavation concrete reinforcement and backfilling (Xover Box) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31642 | Battersea Crossover Bore Piles excavation concrete reinforcement and backfilling (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31643 | Battersea Crossover Install and supply plunge columns in bore piles fittings and connections include | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31644 | Battersea Crossover Cropping Bore piles and bar straighten | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31644 | Battersea Crossover Cropping Bore piles and bar straighten | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31645 | Battersea Crossover Sonic loggin tubes install grouting & tests piles (Xover Box) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31646 | Battersea Crossover Pile Mat install | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31646 | Battersea Crossover Pile Mat install | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31647 | Battersea Crossover Pile Mat remove | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | LAB | Labour | BUDGET | Approved Early Budget | 659091.06 | 53364.91 | 53364.91 | 53364.91 | 53364.91 | 34223.15 | 23588.84 | 23588.84 | 10214.08 | 19290.7 | 19987.91 | 21285.72 | 21208.29 | 17077.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | MAT | Materials | BUDGET | Approved Early Budget | 1155349.88 | 35921.59 | 35921.59 | 35921.59 | 35921.59 | 23036.67 | 15878.38 | 15878.38 | 92084.16 | 14146.51 | 14657.8 | 15609.53 | 15552.74 | 12523.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 79.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 236893.44 | 10241.34 | 10241.34 | 10241.34 | 10241.34 | 6567.82 | 4526.97 | 4526.97 | -39492.48 | 3429.46 | 3553.41 | 3784.13 | 3770.36 | 3035.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31670 | Battersea Crossover Beams (Basement level -1) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 5270.13 | 5270.13 | 5270.13 | 5270.13 | 3379.76 | 2329.55 | 2329.55 | -23761.18 | 6001.55 | 6218.46 | 6622.22 | 6598.13 | 5312.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31671 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31672 | Battersea Crossover Concrete Mix C50/60 primary structures Level -1 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31673 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31674 | Battersea Crossover Reinforcement in situ elements over 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31675 | Battersea Crossover Reinforcement in situ elements up to 2.0 m deep | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31677 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31678 | Battersea Crossover Insitu cruciform stitch connection between precast & instu beams to top of plung | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31680 | Battersea Crossover Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31682 | Waterproofing capping beam | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31685 | Wateproofing of beams Level B01 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31686 | Protection of waterproofing in beams with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | LAB | Labour | BUDGET | Approved Early Budget | 94316.7 | 25593.23 | 25593.23 | 25593.23 | 12010.23 | 6577.03 | 6577.03 | 6577.03 | -82055.58 | 12760.25 | 13221.44 | 14079.9 | 2004.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | MAT | Materials | BUDGET | Approved Early Budget | 212160.94 | 33041.9 | 33041.9 | 33041.9 | 15505.69 | 8491.21 | 8491.21 | 8491.21 | -7964.88 | 38280.74 | 39664.3 | 42239.69 | 6012.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3229.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 32743.04 | 6970.11 | 6970.11 | 6970.11 | 3270.89 | 1791.2 | 1791.2 | 1791.2 | -30632.6 | 8256.63 | 8555.05 | 9110.52 | 1296.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31690 | Battersea Crossover Slabs(Basement level -1) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 13626.07 | 13626.07 | 13626.07 | 6394.36 | 3501.67 | 3501.67 | 3501.67 | -57777.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31691 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -1) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31692 | Battersea Crossover Concrete Mix G C50/60 primary structures Level -1 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31693 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31694 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31695 | Battersea Crossover 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31695 | Battersea Crossover 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31696 | Waterproofing system for roof slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31698 | Protection of waterproofing with red concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31698 | Protection of waterproofing with red concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31710 | Battersea Crossover Beams (Basement Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 420740.38 | 32433.33 | 32433.33 | 32433.33 | 32433.33 | 12741.67 | 0 | 0 | -163118.94 | 13124.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31710 | Battersea Crossover Beams (Basement Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 496259.47 | 64967.47 | 64967.47 | 64967.47 | 64967.47 | 25522.94 | 0 | 0 | -265134.61 | 32499.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31710 | Battersea Crossover Beams (Basement Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 112389.94 | 33796.79 | 33796.79 | 33796.79 | 33796.79 | 13277.31 | 0 | 0 | -128721.47 | 16874.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31710 | Battersea Crossover Beams (Basement Level -2) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14072.94 | 15762.66 | 16332.36 | 17392.81 | 2475.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31711 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31711 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31712 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31713 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31714 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31715 | Battersea Crossover Falsework to construct roof level in situ beams placing precast beams and stitch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31716 | Battersea Crossover Precast beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31718 | Battersea Crossover Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31719 | Battersea Crossover Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31722 | Making Good Prior to handover to MEP/Fitout | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31722 | Making Good Prior to handover to MEP/Fitout | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31723 | Saw concrete slab between GL 40 and GL41 - Subcontract | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31723 | Saw concrete slab between GL 40 and GL41 - Subcontract | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31730 | Battersea Crossover Slabs (Basement Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 39123.95 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18699.7 | 18031.85 | -108318.63 | 7936.24 | 8223.08 | 8757 | 8725.14 | 1527.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31730 | Battersea Crossover Slabs (Basement Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 139373.48 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7740.82 | 7464.36 | 269124.82 | 9258.95 | 9593.59 | 10216.5 | 10179.34 | 1781.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31730 | Battersea Crossover Slabs (Basement Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9068.9 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1574.77 | 1518.53 | -6720.16 | 1984.06 | 2055.77 | 2189.25 | 2181.28 | 381.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31730 | Battersea Crossover Slabs (Basement Level -2) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 17280.16 | 16663.02 | -54198.26 | 46956.09 | 48653.21 | 51812.24 | 51623.76 | 9036.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31731 | Battersea Crossover Provision of mass concrete mix. G and blinding (Level -2) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31732 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31733 | Battersea Crossover Formwork to form voids and joints in slabs up to 600 mm high | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31734 | Battersea Crossover Reinforcement RC slabs (Suspended Slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31735 | Battersea Crossover 75mm Pre Cast planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31735 | Battersea Crossover 75mm Pre Cast planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31738 | Standard couplers | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31739 | Exposure of couplers in beams and slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31740 | Battersea Crossover Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 218556.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2357.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31740 | Battersea Crossover Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 1215772.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78403.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31740 | Battersea Crossover Base Slab | MISC | Miscellaneous | BUDGET | Approved Early Budget | 9.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31740 | Battersea Crossover Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 45665.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31741 | Battersea Crossover Provision of mass concrete mix. G and blinding (Base level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31742 | Waterproofing system for base slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31743 | Battersea Crossover Concrete Mix C50/60 primary structures Base Level (slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31745 | Battersea Crossover Reinforcement RC Slabs (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31746 | Battersea Crossover Exposure of couplers in d-walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31748 | Formwork "in situ" elements (Beams, walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31748 | Formwork "in situ" elements (Beams, walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31749 | Standard coupler to connect beams and slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31750 | Provision of mass concrete Grade C30/40 (1st Stage Concrete) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31760 | Battersea Crossover Columns Intermediate | LAB | Labour | BUDGET | Approved Early Budget | 53222.38 | 40988.07 | 20494.03 | 0 | 0 | 0 | 731.93 | 20494.03 | -74752.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31760 | Battersea Crossover Columns Intermediate | MAT | Materials | BUDGET | Approved Early Budget | 53287.83 | 6703.45 | 3351.72 | 0 | 0 | 0 | 119.7 | 3351.72 | 2885.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31760 | Battersea Crossover Columns Intermediate | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9356.8 | 827.95 | 413.98 | 0 | 0 | 0 | 14.78 | 413.98 | 690.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31761 | Battersea Crossover Concrete Mix C50/60 primary structures Level -2 (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31762 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31763 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31764 | Battersea Crossover Precast Concrete Beam connecting to Plunge Column; to include Insitu stitch at c | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31770 | Battersea Crossover Columns Base Slab | LAB | Labour | BUDGET | Approved Early Budget | 64636.78 | 27278.62 | 27278.62 | 27278.62 | 8768.13 | 0 | 0 | 0 | -68967.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31770 | Battersea Crossover Columns Base Slab | MAT | Materials | BUDGET | Approved Early Budget | 113723.32 | 17821.97 | 17821.97 | 17821.97 | 5728.49 | 0 | 0 | 0 | -51691.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31770 | Battersea Crossover Columns Base Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 35866.07 | 1080.69 | 1080.69 | 1080.69 | 347.37 | 0 | 0 | 0 | 1356.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31770 | Battersea Crossover Columns Base Slab | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31771 | Battersea Crossover Concrete Mix C50/60 primary structures platform level (columns) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31772 | Battersea Crossover Formwork fair finish 900 x 900 Grade F2 for columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31773 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31775 | Battersea Crossover Supply and place concrete to protect columns | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31776 | Couplers for columns between B4 and B2. (Crossover) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31780 | Battersea Crossover Walls (Base Slab) | LAB | Labour | BUDGET | Approved Early Budget | 102260.18 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | 6962.6 | -49497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31780 | Battersea Crossover Walls (Base Slab) | MAT | Materials | BUDGET | Approved Early Budget | 88094.2 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | 7912.28 | -37030.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31780 | Battersea Crossover Walls (Base Slab) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22667.17 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | 1895.29 | -18643.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31781 | Battersea Crossover Concrete Mix C50/60 primary structures B4 level (beams and walls) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31782 | Battersea Crossover Formwork in situ elements (Beams walls and slabs) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31784 | Battersea Crossover Reinforcement for estructural in situ elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31789 | In situ wall connection between d-walls and tunnel eyes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31790 | Vent Shaft, Stairs and Others | LAB | Labour | BUDGET | Approved Early Budget | 13308.61 | 40370.94 | 40370.94 | 40370.94 | 12120.1 | 7411.63 | 7411.63 | 7411.63 | -82201.8 | 0 | 0 | 0 | 0 | 5348.25 | 5757.46 | 6167.98 | 5255.61 | 6277.67 | 387.4 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 12038.02 | 10748.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31790 | Vent Shaft, Stairs and Others | MAT | Materials | BUDGET | Approved Early Budget | 12028.94 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | 41611.2 | -229203.13 | 0 | 13140.54 | 17035.87 | 16973.9 | 16639.01 | 14713.51 | 15762.61 | 13431.01 | 16042.94 | 990.02 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 30763.83 | 27467.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31790 | Vent Shaft, Stairs and Others | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 26072.09 | 26072.09 | 26072.09 | 5073.71 | 1573.98 | 1573.98 | 1573.98 | 17066.88 | 0 | 3427.97 | 4444.14 | 4427.97 | 4340.61 | 3838.31 | 4111.98 | 3503.74 | 4185.11 | 258.27 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 8025.34 | 7165.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31790 | Vent Shaft, Stairs and Others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 16520.22 | 16520.22 | 16520.22 | 16520.22 | 25459.54 | 66580.39 | 66580.39 | -224701.2 | 0 | 35422.33 | 45922.78 | 45755.72 | 44852.98 | 39662.51 | 42490.51 | 36205.33 | 43246.18 | 2668.74 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 82928.59 | 74043.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31791 | Concrete Upstands to receive cladding across Station & Crossover Box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31794 | Ramp Connections between Station & Crossover Box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31795 | Vent Core GL 34-35 & Access Hatch GL 30-31 including roof slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31801 | Waterproofing of concrete in vent core and access hatch | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31802 | FUSSEY ENGINEERING - Plenum Steel | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31803 | KILNBRIDGE - Temporary Steel Structure for Vent Core | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31803 | KILNBRIDGE - Temporary Steel Structure for Vent Core | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C31805 | Making good prior to handover to BPSDC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | LAB | Labour | BUDGET | Approved Early Budget | 333453.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | MAT | Materials | BUDGET | Approved Early Budget | 675208.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | MISC | Miscellaneous | BUDGET | Approved Early Budget | 27164.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 628300.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4079.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33210 | Battersea Station Excavation temporary shoring and removal of spoil | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5280489.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33212 | Battersea Station Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33214 | Battersea Station Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33216 | Battersea Station Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33219 | Battersea Station Extra excavation sequencing & methodology to increased depth of capping beam to en | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33221 | Battersea Station allowance to import suitable fill l&c to D Wall plant tracking area (162m * 15m * | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33221 | Battersea Station allowance to import suitable fill l&c to D Wall plant tracking area (162m * 15m * | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33222 | Battersea Main Works PilingC Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33222 | Battersea Main Works PilingC Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | LAB | Labour | BUDGET | Approved Early Budget | 104368.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | MAT | Materials | BUDGET | Approved Early Budget | 441710.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4766.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 161539.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33270 | Battersea Crossover Excavation temporary shoring and removal of spoil | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1703349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33272 | Battersea Crossover Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33274 | Battersea Crossover Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C33276 | Battersea Crossover Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1695.5 | 23737.03 | 23737.03 | 23737.03 | 10173.01 | 24904.54 | 27932.12 | 28941.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1091.92 | 15286.81 | 15286.81 | 15286.81 | 6551.49 | 68612.81 | 31587.76 | 32729.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 1469.96 | 20579.39 | 20579.39 | 20579.39 | 8819.74 | -72027.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 569.37 | 7971.24 | 7971.24 | 7971.24 | 3416.25 | 4218.43 | 8307.86 | 8608.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38010 | Dwarf Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 204.08 | 2857.14 | 2857.14 | 2857.14 | 1224.49 | -9999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38012 | Drilling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38013 | Installation of Reinforcement | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38014 | Installation of Formwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38015 | Installation of Concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38016 | Scabbling | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 44321.62 | 45963.16 | 45963.16 | -1578.85 | 34834.69 | 36093.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 50453.22 | 52321.86 | 52321.86 | 92218.16 | 53367.27 | 55296.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 38425.71 | 39848.89 | 39848.89 | -118123.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 16481.72 | 17092.16 | 17092.16 | -14606.82 | 9327.39 | 9664.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38020 | Concrete Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 18089.37 | 18759.35 | 18759.35 | -55608.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38021 | Installation of Concrete for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38021 | Installation of Concrete for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38022 | Installation of Lattice Planks | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38022 | Installation of Lattice Planks | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38023 | Installation of Reinforcement for Slabs and Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38024 | Installation of Formwork for Slabs and Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38025 | Installation of Screed | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38025 | Installation of Screed | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38026 | Installation of Falsework for Beams | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 584.76 | 8186.61 | 8186.61 | 8186.61 | 3508.55 | -9629.11 | 4920.92 | 5098.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 593.62 | 8310.66 | 8310.66 | 8310.66 | 3561.71 | -6635.5 | 5807.58 | 6017.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 506.97 | 7097.58 | 7097.58 | 7097.58 | 3041.82 | -24841.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 235.97 | 3303.64 | 3303.64 | 3303.64 | 1415.85 | -7770.59 | 980.91 | 1016.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38030 | Retaining Walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 510.2 | 7142.86 | 7142.86 | 7142.86 | 3061.22 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38031 | Installation of Reinforcement | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38032 | Installation of Formwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38032 | Installation of Formwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38033 | Installation of Concrete | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729.98 | 188.82 | 195.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38040 | Bridge Build-up | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38042 | Installation of Concrete | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38050 | Drainage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578.28 | 3878.9 | 1152.93 | 1194.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6307.89 | 26303.73 | 8435.61 | 8740.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501.35 | -501.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38060 | Waterproofing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.66 | 27.85 | 28.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38061 | Installation of Horizontal Waterproofing on Deck | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38061 | Installation of Horizontal Waterproofing on Deck | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38061 | Installation of Horizontal Waterproofing on Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38062 | Waterproofing Retaining Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38063 | Installation of Vertical Waterproofing on Deck | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38064 | Movement Joint | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38070 | Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3832.73 | 991.41 | 1027.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38080 | Carriageway | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38082 | Installation of Bollards (HVM) and Baseplates | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38083 | Installation of Parapet Posts and Baseplates | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C38083 | Installation of Parapet Posts and Baseplates | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43354 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 143288.26 | 88951.9 | 0 | 0 | 0 | 0 | 0 | 0 | 211559.34 | 0 | 0 | 0 | 153156.33 | 18207.4 | 117812.56 | 214204.66 | 519446.3 | 240596.76 | 160653.49 | 48196.05 | 14000 | 14000 | 14000 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43356 | Fire Suppression | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3178.5 | 0 | 0 | 893.57 | 1530.39 | 42184.59 | 96345.31 | 50728.3 | 82921.63 | 22840.28 | 17130.21 | 15611.33 | 22078.94 | 25885.65 | 10662.6 | 1522.69 | 4948.73 | 761.34 | 3045.37 | 761.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43358 | Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9545.63 | 0 | 0 | 2683.57 | 4596.04 | 4410.96 | 50734.02 | 84059.73 | -24545.56 | 10402.91 | 129563.55 | 103083.41 | 40665.93 | 56506.73 | 86779.21 | 100851.51 | 88784.13 | 89370.48 | 81568.29 | 56033.87 | 47285.97 | 19860.11 | 5201.46 | 1472.86 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43360 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 31144.12 | 15572.06 | 18975.31 | 35768.26 | 35768.26 | 35768.26 | 35768.26 | 49860.24 | 140918.15 | 5044.11 | 78183.75 | 189154.24 | 172760.88 | 137452.08 | 154955.16 | 549669.62 | 197666.18 | 173391.39 | 145648.77 | 337325.07 | 298863.7 | 208069.67 | 143126.71 | 102773.81 | 6305.14 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 2003.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43362 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 52628.76 | 113354.25 | 113354.25 | -234259.85 | 34234.88 | 124633.6 | 96591.04 | 213576.66 | 208194.76 | 190491.12 | 115427.71 | 39656.14 | 708.15 | 13454.76 | 43196.87 | 25493.24 | 2832.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43362 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 32821.52 | 70692.5 | 91293.11 | 88278.15 | 102824.2 | 182604.47 | 234109.83 | 314871.65 | 314611.7 | 288006.1 | 186287.37 | 87880.64 | 3465.34 | 21950.09 | 133930.34 | 106679.28 | 55170.85 | 26463.89 | 46473.18 | 18072.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43364 | Escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 172973.45 | 0 | 0 | 0 | 0 | 0 | 2444120.55 | 0 | 0 | 47957.76 | 319718.43 | 319718.43 | 303732.51 | 379665.63 | 439612.84 | 407641 | 59947.21 | 119894.41 | 119894.41 | 119894.41 | 107904.97 | 113899.69 | 17984.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43366 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 78495.28 | 0 | 0 | 0 | 0 | 134177.35 | 174202.71 | -36701.61 | 0 | 329893.16 | 329893.16 | 0 | 0 | 59105.86 | 73309.59 | 73309.59 | 73309.59 | 32531.13 | 0 | 134706.37 | 235965.24 | 65978.63 | 69644.11 | 69644.11 | 73309.59 | 47193.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43369 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 10830 | 0 | 40551.74 | 58666.94 | 58666.94 | 58666.94 | 94751.4 | 268462.29 | -70850.09 | 234634.39 | 360403.87 | 968774.77 | 622236.13 | 823754.69 | 603738.46 | 489015.25 | 215783.21 | 230474.83 | 77590.13 | 101004.91 | 112482.74 | 45911.32 | 8493.59 | 12625.61 | 0 | 0 | 16528.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43369 | M&E Labour | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43369 | M&E Labour | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43370 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9796.34 | 0 | 1853.58 | 1853.58 | 3442.36 | 4501.54 | 4766.34 | 13504.62 | 31677.97 | 10262.82 | 15763.93 | 42373.86 | 27216.38 | 36030.73 | 26407.3 | 21389.35 | 9438.28 | 10080.88 | 3393.76 | 4417.92 | 4919.95 | 2008.14 | 371.51 | 552.24 | 0 | 0 | 722.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43371 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 9731.1 | 8058.7 | 9731.1 | 16117.4 | 35374.19 | 131912.7 | 137751.7 | 148438.12 | -297201.3 | 129426.06 | 198801.43 | 534383.3 | 343230.03 | 454389.16 | 333026.58 | 526450.11 | 232301.74 | 248118.03 | 83529.77 | 108736.98 | 121093.46 | 49425.9 | 9143.79 | 13592.12 | 0 | 0 | 9117.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43371 | M&E Material | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43371 | M&E Material | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43372 | M&E Subcontractor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43372 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 43959.55 | 291.47 | 108.02 | 0 | 0 | 17371.31 | 16272.91 | 24281.48 | 78125.96 | 80220.64 | 118771.23 | 132173.83 | 202088.18 | 14069.43 | 40929.25 | 170597.7 | 186381.11 | 54814.28 | 17906.55 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43600 | Floor finishes | LAB | Labour | BUDGET | Approved Early Budget | 6795.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6738.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43600 | Floor finishes | MAT | Materials | BUDGET | Approved Early Budget | 41516.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41578.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43600 | Floor finishes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 107.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43600 | Floor finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 24875.09 | 24875.09 | 0 | 0 | 0 | 102518 | 128148 | -156528.34 | 143372.63 | 135039.47 | 86977.2 | 92624.59 | 64200.36 | 62933.71 | 55650.91 | 59618.9 | 73024.84 | 87225.98 | 5382.75 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 325640.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43601 | Station Box Underplatform level - Concrete subbase 200mm | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43601 | Station Box Underplatform level - Concrete subbase 200mm | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43601 | Station Box Underplatform level - Concrete subbase 200mm | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43604 | Back of House BoH floor screeds | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43606 | Front of House FoH Stone flooring and bedding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43608 | Floor Concrete Plinths for M&E Equipments | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43610 | Wall finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43610 | Wall finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 95166 | 190333 | 162386.92 | 203667.8 | 302974.42 | 391482.6 | 499494.21 | 497677.19 | 487858.18 | 360068.75 | 385742.16 | 328683.32 | 392602.38 | 24227.67 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 703134.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43611 | Double coat of Paint to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43612 | Concrete sealant to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43614 | Station Box - FoH cladding (Stainless steel cladding to walls and columns, Stainless steel skirting | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43615 | Station Box - GRC cladding to walls, columns, escalators walls, beams | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43620 | Ceiling finishes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43620 | Ceiling finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49506.86 | 10607.2 | 22595.8 | 26990 | 3331.13 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 78209.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43621 | Concrete sealant to soffits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43621 | Concrete sealant to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43622 | Back of House BoH soffit insulation and grid ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43630 | Metalwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43630 | Metalwork | MAT | Materials | BUDGET | Approved Early Budget | 45193.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43658.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43630 | Metalwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43630 | Metalwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14820.38 | 14766.46 | 14475.13 | 32001.2 | 34282.93 | 46738.63 | 69784.46 | 6459.67 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 75829.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43633 | Crossover box plenum steelwork, lifting beams, and windposts for CMS | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43640 | SOR control desk and fit out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465.89 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 30563.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43650 | Install furniture, fixtures and fittings, including seatings, advertisements, signage and others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23013.51 | 19609.36 | 46844.8 | 2890.81 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 69868.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43653 | BoH office furniture | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43660 | Internal blockwork, Durasteel, Drywalling and acoustic cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 333545.86 | 126845.33 | 126845.33 | 126845.33 | 126843 | 126843 | 338247 | 394622 | 970810.42 | 216461.4 | 268141.51 | 277832.86 | 295872.42 | 266552.52 | 261293.53 | 218814.24 | 195073.88 | 121521.09 | 98437.08 | 10604.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43661 | Acoustic wall lining Wall type E24 - West core shafts, East Vent shaft, gridline 41 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43662 | Durasteel - Wal ltypes G20, G21, Fire rated ceiling 01 & 02. Located in MainBox all levels and Cross | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43665 | Internal blockwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43670 | Internal doors | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8385.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43670 | Internal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49753.61 | 51551.84 | 137248.53 | 136749.26 | 268102.48 | 237077.2 | 253981.14 | 216412.34 | 258498.05 | 15952.03 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 143200.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43674 | Intenal slab access hatches. Aver 1m*2m. 6nr | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43680 | Firestopping & BWIC | MAT | Materials | BUDGET | Approved Early Budget | 610.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -328.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43680 | Firestopping & BWIC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4866.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43680 | Firestopping & BWIC | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 37170 | 37170 | -40035.41 | 50985.73 | 57107.52 | 116967.09 | 155335.37 | 185432.87 | 181774.34 | 160739.11 | 143725.6 | 73941.43 | 59340.79 | 1873.53 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 39695.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43681 | Firestopping: BWO, lifts, escalators, other firestopping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43690 | External Cladding & Roofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 48381.26 | 0 | 0 | 0 | 0 | 0 | 214176 | 214176 | 1155556.8 | 269004.66 | 301303.67 | 312193.58 | 332464.17 | 331254.75 | 324719.21 | 287142.15 | 307615.78 | 136754.77 | 163349.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43691 | Eastern Headhouse envelope | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43695 | East Vent shaft cladding, roof, louvres and external doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C43696 | West core cladding, roof, louvres and external doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C53400 | Completion of landscaping paving external areas and the like | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C53400 | Completion of landscaping paving external areas and the like | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 108915.77 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C63504 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9241.51 | 9241.51 | 9241.51 | 9241.51 | 9241.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C63506 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 20031.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C63508 | Station Ventilation | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 48739.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 99993037.43 | 2500133.97 | 2558951.12 | 2380183.01 | 2271835.67 | 2721288.48 | 3755956.45 | 4031021.84 | 1232101.02 | 3230759.89 | 4279703.18 | 5521935.06 | 5540892.1 | 5420174.22 | 5194713.68 | 5580519.94 | 5345993.33 | 3395873.72 | 2792340.94 | 2127569.6 | 3589742.35 | 3408154.07 | 3032880.12 | 3105819.33 | 2851723.7 | 2859043.49 | 2878087.29 | 3106198.74 | 2259989.51 | 762400.49 | 740086.17 | 816642.91 | 615207.22 | 359620.95 | 309736.68 | 878733.58 | 402484.82 | 157021.87 | 5747.77 | 442.14 | 0 | 6105.54 | 6105.54 | 6105.54 | 0 | 0 | 0 | 0
|  |  |  | C | STAFF | 7242847.82 | 254552.63 | 262808.58 | 274341.07 | 302876.48 | 323410.92 | 303149 | 293504.81 | -493315.55 | 209932 | 209932 | 198127 | 196132 | 196132 | 196132 | 196132 | 193186 | 159927 | 155812 | 155812 | 155812 | 207626.52 | 207626.52 | 207626.52 | 207626.52 | 205803.42 | 201549.52 | 152938 | 152938 | 152938 | 152938 | 152938 | 150938 | 52938 | 52938 | 30938 | 32938 | 30938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 15168620.68 | 611897.27 | 626952.17 | 631415.12 | 601100.92 | 582599.76 | 582609.66 | 736750.62 | -345728.76 | 702221.71 | 833425.15 | 1397240.11 | 1035280.52 | 1223196.84 | 932603.3 | 827436.7 | 528985.24 | 451847.92 | 133127.58 | 482119.11 | 493596.94 | 427025.52 | 389607.79 | 393739.81 | 381114.2 | 381114.2 | 458151.65 | 520402.68 | 337810.42 | 251271.82 | 157212.78 | 143612.47 | 143612.47 | 143612.47 | 143612.47 | 143612.47 | 143612.47 | 45490.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 8281792.65 | 392966.71 | 394619.25 | 411120.17 | 381771.49 | 360199.12 | 435570.58 | 374732.13 | -804190.64 | 227418.35 | 168780.29 | 204685.65 | 170659.63 | 171393.76 | 122160.17 | 173827.48 | 95082.96 | 81783.76 | 7802.93 | 141234.04 | 167820.15 | 164908.34 | 137187.63 | 137368.36 | 130903.59 | 152180.81 | 161129.28 | 217440.42 | 56149.86 | 50485.44 | 38245.84 | 41311.88 | 31109.72 | 26277.11 | 26277.11 | 26277.11 | 26277.11 | 8346.07 | 0 | 0 | 0 | 5912.52 | 5912.52 | 5912.52 | 0 | 0 | 0 | 0
[5 empty] | MAT | 18902754.88 | 502213.83 | 515464.39 | 516785.89 | 529174.41 | 658844.61 | 714752.22 | 713462.41 | -1019522.45 | 562864.78 | 684102.79 | 896539.23 | 768773.79 | 854924.27 | 679749.29 | 788489.01 | 432689.12 | 318938.94 | 102509.52 | 273729.76 | 268382.61 | 174054.39 | 154834.09 | 128887.16 | 115102.02 | 162890.81 | 195968.07 | 151654.23 | 9304.04 | 9063.12 | 8629.48 | 8629.48 | 8629.48 | 8629.48 | 8629.48 | 8629.48 | 8629.48 | 2410.42 | 0 | 0 | 0 | 193.02 | 193.02 | 193.02 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 46243832.53 | 709009.71 | 730924.98 | 513864.25 | 390017.25 | 680747.48 | 1595717.42 | 1805979.15 | 3922016.88 | 1494956.15 | 2345690.04 | 2774769.63 | 3325681.32 | 2927673.95 | 3224738.83 | 3556913.33 | 4074370.45 | 2358401.23 | 2390707.44 | 1050266.38 | 2479749.98 | 2411280.53 | 2120995.91 | 2215499.67 | 1994492.33 | 1934569.21 | 1839024.79 | 2042268.36 | 1677926.49 | 271539.57 | 360378.89 | 453880.88 | 265973.76 | 117641.46 | 68641.46 | 659638.36 | 181389.6 | 60767.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 3348148.51 | 0 | 0 | 1976.93 | 27676.97 | 66102.68 | 67525.86 | 52211.8 | 107417.93 | 9220.61 | 9627.73 | 10252.85 | 10215.56 | 10014.01 | 8855.17 | 8865.14 | 670.37 | 800.75 | 49.42 | 1535.5 | 1535.5 | 1535.5 | 1535.5 | 1535.5 | 1535.5 | 1535.5 | 1535.5 | 1429.78 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 795.43 | 227.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 805040.36 | 29493.82 | 28181.75 | 30679.58 | 39218.15 | 49383.91 | 56631.71 | 54380.92 | -134576.39 | 24146.29 | 28145.18 | 40320.59 | 34149.28 | 36839.39 | 30474.92 | 28856.28 | 21009.19 | 24174.12 | 2332.05 | 22872.81 | 22845.17 | 21723.27 | 21092.68 | 21162.31 | 20949.54 | 20949.54 | 20728.48 | 20065.27 | 25065.27 | 26307.11 | 21885.75 | 15474.77 | 14148.36 | 9727 | 8842.73 | 8842.73 | 8842.73 | 8842.73 | 5747.77 | 442.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 99993037.43 | 2500133.97 | 2558951.12 | 2380183.01 | 2271835.67 | 2721288.48 | 3755956.45 | 4031021.84 | 1232101.02 | 3230759.89 | 4279703.18 | 5521935.06 | 5540892.1 | 5420174.22 | 5194713.68 | 5580519.94 | 5345993.33 | 3395873.72 | 2792340.94 | 2127569.6 | 3589742.35 | 3408154.07 | 3032880.12 | 3105819.33 | 2851723.7 | 2859043.49 | 2878087.29 | 3106198.74 | 2259989.51 | 762400.49 | 740086.17 | 816642.91 | 615207.22 | 359620.95 | 309736.68 | 878733.58 | 402484.82 | 157021.87 | 5747.77 | 442.14 | 0 | 6105.54 | 6105.54 | 6105.54 | 0 | 0 | 0 | 0 | 202033064.47
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8626e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## D
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
D08400 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 653334.02 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 27784.35 | 82649.13 | 28011.5 | 26239.85 | 26239.85 | 26239.85 | 26491.92 | 26491.92 | 24986.73 | 24543.82 | 23910.06 | 23910.06 | 22390.48 | 22390.48 | 21839.54 | 20953.71 | 18080.18 | 16589.41 | 13298.17 | 9531.62 | 8346.92 | 7461.09 | 7461.09 | 7461.09 | 4976.46 | 3471.28 | 2369.4 | 2369.4 | 2369.4 | 1735.64 | 1735.64 | 1101.88 | 1101.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D08410 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 1093.04 | 656.04 | 656.04 | 874.71 | 3280.18 | 3280.18 | 6560.36 | 21695.54 | 4236.58 | 7673.52 | 5801.34 | 12561.12 | 12486.97 | 7324.78 | 7529.97 | 6344.71 | 3558.46 | 1145.81 | 1186.15 | 306.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | LAB | Labour | BUDGET | Approved Early Budget | 1957.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | MAT | Materials | BUDGET | Approved Early Budget | -14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09999 | Nine Elms Temporary code (to be reconciled periodically) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14000 | General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 7.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14000 | General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | -75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14000 | General management & Supervision | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 696.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14000 | General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 4575922.27 | 162080 | 165695 | 167505 | 170945 | 170945 | 172695 | 172695 | 132723.08 | 179471.73 | 168120.64 | 168120.64 | 168120.64 | 169735.63 | 169735.63 | 160091.83 | 157254.06 | 153193.5 | 153193.5 | 143457.41 | 143457.41 | 139927.5 | 134251.96 | 115841.05 | 106289.53 | 85202.35 | 61069.76 | 53479.3 | 47803.76 | 47803.76 | 47803.76 | 31884.55 | 22240.74 | 15180.92 | 15180.92 | 15180.92 | 11120.37 | 11120.37 | 7059.82 | 7059.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14000 | General management & Supervision | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | 1398.21 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | 393.19 | -2752.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 23654.43 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 593.34 | 4662.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 225603.57 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | 12796.82 | -25868.85 | 27085.37 | 27085.37 | 27085.37 | 27085.37 | 23699.7 | 23699.7 | 13542.69 | 13542.69 | 13542.69 | 10157.02 | 10157.02 | 10157.02 | 10157.02 | 10157.02 | 6771.34 | 6771.34 | 6771.34 | 6771.34 | 6771.34 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 99131.1 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 827.68 | 10113.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 372543.42 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 7821.38 | 137356.97 | 19384.82 | 19384.82 | 19384.82 | 19384.82 | 16961.72 | 16961.72 | 9692.41 | 9692.41 | 9692.41 | 7269.31 | 7269.31 | 7269.31 | 7269.31 | 7269.31 | 4846.21 | 4846.21 | 4846.21 | 4846.21 | 4846.21 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 2423.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 292622.25 | 8315.58 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 11641.81 | 18538.37 | 12800 | 12800 | 12800 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 18300 | 14300 | 14300 | 14300 | 14300 | 14300 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 21244.38 | 1610.83 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | 2255.17 | -9496.22 | 2672 | 2672 | 2672 | 2672 | 2338 | 2338 | 2338 | 2338 | 2004 | 1002 | 1002 | 1002 | 1002 | 1002 | 668 | 334 | 334 | 334 | 334 | 334 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 560996.23 | 4433 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | 6206.2 | -13052.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23531.23 | 2059.05 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 2882.66 | 41828.08 | 3383.67 | 3383.67 | 3383.67 | 3383.67 | 2960.71 | 2960.71 | 2960.71 | 2960.71 | 2537.75 | 1268.88 | 1268.88 | 1268.88 | 1268.88 | 1268.88 | 845.92 | 422.96 | 422.96 | 422.96 | 422.96 | 422.96 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 211.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15178.92 | 15178.92 | 15178.92 | 15178.92 | 15178.92 | 13281.56 | 13281.56 | 13281.56 | 13281.56 | 11384.19 | 5692.1 | 5692.1 | 5692.1 | 5692.1 | 5692.1 | 3794.73 | 1897.37 | 1897.37 | 1897.37 | 1897.37 | 1897.37 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 948.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 14151.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14026 | IT Equipment & running costs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | 202.35 | -1416.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 34186.23 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | 1007.1 | -1026.08 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 143.62 | 100.54 | 100.54 | 100.54 | 64.63 | 64.63 | 64.63 | 64.63 | 14.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -98.65 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 622 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 91.92 | 64.35 | 64.35 | 64.35 | 41.36 | 41.36 | 41.36 | 41.36 | 9.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14026 | IT Equipment & running costs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | 426.13 | -2207.79 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 775.13 | 542.59 | 542.59 | 542.59 | 348.81 | 348.81 | 348.81 | 348.81 | 77.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14026 | IT Equipment & running costs | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2980.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14028 | Environmental Control | LAB | Labour | BUDGET | Approved Early Budget | 33160.18 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 448.32 | 36746.45 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 8696.19 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | 332.99 | -1222.37 | 422.21 | 422.21 | 422.21 | 422.21 | 375.3 | 375.3 | 187.65 | 187.65 | 140.74 | 140.74 | 140.74 | 140.74 | 117.28 | 93.83 | 93.83 | 93.83 | 93.83 | 93.83 | 46.91 | 46.91 | 46.91 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 23.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 22556.09 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | 1323.31 | -7495.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 53172.82 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 605.39 | 9174.04 | 2867.28 | 2867.28 | 2867.28 | 2867.28 | 2548.69 | 2548.69 | 1274.35 | 1274.35 | 955.76 | 955.76 | 955.76 | 955.76 | 796.47 | 637.17 | 637.17 | 637.17 | 637.17 | 637.17 | 318.59 | 318.59 | 318.59 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 159.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 166967.53 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 855.17 | 4225.12 | 3719.57 | 3719.57 | 3719.57 | 3719.57 | 3306.29 | 3306.29 | 1653.14 | 1653.14 | 1239.86 | 1239.86 | 1239.86 | 1239.86 | 1033.22 | 826.57 | 826.57 | 826.57 | 826.57 | 826.57 | 413.29 | 413.29 | 413.29 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 206.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 1202.17 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | 444.22 | -3109.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 9028.02 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | 197.69 | -30509.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 120889.6 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 335.63 | 104304.57 | 16744.95 | 16744.95 | 16744.95 | 16744.95 | 14884.4 | 14884.4 | 7442.2 | 7442.2 | 5581.65 | 5581.65 | 5581.65 | 5581.65 | 4651.38 | 3721.1 | 3721.1 | 3721.1 | 3721.1 | 3721.1 | 1860.55 | 1860.55 | 1860.55 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 930.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2590 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | 7846.3 | -54924.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14036 | General Logistics | LAB | Labour | BUDGET | Approved Early Budget | 533174.93 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 13604.15 | 55828.76 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14036 | General Logistics | MAT | Materials | BUDGET | Approved Early Budget | 219743.45 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | 3484.99 | -14357.16 | 8341.63 | 8341.63 | 8341.63 | 8341.63 | 7414.78 | 7414.78 | 3707.39 | 3707.39 | 2780.54 | 2780.54 | 2780.54 | 2780.54 | 2317.12 | 1853.7 | 1853.7 | 1853.7 | 1853.7 | 1853.7 | 926.85 | 926.85 | 926.85 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 463.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14036 | General Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17382.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14036 | General Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 109664.35 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 1616.01 | 2256.92 | 6074.19 | 6074.19 | 6074.19 | 6074.19 | 5399.28 | 5399.28 | 2699.64 | 2699.64 | 2024.73 | 2024.73 | 2024.73 | 2024.73 | 1687.28 | 1349.82 | 1349.82 | 1349.82 | 1349.82 | 1349.82 | 674.91 | 674.91 | 674.91 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 337.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14036 | General Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 112118.84 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | 4300.07 | -26600.52 | 3499.97 | 3499.97 | 3499.97 | 3499.97 | 3111.09 | 3111.09 | 1555.54 | 1555.54 | 1166.66 | 1166.66 | 1166.66 | 1166.66 | 972.22 | 777.77 | 777.77 | 777.77 | 777.77 | 777.77 | 388.89 | 388.89 | 388.89 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 194.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 871232.29 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 25001.06 | 16714.62 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 18200 | 18200 | 18200 | 18200 | 18200 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 1691.91 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 115.77 | 2277.39 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 249.13 | 171.28 | 171.28 | 171.28 | 171.28 | 171.28 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 86.68 | 65.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 17992 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 1005.25 | 10703.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 147.5 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | 1715.88 | -9793.1 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 2035.06 | 1399.1 | 1399.1 | 1399.1 | 1399.1 | 1399.1 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 708.03 | 538.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 27135 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 192.04 | 1747.32 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 351.6 | 241.73 | 241.73 | 241.73 | 241.73 | 241.73 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 122.33 | 93.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14040 | Plant & Equipment | LAB | Labour | BUDGET | Approved Early Budget | 8904.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14040 | Plant & Equipment | MISC | Miscellaneous | BUDGET | Approved Early Budget | -560.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14040 | Plant & Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -3696.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14042 | Materials Handling Plant | LAB | Labour | BUDGET | Approved Early Budget | 40806.26 | 2306.58 | 2306.58 | 2306.58 | 3459.87 | 3459.87 | 4613.15 | 4613.15 | 12577.56 | 10400 | 10400 | 10400 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14042 | Materials Handling Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 47.16 | 47.16 | 47.16 | 70.74 | 70.74 | 94.32 | 94.32 | -471.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14042 | Materials Handling Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1101.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14042 | Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 45515.56 | 735.5 | 735.5 | 735.5 | 1103.25 | 1103.25 | 1471 | 1471 | 13133.73 | 2167.07 | 2167.07 | 2167.07 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1073.22 | 1066.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14044 | Craneage | LAB | Labour | BUDGET | Approved Early Budget | 489573.34 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 48405.6 | 41490.51 | 1751.53 | 41400 | 17200 | 17200 | 23200 | 11700 | 17700 | 17200 | 17700 | 11700 | 23200 | 11700 | 17700 | 17200 | 17700 | 11700 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14044 | Craneage | MAT | Materials | BUDGET | Approved Early Budget | 90026.08 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1500 | 6926.04 | 2687.5 | 1117.5 | 1117.5 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 1070 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14044 | Craneage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14044 | Craneage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 947633.1 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 44255.05 | 37932.9 | 133484.79 | 14727.5 | 6123.9 | 6123.9 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 5863.6 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1945.4 | 1589.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14044 | Craneage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 411.31 | 411.31 | 411.31 | 411.31 | 411.31 | 411.31 | 352.56 | -1745.42 | 1075 | 447 | 447 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 428 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14046 | Passenger/Goods Hoists | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 3571.32 | 66474.22 | 4600 | 4600 | 4600 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14046 | Passenger/Goods Hoists | MISC | Miscellaneous | BUDGET | Approved Early Budget | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14046 | Passenger/Goods Hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 178 | 0 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 5605.27 | 33179.43 | 3789.33 | 3789.33 | 3789.33 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 8521.19 | 9069.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14048 | General Plant | LAB | Labour | BUDGET | Approved Early Budget | 788 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | 422.67 | -2958.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14048 | General Plant | MAT | Materials | BUDGET | Approved Early Budget | 79.35 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 211.33 | 1559.43 | 134.27 | 134.27 | 134.27 | 134.27 | 119.35 | 119.35 | 59.68 | 59.68 | 44.76 | 44.76 | 44.76 | 44.76 | 37.3 | 29.84 | 29.84 | 29.84 | 29.84 | 29.84 | 14.92 | 14.92 | 14.92 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 7.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14048 | General Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8492.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14048 | General Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 172973.71 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 6687.92 | 81915.26 | 8971.35 | 8971.35 | 8971.35 | 8971.35 | 7974.53 | 7974.53 | 3987.26 | 3987.26 | 2990.45 | 2990.45 | 2990.45 | 2990.45 | 2492.04 | 1993.63 | 1993.63 | 1993.63 | 1993.63 | 1993.63 | 996.82 | 996.82 | 996.82 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 498.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14048 | General Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | 2749.6 | -15932.95 | 3314.25 | 3314.25 | 3314.25 | 3314.25 | 2946 | 2946 | 1473 | 1473 | 1104.75 | 1104.75 | 1104.75 | 1104.75 | 920.63 | 736.5 | 736.5 | 736.5 | 736.5 | 736.5 | 368.25 | 368.25 | 368.25 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 184.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 204906.3 | 13794.56 | 13794.56 | 13794.56 | 13794.56 | 13794.56 | 17243.21 | 17243.21 | 38689.02 | 22600 | 22600 | 22600 | 37100 | 37100 | 37100 | 37100 | 37100 | 31900 | 31900 | 31900 | 31900 | 31900 | 26700 | 21500 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | 2760.06 | 369.78 | 369.78 | 369.78 | 369.78 | 369.78 | 462.23 | 462.23 | -2648.88 | 124.48 | 124.48 | 124.48 | 204.25 | 204.25 | 204.25 | 204.25 | 204.25 | 175.54 | 175.54 | 175.54 | 175.54 | 175.54 | 146.84 | 118.13 | 98.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225240.44 | 6911.92 | 6911.92 | 6911.92 | 6911.92 | 6911.92 | 8639.89 | 8639.89 | -2153.62 | 3065.23 | 3065.23 | 3065.23 | 5029.43 | 5029.43 | 5029.43 | 5029.43 | 5029.43 | 4322.59 | 4322.59 | 4322.59 | 4322.59 | 4322.59 | 3615.75 | 2908.91 | 2419.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14062 | Concrete, Soil and Water testing | LAB | Labour | BUDGET | Approved Early Budget | 0 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 2559.28 | 12877.57 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14062 | Concrete, Soil and Water testing | MAT | Materials | BUDGET | Approved Early Budget | 480.94 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | 275.04 | -1853.13 | 72.15 | 72.15 | 72.15 | 72.15 | 72.15 | 48.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14062 | Concrete, Soil and Water testing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 33343.48 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | 2616.37 | -8869.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14062 | Concrete, Soil and Water testing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3320.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055.26 | 701.18 | 701.18 | 701.18 | 701.18 | 701.18 | 467.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14062 | Concrete, Soil and Water testing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 4533.18 | 3022.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14064 | PPE and the like | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14064 | PPE and the like | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24491.86 | 7514.1 | 7514.1 | 7514.1 | 7514.1 | 6679.2 | 6679.2 | 3339.6 | 3339.6 | 2504.7 | 2504.7 | 2504.7 | 2504.7 | 2087.25 | 1669.8 | 1669.8 | 1669.8 | 1669.8 | 1669.8 | 834.9 | 834.9 | 834.9 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 417.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14064 | PPE and the like | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 162126.67 | 3834 | 3834 | 3834 | 3834 | 3834 | 3834 | 3834 | 27104.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14066 | Signage | MAT | Materials | BUDGET | Approved Early Budget | 4946.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | 317.5 | -1531.51 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 640.99 | 427.33 | 213.66 | 213.66 | 213.66 | 213.66 | 106.83 | 106.83 | 106.83 | 53.42 | 53.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14066 | Signage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 345.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14068 | Fuel and Tanks | MAT | Materials | BUDGET | Approved Early Budget | 123447.07 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | 6472.5 | -30109.23 | 7985.25 | 7985.25 | 7985.25 | 7985.25 | 7098 | 7098 | 3549 | 3549 | 2661.75 | 2661.75 | 2661.75 | 2661.75 | 2218.13 | 1774.5 | 1774.5 | 1774.5 | 1774.5 | 1774.5 | 887.25 | 887.25 | 887.25 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 443.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14068 | Fuel and Tanks | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17399.47 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 736.76 | 3836.33 | 1136.55 | 1136.55 | 1136.55 | 1136.55 | 1010.26 | 1010.26 | 505.13 | 505.13 | 378.85 | 378.85 | 378.85 | 378.85 | 315.71 | 252.57 | 252.57 | 252.57 | 252.57 | 252.57 | 126.28 | 126.28 | 126.28 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 63.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14072 | Haul road maintenance works, road sweeping and jet washing | LAB | Labour | BUDGET | Approved Early Budget | 8030.4 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | 1937.77 | -8666.82 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14072 | Haul road maintenance works, road sweeping and jet washing | MAT | Materials | BUDGET | Approved Early Budget | 12380.71 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | 968.77 | -5763.85 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 408.53 | 366.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14072 | Haul road maintenance works, road sweeping and jet washing | MISC | Miscellaneous | BUDGET | Approved Early Budget | -470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14072 | Haul road maintenance works, road sweeping and jet washing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 185586.05 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 5238.62 | 24234.4 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 6613.65 | 5940.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14072 | Haul road maintenance works, road sweeping and jet washing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14074 | Temporary works for Logistics and further site surveys (no utilities) | LAB | Labour | BUDGET | Approved Early Budget | 36273.46 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 2953.29 | 18293.46 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 9000 | 9000 | 4800 | 4800 | 4800 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14074 | Temporary works for Logistics and further site surveys (no utilities) | MAT | Materials | BUDGET | Approved Early Budget | 46778.06 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | 3713.46 | -15366.16 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 2913.58 | 3800.61 | 3800.61 | 2026.56 | 2026.56 | 2026.56 | 2026.56 | 2421.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14074 | Temporary works for Logistics and further site surveys (no utilities) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14074 | Temporary works for Logistics and further site surveys (no utilities) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 15277.84 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 1275.12 | 6598.71 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 674.55 | 879.92 | 879.92 | 469.19 | 469.19 | 469.19 | 469.19 | 560.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14076 | Site supervision | LAB | Labour | BUDGET | Approved Early Budget | 480913.63 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 36027.04 | 76513.18 | 66400 | 52800 | 52800 | 40400 | 40400 | 34000 | 34000 | 34000 | 34000 | 27200 | 27200 | 20800 | 20800 | 20800 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14076 | Site supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 540.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14078 | Assets Temporary Protection | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 5880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14078 | Assets Temporary Protection | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14078 | Assets Temporary Protection | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 12880 | 9940 | 9940 | 6580 | 6580 | 6580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 3680.63 | 2836.9 | 2836.9 | 1883.11 | 1883.11 | 1874.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14080 | LU 16 Attendances / Enabling Phase 3, 4 & 5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1840.31 | 1418.45 | 1418.45 | 941.56 | 941.56 | 937.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D14666 | Small Plant | MAT | Materials | BUDGET | Approved Early Budget | 10.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | MAT | Materials | BUDGET | Approved Early Budget | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24102 | Phase 1: Boiler House + Covent Garden Market Association Offices | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 246438.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24104 | Phase 2: Banham House | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24104 | Phase 2: Banham House | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 121636.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24122 | General | LAB | Labour | BUDGET | Approved Early Budget | 11812.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24122 | General | MAT | Materials | BUDGET | Approved Early Budget | 1132.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24122 | General | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 191.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24124 | Water Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24128 | Other Utilities | LAB | Labour | BUDGET | Approved Early Budget | 17327.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24128 | Other Utilities | MAT | Materials | BUDGET | Approved Early Budget | 9858.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24128 | Other Utilities | MISC | Miscellaneous | BUDGET | Approved Early Budget | 62681.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24128 | Other Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 279.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24128 | Other Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | MISC | Miscellaneous | BUDGET | Approved Early Budget | 317425.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3325 | 0 | 0 | 0 | 0 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 9509.25 | 4754.63 | 4754.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24130 | Utilities Permanent Connections | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24132 | Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 25433.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D24132 | Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34212 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 37067.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34212 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 71244.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34212 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 537154.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34214 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 441985.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -469.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34214 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 15303.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6423.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34214 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 377258.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171409.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34214 | Excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 29102.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34216 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 12807.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34216 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 3045857.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34216 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 4195.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34216 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5503.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34216 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 953127.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34222 | Piling | LAB | Labour | BUDGET | Approved Early Budget | 423227.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34222 | Piling | MAT | Materials | BUDGET | Approved Early Budget | 1535457.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34222 | Piling | MISC | Miscellaneous | BUDGET | Approved Early Budget | 35174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34222 | Piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 338148.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6663.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34222 | Piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 17661220.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34224 | Ground Floor Level | LAB | Labour | BUDGET | Approved Early Budget | 64081.97 | 0 | 33922.39 | 67844.77 | 56537.31 | 33922.39 | 33922.39 | 0 | -16352.54 | 10308.75 | 5154.38 | 5154.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34224 | Ground Floor Level | MAT | Materials | BUDGET | Approved Early Budget | 130027.37 | 0 | 68947.03 | 137894.05 | 114911.71 | 68947.03 | 68947.03 | 0 | 3545.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34224 | Ground Floor Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10855.24 | 0 | 10865.58 | 21731.16 | 18109.3 | 10865.58 | 10865.58 | 0 | 11530.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34226 | B1 Slab Level | LAB | Labour | BUDGET | Approved Early Budget | 224715.2 | 30043.65 | 40058.2 | 25036.38 | 5007.28 | 0 | 0 | 0 | -8827.8 | 12520.82 | 6260.41 | 6260.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34226 | B1 Slab Level | MAT | Materials | BUDGET | Approved Early Budget | 370950.64 | 28879.15 | 38505.53 | 24065.95 | 4813.19 | 0 | 0 | 0 | 41769.66 | 3982.2 | 1991.1 | 1991.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34226 | B1 Slab Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 50447.93 | 7048.17 | 9397.56 | 5873.48 | 1174.7 | 0 | 0 | 0 | 70251.12 | 3394.87 | 1697.44 | 1697.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34228 | B2 Slab Level | LAB | Labour | BUDGET | Approved Early Budget | 199788.68 | 30485.6 | 0 | 0 | 0 | 0 | 0 | 0 | 9899.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34228 | B2 Slab Level | MAT | Materials | BUDGET | Approved Early Budget | 327992.29 | 28685.23 | 0 | 0 | 0 | 0 | 0 | 0 | -25923.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34228 | B2 Slab Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23737.42 | 13653.26 | 0 | 0 | 0 | 0 | 0 | 0 | -3905.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34228 | B2 Slab Level | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34230 | Base Slabs | LAB | Labour | BUDGET | Approved Early Budget | 872782.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38462.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34230 | Base Slabs | MAT | Materials | BUDGET | Approved Early Budget | 2477882.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25985.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34230 | Base Slabs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 102473.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34230 | Base Slabs | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34232 | Roof Slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 90350.84 | 108421 | 95870.63 | 158446.94 | 79223.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34232 | Roof Slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 178274.57 | 213929.48 | 150572.54 | 190499.72 | 95249.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34232 | Roof Slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 33103.49 | 39724.19 | 886.73 | 57737.61 | 28868.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34234 | Columns - all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 359124.46 | 34987.66 | 40818.94 | 29156.38 | 11662.55 | 0 | 0 | 0 | -20656.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34234 | Columns - all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 483596.01 | 24194.83 | 28227.31 | 20162.36 | 8064.94 | 0 | 0 | 0 | -12742.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34234 | Columns - all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 30118.26 | 16423.63 | 19160.91 | 13686.36 | 5474.54 | 0 | 0 | 0 | -29850.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34234 | Columns - all levels below ground | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | LAB | Labour | BUDGET | Approved Early Budget | 29856.96 | 30520.26 | 30520.26 | 35606.97 | 5086.71 | 0 | 0 | 0 | 61994.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | MAT | Materials | BUDGET | Approved Early Budget | 146732 | 113348.48 | 113348.48 | 132239.9 | 18891.41 | 0 | 0 | 0 | -134777.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 8437.5 | 8437.5 | 9843.75 | 1406.25 | 0 | 0 | 0 | -28125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34236 | Platform Level | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9920.13 | 6260.42 | 6260.42 | 7303.82 | 1043.4 | 0 | 0 | 0 | 34692.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34238 | In situ walls - all levels below | LAB | Labour | BUDGET | Approved Early Budget | 73729.78 | 41109.29 | 41109.29 | 8221.86 | 32887.43 | 16443.72 | 24665.57 | 0 | 131674.16 | 36656.15 | 18328.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34238 | In situ walls - all levels below | MAT | Materials | BUDGET | Approved Early Budget | 101493.29 | 38127.96 | 38127.96 | 7625.59 | 30502.37 | 15251.19 | 22876.78 | 0 | 58610.24 | 10157.1 | 5078.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34238 | In situ walls - all levels below | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6520.44 | 27920.64 | 27920.64 | 5584.13 | 22336.51 | 11168.26 | 16752.38 | 0 | -88889 | 9982.01 | 4991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34240 | Capping beam | LAB | Labour | BUDGET | Approved Early Budget | 590891.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34240 | Capping beam | MAT | Materials | BUDGET | Approved Early Budget | 786517.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34240 | Capping beam | MISC | Miscellaneous | BUDGET | Approved Early Budget | 7801.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34240 | Capping beam | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 272566.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4638.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34240 | Capping beam | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34242 | Waling beam B1 | LAB | Labour | BUDGET | Approved Early Budget | 205481.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34242 | Waling beam B1 | MAT | Materials | BUDGET | Approved Early Budget | 286102.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2454.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34242 | Waling beam B1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 422.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34242 | Waling beam B1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 38070.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1617.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34242 | Waling beam B1 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1665.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34244 | Waling beam B2 | LAB | Labour | BUDGET | Approved Early Budget | 213037.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34244 | Waling beam B2 | MAT | Materials | BUDGET | Approved Early Budget | 379818.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34244 | Waling beam B2 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 385.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34246 | PCC beams including in-situ stitches – all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 486646.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34246 | PCC beams including in-situ stitches – all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 1773936.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34246 | PCC beams including in-situ stitches – all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 80747.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8773.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34246 | PCC beams including in-situ stitches – all levels below ground | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3024.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34248 | PCC walls – all levels below ground | LAB | Labour | BUDGET | Approved Early Budget | 36649.81 | 12224.52 | 12224.52 | 12224.52 | 2037.42 | 2037.42 | 0 | 0 | 92583.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34248 | PCC walls – all levels below ground | MAT | Materials | BUDGET | Approved Early Budget | 101706.15 | 105535.38 | 105535.38 | 105535.38 | 17589.23 | 17589.23 | 0 | 0 | -137951.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34248 | PCC walls – all levels below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6859.33 | 4589.21 | 4589.21 | 4589.21 | 764.87 | 764.87 | 0 | 0 | 4000.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34252 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 6332.99 | 6332.99 | 6332.99 | 6332.99 | 0 | 4221.99 | 6332.99 | 32083.2 | 16691.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34252 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 9543.87 | 51839.14 | 51839.14 | 51839.14 | 51839.14 | 0 | 34559.43 | 51839.14 | -24435.06 | 3840.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34252 | Staircases | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 10333.85 | 10333.85 | 10333.85 | 10333.85 | 0 | 6889.23 | 10333.85 | -54868.17 | 3690.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34252 | Staircases | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 483.92 | 483.92 | 483.92 | 483.92 | 0 | 322.62 | 483.92 | 16121.01 | 259.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34252 | Staircases | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11441.98 | 11441.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34254 | Above ground structure (Mezzanine Level) | LAB | Labour | BUDGET | Approved Early Budget | 875.85 | 0 | 38565.13 | 38565.13 | 38565.13 | 12855.04 | 38565.13 | 38565.13 | -40501.26 | 66638.08 | 14808.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34254 | Above ground structure (Mezzanine Level) | MAT | Materials | BUDGET | Approved Early Budget | 504.48 | 0 | 54588.32 | 54588.32 | 54588.32 | 18196.11 | 54588.32 | 54588.32 | 60342.59 | 106240.82 | 23609.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34254 | Above ground structure (Mezzanine Level) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 13199.67 | 13199.67 | 13199.67 | 4399.89 | 13199.67 | 13199.67 | 15456.69 | 66780.03 | 14840.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 3250 | 3250 | 3250 | 3250 | 3250 | 3250 | 3250 | -22750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | MAT | Materials | BUDGET | Approved Early Budget | 7620.37 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | 1501.21 | -10335.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | 5767.9 | -40375.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34256 | Drainage (Sumps fittings including power and connection to the existing system) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | 1398.86 | -9792.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34260 | Construction of Sainsburys ramp | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 16104.61 | 26841.01 | -5938.43 | 28622.3 | 32711.2 | 4088.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34260 | Construction of Sainsburys ramp | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 21029.5 | 35049.17 | -1072.26 | 25576.43 | 29230.2 | 3653.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34260 | Construction of Sainsburys ramp | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4855.72 | 8092.87 | -3463.41 | 14748.27 | 16855.17 | 2106.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34260 | Construction of Sainsburys ramp | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17092.47 | 29911.82 | 34184.93 | 4273.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | LAB | Labour | BUDGET | Approved Early Budget | 1132675.59 | 85262.71 | 59683.89 | 25578.81 | 0 | 0 | 0 | 0 | -72222.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | MAT | Materials | BUDGET | Approved Early Budget | 1043624.34 | 120210.39 | 84147.28 | 36063.12 | 0 | 0 | 0 | 0 | 34337.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5106.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 187720.44 | 11053.88 | 7737.71 | 3316.16 | 0 | 0 | 0 | 0 | 8177.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34264 | RC Skin walls – all levels below ground incl. Waterproofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 12017.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34266 | In situ walls - all levels above ground | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 22615.02 | 33922.53 | 33922.53 | 22615.02 | 45230.04 | 22615.02 | 47271.53 | 30011.17 | 7502.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34266 | In situ walls - all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 8866.38 | 0 | 28757.35 | 43136.02 | 43136.02 | 28757.35 | 57514.69 | 28757.35 | 186603.55 | 25747.46 | 6436.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34266 | In situ walls - all levels above ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 1188.57 | 1782.85 | 1782.85 | 1188.57 | 2377.14 | 1188.57 | 62177.06 | 16182.11 | 4045.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34268 | In situ columns – all levels above ground | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 37407.04 | 56110.56 | 56110.56 | 37407.04 | 56110.56 | 56110.56 | 69424.48 | 18689.83 | 4672.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34268 | In situ columns – all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 18432.18 | 0 | 42329.08 | 63493.63 | 63493.63 | 42329.08 | 63493.63 | 63493.63 | 259272.06 | 8709.76 | 2177.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34268 | In situ columns – all levels above ground | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 4296 | 6444 | 6444 | 4296 | 6444 | 6444 | -31086.33 | 875.11 | 218.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34268 | In situ columns – all levels above ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -10986.8 | 0 | 5941.21 | 8911.82 | 8911.82 | 5941.21 | 8911.82 | 8911.82 | -4182.58 | 1781.4 | 445.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34270 | PCC walls – all levels above ground | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34274 | Temporary Steel Propping | LAB | Labour | BUDGET | Approved Early Budget | 35379.39 | 0 | 0 | 0 | 15626.09 | 15626.09 | 0 | 0 | -30464.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34274 | Temporary Steel Propping | MAT | Materials | BUDGET | Approved Early Budget | 182252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34274 | Temporary Steel Propping | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 25768.25 | 0 | 0 | 0 | 2403.94 | 2403.94 | 0 | 0 | -2970.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34274 | Temporary Steel Propping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5584.8 | 5584.8 | 0 | 0 | -5411.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34276 | OSD Corridor Construction incl. sheet piling | LAB | Labour | BUDGET | Approved Early Budget | 62235.59 | 0 | 0 | 0 | 0 | 0 | 0 | 8401.61 | -8401.61 | 0 | 8695.48 | 12422.12 | 3726.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34276 | OSD Corridor Construction incl. sheet piling | MAT | Materials | BUDGET | Approved Early Budget | 305057.64 | 0 | 0 | 0 | 0 | 0 | 0 | 8689.92 | -3859.92 | 0 | 8719.26 | 12456.09 | 3736.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34276 | OSD Corridor Construction incl. sheet piling | MISC | Miscellaneous | BUDGET | Approved Early Budget | 425.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34276 | OSD Corridor Construction incl. sheet piling | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21364.34 | 0 | 0 | 0 | 0 | 0 | 0 | 3965.48 | -2555.62 | 0 | 5551.67 | 7930.96 | 2379.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34276 | OSD Corridor Construction incl. sheet piling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446.63 | 4923.76 | 1477.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 16864.02 | 25296.03 | 14053.35 | 0 | 0 | 0 | 59188.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 105280.21 | 157920.31 | 87733.51 | 0 | 0 | 0 | -12648.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 18888 | 28332 | 15740 | 0 | 0 | 0 | -62960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 1334.66 | 2001.99 | 1112.22 | 0 | 0 | 0 | -4448.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34278 | Track Slab (Mass Fill) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 6000 | 9000 | 5000 | 0 | 0 | 0 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | LAB | Labour | BUDGET | Approved Early Budget | 316229.17 | 33470.56 | 50205.83 | 0 | 0 | 0 | 0 | 0 | -46314.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | MAT | Materials | BUDGET | Approved Early Budget | 166233.78 | 39513.31 | 59269.96 | 0 | 0 | 0 | 0 | 0 | -24740.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 3000 | 4500 | 0 | 0 | 0 | 0 | 0 | -7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 36999.34 | 8769.35 | 13154.03 | 0 | 0 | 0 | 0 | 0 | -24135.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34280 | Head Walls Construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 9866.98 | 2090.24 | 3135.36 | 0 | 0 | 0 | 0 | 0 | -1193.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34282 | UMC slab | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 18084.9 | 18084.9 | 4018.87 | 0 | 0 | 0 | -8504.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34282 | UMC slab | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 10687.53 | 10687.53 | 2375.01 | 0 | 0 | 0 | -12593.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34282 | UMC slab | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 8183.77 | 8183.77 | 1818.61 | 0 | 0 | 0 | -13653.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34284 | Allowance for piling works defects rectification | LAB | Labour | BUDGET | Approved Early Budget | 60489.51 | 14421.98 | 14421.98 | 14421.98 | 4807.33 | 0 | 0 | 0 | 8051.04 | 3176.44 | 3176.44 | 3176.44 | 3176.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34284 | Allowance for piling works defects rectification | MAT | Materials | BUDGET | Approved Early Budget | 14230.93 | 4365.4 | 4365.4 | 4365.4 | 1455.13 | 0 | 0 | 0 | 4165.98 | 460.56 | 460.56 | 460.56 | 460.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34284 | Allowance for piling works defects rectification | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8684.66 | 3323.8 | 3323.8 | 3323.8 | 1107.93 | 0 | 0 | 0 | -3341.63 | 182.13 | 182.13 | 182.13 | 182.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34284 | Allowance for piling works defects rectification | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091.67 | 4091.67 | 4091.67 | 4091.67 | 4091.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34286 | Allowance for remediation works to exposed concrete elements | LAB | Labour | BUDGET | Approved Early Budget | 56751.27 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 9847.26 | 19694.52 | 109358.1 | 2566.8 | 2566.8 | 2566.8 | 2566.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34286 | Allowance for remediation works to exposed concrete elements | MAT | Materials | BUDGET | Approved Early Budget | 4431.93 | 398.55 | 398.55 | 398.55 | 398.55 | 398.55 | 398.55 | 797.1 | 28666.82 | 4940.4 | 4940.4 | 4940.4 | 4940.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34286 | Allowance for remediation works to exposed concrete elements | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10485.72 | 666.07 | 666.07 | 666.07 | 666.07 | 666.07 | 666.07 | 1332.13 | 5552.45 | 636.76 | 636.76 | 636.76 | 636.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34288 | Nine Elms Main Raised Access | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 2047.6 | 1365.06 | 3412.66 | 0 | 3424.21 | 4692.77 | 4692.77 | 4692.77 | 4692.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34288 | Nine Elms Main Raised Access | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5288.63 | 3525.75 | 8814.38 | 0 | -4538.25 | 13090.51 | 13090.51 | 13090.51 | 13090.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34288 | Nine Elms Main Raised Access | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 3387.94 | 2258.63 | 5646.57 | 0 | -5634.31 | 5658.83 | 5658.83 | 5658.83 | 5658.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34292 | Plant room plinths | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5293.14 | 5293.14 | 5293.14 | 5293.14 | 5293.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34292 | Plant room plinths | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6732.34 | 6732.34 | 6732.34 | 6732.34 | 6732.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34292 | Plant room plinths | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064.63 | 1064.63 | 1064.63 | 1064.63 | 1064.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34294 | Knock out panels | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5075.75 | 5075.75 | 5075.75 | 5075.75 | 5075.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34294 | Knock out panels | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4645.05 | 4645.05 | 4645.05 | 4645.05 | 4645.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34294 | Knock out panels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3134.1 | 3134.1 | 3134.1 | 3134.1 | 3134.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D34294 | Knock out panels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4073.14 | 4073.14 | 4073.14 | 4073.14 | 4073.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44302 | Finishes to floors walls ceilings and entrances including matwells and the like | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44312 | External Cladding & Roofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44332 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 192197 | 119314.27 | 0 | 0 | 0 | 0 | 0 | 0 | 205637.13 | 0 | 0 | 0 | 0 | 129542.8 | 261356.24 | 174541.88 | 398855.12 | 361355.94 | 161814.87 | 163633.02 | 352720.06 | 68181.45 | 22500 | 22500 | 22500 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44334 | Fire Suppression | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2731.69 | 0 | 0 | 767.96 | 1315.26 | 1262.29 | 1234.75 | 8983.16 | 208118.19 | 61620.24 | 63956.43 | 39950.11 | 17789.92 | 2013.95 | 1342.64 | 25872.58 | 34096.22 | 1121.1 | 0 | 12755.03 | 9398.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44336 | Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 8391.18 | 0 | 0 | 2359.01 | 4040.2 | 3877.5 | 3792.9 | 4934.96 | 29618.5 | 0 | 19379.1 | 75363.16 | 78951.88 | 54548.57 | 68544.59 | 108020.53 | 107302.79 | 45935.64 | 12560.53 | 41629.18 | 43782.41 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44338 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 30259.46 | 15129.73 | 18436.27 | 34752.23 | 34752.23 | 34752.23 | 34752.23 | 48443.92 | 215942 | 27665.35 | 65013.58 | 222706.08 | 381781.86 | 273886.98 | 280001.03 | 572797.28 | 426751.89 | 118961.01 | 12449.41 | 55330.7 | 40114.76 | 0 | 0 | 0 | 0 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 1992.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44340 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 5675.84 | 158923.43 | -153841.06 | 35132.43 | 76103.9 | 88664.74 | 209500.01 | 238256.94 | 173635.12 | 165507.52 | 48765.61 | 2586.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44340 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 14504.06 | 97329.63 | -111833.69 | 71868.54 | 128804.77 | 196248.11 | 375381.22 | 479526.1 | 323333.73 | 298095.78 | 127526.36 | 88205 | 39520.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44342 | Escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 74131.48 | 0 | 0 | 0 | 0 | 0 | 741053.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175976.66 | 319957.56 | 159978.78 | 319957.56 | 319957.56 | 319957.56 | 287961.8 | 207972.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44344 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 46925.05 | 0 | 0 | 47631.29 | 62539.36 | 62539.36 | 68503.06 | -89311.72 | 0 | 0 | 0 | 183277.7 | 78547.59 | 44510.3 | 52365.06 | 52365.06 | 52365.06 | 26182.53 | 34037.29 | 261825.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44347 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 7121.87 | 15791.9 | 15791.9 | 39479.75 | 78959.5 | 78959.5 | 77111.1 | 241016.97 | 436542.58 | 330034.96 | 714595.29 | 710376.67 | 416702.65 | 428376.17 | 360947.05 | 202438.83 | 65184.38 | 67479.61 | 17443.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44348 | M&E Plant | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44348 | M&E Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44348 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 888.97 | 888.97 | 888.97 | 1185.29 | 4444.84 | 4444.84 | 39780.71 | 10536.67 | 19084.57 | 14428.32 | 31240.34 | 31055.92 | 18217.21 | 18727.55 | 15779.72 | 8850.13 | 2849.7 | 2950.04 | 762.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44349 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 19378.62 | 12079.01 | 2796.51 | 6023.26 | 11232.95 | 26102.05 | 33723.24 | 155744.85 | 83840.93 | 122102.15 | 221157.81 | 167199.75 | 362022.72 | 359885.52 | 211106.67 | 406656.82 | 342646.47 | 192174.86 | 61879.43 | 64058.29 | 16559.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44349 | M&E Material | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44349 | M&E Material | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44350 | M&E Subcontractor | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44350 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 44251.03 | 0 | 0 | 0 | 0 | 6776.26 | 17233.68 | 25652.29 | 127953.23 | 49971.65 | 69697.29 | 78132.77 | 65213.29 | 106026.27 | 98238.51 | 125122.12 | 113690.9 | 117185.45 | 38404.16 | 52577.01 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 8333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44611 | Back of House BoH floor screeds | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41244.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44611 | Back of House BoH floor screeds | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29141.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44611 | Back of House BoH floor screeds | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44611 | Back of House BoH floor screeds | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 29530.58 | 29530.58 | 68904.68 | 147652.88 | -192220.8 | 125096.88 | 125096.88 | 125096.88 | 125096.88 | 125096.88 | 0 | 0 | 41698.96 | 41698.96 | 41698.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44612 | Floor Epoxi coating | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 22063.36 | 44126.72 | 66190.08 | -132380.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26061.85 | 26061.85 | 15637.11 | 15637.11 | 0 | 10424.74 | 10424.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44613 | Soft flooring: vinyl and ceramic tiles | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 5999.38 | 11998.76 | -17998.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36486.59 | 20849.48 | 31274.22 | 15637.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44614 | Front of House FoH screeds for stone flooring | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19774.2 | 49435.51 | 29661.31 | 49435.51 | 39548.41 | 9887.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44615 | Front of House FoH Stone flooring and bedding | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311.73 | 311.73 | 311.73 | 311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44615 | Front of House FoH Stone flooring and bedding | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.39 | 249.39 | 249.39 | 249.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44615 | Front of House FoH Stone flooring and bedding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.35 | 62.35 | 62.35 | 62.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44615 | Front of House FoH Stone flooring and bedding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159287.99 | 159287.99 | 159287.99 | 159287.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44616 | Waterproofing of internal areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533.72 | 1533.72 | 1533.72 | 1533.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44621 | Stainless steel cladding incl. grille 02, glazed frieze, stainless steel access panels to walls and | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 15646.15 | 15646.15 | 15646.15 | 46938.45 | 62584.6 | 48084.41 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 86747.54 | 115663.39 | 115663.39 | 115663.39 | 57831.69 | 101205.46 | 72289.62 | 72289.62 | 72289.62 | 43373.77 | 14457.92 | 14457.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44622 | Glazed downstand panel 01 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 935.39 | 935.39 | 935.39 | 2806.16 | 3741.54 | -935.4 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 5612.31 | 7483.08 | 7483.08 | 7483.08 | 3741.54 | 6547.7 | 4676.93 | 4676.93 | 4676.93 | 2806.16 | 935.39 | 935.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44623 | GFRC cladding to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 20001.62 | 20001.62 | 20001.62 | 20001.62 | 30002.43 | 118926.61 | 74562.72 | 111844.08 | 111844.08 | 111844.08 | 111844.08 | 111844.08 | 37281.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44624 | Platform edge OTE screen - support steel, cladding and louvres - North and South elevation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 8795.94 | 8795.94 | 8795.94 | 26387.82 | 35183.76 | 57967.75 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 48373.63 | 64498.18 | 64498.18 | 64498.18 | 32249.09 | 56435.91 | 40311.36 | 40311.36 | 40311.36 | 24186.82 | 8062.27 | 8062.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44625 | FoH cladding trackside acoustic cladding 04 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 5014.66 | 5014.66 | 5014.66 | 15043.98 | 20058.64 | 51399.15 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 26368.37 | 35157.82 | 35157.82 | 35157.82 | 17578.91 | 30763.09 | 21973.64 | 21973.64 | 21973.64 | 13184.18 | 4394.73 | 4394.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44626 | Glazed ballustrade and gates | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 27.53 | 27.53 | 27.53 | 82.59 | 110.12 | -27.53 | 165.18 | 165.18 | 165.18 | 165.18 | 165.18 | 165.18 | 220.24 | 220.24 | 220.24 | 110.12 | 192.71 | 137.65 | 137.65 | 137.65 | 82.59 | 27.53 | 27.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44627 | Escalator advertisement panels 01 incl. metal trim and grillages | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 410.48 | 410.48 | 410.48 | 1231.44 | 1641.92 | 16666.85 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1336.9 | 1782.54 | 1782.54 | 1782.54 | 891.27 | 1559.72 | 1114.09 | 1114.09 | 1114.09 | 668.45 | 222.82 | 222.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44631 | Double coat of Paint to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 3570 | 2040 | 2040 | 2040 | 2040 | 2040 | 1020 | 1020 | 1020 | 1020 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44631 | Double coat of Paint to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 1248.99 | 713.71 | 713.71 | 713.71 | 713.71 | 713.71 | 356.85 | 356.85 | 356.85 | 356.85 | 356.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44631 | Double coat of Paint to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 832.66 | 475.81 | 475.81 | 475.81 | 475.81 | 475.81 | 237.9 | 237.9 | 237.9 | 237.9 | 237.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44631 | Double coat of Paint to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6935.85 | 16183.65 | -19386.33 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 3733.17 | 2133.24 | 2133.24 | 2133.24 | 2133.24 | 2133.24 | 1066.62 | 1066.62 | 1066.62 | 1066.62 | 1066.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44632 | Concrete sealant to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 133.82 | 312.25 | 1338.93 | 1785 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 2550 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44632 | Concrete sealant to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 26.76 | 62.45 | 535.29 | 624.5 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 892.14 | 535.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44632 | Concrete sealant to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 17.84 | 41.63 | 356.86 | 416.33 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 594.76 | 356.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44632 | Concrete sealant to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4869.69 | 4869.69 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 6956.7 | 4174.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 755.7 | 1763.3 | -2519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 480.9 | 1122.1 | -1603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 137.4 | 320.6 | -458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44633 | Acoustic Render and plaster to walls | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6635.18 | 15482.08 | -13924.43 | 8192.84 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 11704.05 | 7022.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44634 | Windows 01 and 02 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 315.46 | 315.46 | 315.46 | 1892.75 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 1892.76 | 2523.68 | 2523.68 | 2523.68 | 1261.84 | 2208.22 | 1577.3 | 1577.3 | 1577.3 | 946.38 | 315.46 | 315.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44635 | Wall ceramic tiles | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 845.59 | 1973.03 | -2818.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5046.54 | 7065.16 | 8074.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44636 | Acoustic wall lining Wall type in Vent shafts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 11866.85 | 11866.85 | 8000 | 32600.55 | 43467.4 | 54334.25 | 43467.4 | 21733.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44641 | Concrete sealant and paint to soffits | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570 | 3570 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 5100 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44641 | Concrete sealant and paint to soffits | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44641 | Concrete sealant and paint to soffits | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44641 | Concrete sealant and paint to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4969.26 | 4969.26 | -6613.8 | 3324.72 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 4749.6 | 2849.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44642 | Back of House BoH soffit insulation and grid ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2501.8 | 2501.8 | 4441.9 | 14168.25 | 18891 | 18891 | 14168.25 | 9445.5 | 9445.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44643 | Front of House FoH metal tube ceiling, including acoustic insulation to soffit | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 11298.38 | 11298.38 | 22596.76 | 33895.14 | 154169.2 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 59115.17 | 78820.23 | 78820.23 | 78820.23 | 39410.12 | 68967.7 | 49262.64 | 49262.64 | 49262.64 | 29557.59 | 9852.53 | 9852.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44644 | Render / airtight to soffits | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2440.75 | 2440.75 | -4881.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44645 | Monorail | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | -15000 | 0 | 11864.7 | 11864.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94917.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44651 | Metalwork: handrail to stairs, railings; metal ladder; ship ladder; platform end barrier | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 6032.2 | 6032.2 | -12064.4 | 0 | 0 | 8960.75 | 22401.87 | 22401.87 | 22401.87 | 67205.61 | 67205.61 | 67205.61 | 22401.87 | 44803.74 | 44803.74 | 22401.87 | 22401.87 | 13441.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44652 | Metalwork to risers and shafts: metal floor safety grillage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 12300 | 12300 | -24600 | 0 | 0 | 6272.41 | 15681.02 | 15681.02 | 15681.02 | 47043.07 | 47043.07 | 47043.07 | 15681.02 | 31362.05 | 31362.05 | 15681.02 | 15681.02 | 9408.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44653 | Spring doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691.34 | 3691.34 | 3691.34 | 3691.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44654 | Lifting beam, jacking points and lifting eyes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 768.7 | 768.7 | -1024.93 | 1537.4 | 2049.87 | 1537.4 | 1537.4 | 1537.4 | 1537.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44654 | Lifting beam, jacking points and lifting eyes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2890.28 | 2890.28 | -4817.13 | 2890.28 | 3853.71 | 2890.28 | 2890.28 | 2890.28 | 2890.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44654 | Lifting beam, jacking points and lifting eyes | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 307.48 | 307.48 | -262.47 | 1057.48 | 1409.97 | 1057.48 | 1057.48 | 1057.48 | 1057.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44654 | Lifting beam, jacking points and lifting eyes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6710 | 20130 | 26840 | 20130 | 20130 | 20130 | 20130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44655 | Durasteel floors including raised flooring | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 2550 | 5100 | 7650 | 10200 | 10200 | 7650 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44661 | Internal fit out to Sainsbury's ramp | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 1025.82 | 683.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44661 | Internal fit out to Sainsbury's ramp | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439.64 | 439.64 | 439.64 | 439.64 | 439.64 | 439.64 | 293.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44661 | Internal fit out to Sainsbury's ramp | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.55 | 146.55 | 146.55 | 146.55 | 146.55 | 146.55 | 97.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44661 | Internal fit out to Sainsbury's ramp | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 10258.2 | 6838.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44671 | Station Office Room SOR control desk | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11558.92 | 11558.92 | 11558.92 | 11558.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44672 | Front of House Signage and Wayfinding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 6667.48 | 16668.71 | 50006.13 | 66674.84 | 83343.56 | 50006.13 | 16668.71 | 6667.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44673 | Back of House Signage and Wayfinding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 1832.23 | 4580.57 | 13741.71 | 18322.28 | 22902.85 | 13741.71 | 4580.57 | 1832.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44674 | FoH office furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420 | 4420 | 6630 | 6630 | 6630 | 6630 | 6630 | 2210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44675 | BoH office furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6909.67 | 6909.67 | 10364.5 | 10364.5 | 3454.83 | 10364.5 | 10364.5 | 6909.67 | 3454.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44676 | Defibrilators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562.66 | 3562.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44681 | Durasteel - Wal ltypes M1, M2, M3, Fire rated ceiling | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12666.71 | 25333.42 | 38000.12 | 38000.12 | 38000.12 | 25333.42 | 38000.12 | 38000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44682 | Drywall lining - Wall types D4, E1, E2, E5, E6, F3, F4, G4 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23675.5 | -23675.5 | 0 | 0 | 0 | 0 | 0 | 0 | 29164.2 | 29164.2 | 29164.2 | 19442.8 | 29164.2 | 29164.2 | 29164.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44683 | Internal blockwork & brickwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44683 | Internal blockwork & brickwork | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 201446.05 | 201446.05 | 115112.03 | 259002.06 | 316558.07 | 559943.98 | 284730.43 | 237275.36 | 221457 | 94910.14 | 94910.14 | 94910.14 | 63273.43 | 47455.07 | 47455.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44684 | Internal blockwork & brickwork fireproofing | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 25051.29 | 10020.52 | 35071.81 | 50102.58 | 37561.4 | 82372.39 | 68643.66 | 64067.42 | 27457.46 | 27457.46 | 27457.46 | 18304.98 | 13728.73 | 13728.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44691 | Internal metal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 30022.53 | 60045.06 | -90067.59 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 70632.3 | 188352.8 | 258985.1 | 353161.5 | 188352.8 | 282529.2 | 282529.2 | 164808.7 | 117720.5 | 47088.2 | 23544.1 | 23544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44692 | Internal access panels | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 213.45 | 426.9 | -640.35 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 2134.5 | 1067.25 | 1067.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44692 | Internal access panels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 516 | -774 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 2580 | 1290 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44693 | Intenal floor access hatches. | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 312 | -468 | 0 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 780 | 1560 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44694 | Wall access panels with firestopping, pressurised, etc | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | -300 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 500 | 1000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44695 | Temporary Doors Installation | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 2520 | 5040 | 7560 | 7560 | 7560 | 5040 | 7560 | 2520 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44695 | Temporary Doors Installation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 1440 | 2160 | 2160 | 2160 | 1440 | 2160 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44695 | Temporary Doors Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 720 | 1080 | 1080 | 1080 | 720 | 1080 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44701 | Firestopping to penetrations, voids, lifts and escalators | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 14073.79 | 28147.59 | -12733.86 | 32981.28 | 43975.03 | 54968.79 | 54968.79 | 54968.79 | 76956.31 | 76956.31 | 76956.31 | 76956.31 | 54968.79 | 76956.31 | 54968.79 | 54968.79 | 54968.79 | 54968.79 | 32981.28 | 32981.28 | 32981.28 | 21987.52 | 10993.76 | 10993.76 | 10993.76 | 10993.76 | 10993.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44702 | Fireproof mastic to doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.44 | -495.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4954.4 | 4954.4 | 2477.2 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 4954.4 | 2477.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44703 | Firecurtains to lift doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 8500 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44704 | Diamond drilling to services | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.4 | 1898.4 | 2847.6 | 3796.8 | 4746 | 4746 | 4746 | 6644.4 | 6644.4 | 6644.4 | 4746 | 6644.4 | 6644.4 | 4746 | 4746 | 4746 | 4746 | 2847.6 | 2847.6 | 2847.6 | 1898.4 | 949.2 | 949.2 | 949.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44704 | Diamond drilling to services | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271.2 | 271.2 | 406.8 | 542.4 | 678 | 678 | 678 | 949.2 | 949.2 | 949.2 | 678 | 949.2 | 949.2 | 678 | 678 | 678 | 678 | 406.8 | 406.8 | 406.8 | 271.2 | 135.6 | 135.6 | 135.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44704 | Diamond drilling to services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.4 | 542.4 | 813.6 | 1084.8 | 1356 | 1356 | 1356 | 1898.4 | 1898.4 | 1898.4 | 1356 | 1898.4 | 1898.4 | 1356 | 1356 | 1356 | 1356 | 813.6 | 813.6 | 813.6 | 542.4 | 271.2 | 271.2 | 271.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44704 | Diamond drilling to services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2154.56 | 253.62 | 2408.18 | 3612.27 | 4816.36 | 6020.45 | 6020.45 | 6020.45 | 8428.63 | 8428.63 | 8428.63 | 6020.45 | 8428.63 | 8428.63 | 6020.45 | 6020.45 | 6020.45 | 6020.45 | 3612.27 | 3612.27 | 3612.27 | 2408.18 | 1204.09 | 1204.09 | 1204.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44711 | Eastern entrance envelope and canopy | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 46925.49 | 46925.49 | 46925.49 | 93850.97 | 93850.97 | -48575.41 | 110645 | 110645 | 110645 | 110645 | 110645 | 221290 | 287677 | 265548 | 265548 | 110645 | 177032 | 110645 | 66387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44712 | External louvres and metal cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 65799.32 | 65799.32 | 65799.32 | 131598.63 | 63906.41 | 155645 | 155645 | 155645 | 155645 | 155645 | 311290 | 404677 | 373548 | 373548 | 155645 | 249032 | 155645 | 93387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44713 | External Reconstituted stone cladding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 44945.73 | 44945.73 | 44945.73 | 74909.55 | 74909.55 | -74550.07 | 96952.62 | 124653.37 | 166204.49 | 207755.61 | 138503.74 | 138503.74 | 96952.62 | 96952.62 | 69251.87 | 27700.75 | 69251.87 | 41551.12 | 13850.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44714 | External Metal doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 21292.95 | 21292.95 | -42585.9 | 0 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 15393.3 | 30786.6 | 46179.9 | 30786.6 | 46179.9 | 46179.9 | 15393.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44715 | External Sunray louvered doors | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11557.25 | 16180.15 | 18491.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44716 | External access hatches | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44717 | Bituminous painting to columns and blockwork | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | -4130 | 10800 | 13500 | 13500 | 13500 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44717 | Bituminous painting to columns and blockwork | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126 | -1126 | 9007.99 | 11259.99 | 11259.99 | 11259.99 | 2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44717 | Bituminous painting to columns and blockwork | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.67 | -750.67 | 6005.33 | 7506.66 | 7506.66 | 7506.66 | 1501.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44718 | External waterproofing to roof and Pascal square | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 8259.99 | 24779.97 | -33039.96 | 0 | 0 | 13500 | 13500 | 13500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44718 | External waterproofing to roof and Pascal square | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2252 | 6755.99 | -9007.99 | 0 | 0 | 13511.99 | 13511.99 | 13511.99 | 4504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44718 | External waterproofing to roof and Pascal square | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 375.33 | 1126 | -1501.33 | 0 | 0 | 4504 | 4504 | 4504 | 1501.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44718 | External waterproofing to roof and Pascal square | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 17475.4 | 52426.2 | -69901.6 | 0 | 0 | 74914.2 | 74914.2 | 74914.2 | 24971.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44721 | Cleaning to Front of House areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44722 | Cleaning to Back of House areas | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11533 | 11533 | 5766.5 | 11533 | 11533 | 11533 | 11533 | 11533 | 11533 | 11533 | 5766.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44723 | Cleaning to External Envelope | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 4135.05 | 2756.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44724 | FLO Cleaning works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758 | 16758 | 16758 | 16758 | 16758 | 16758 | 11172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44724 | FLO Cleaning works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788 | 4788 | 4788 | 4788 | 4788 | 4788 | 3192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44724 | FLO Cleaning works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394 | 2394 | 2394 | 2394 | 2394 | 2394 | 1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44725 | Outstanding Works / Final Snagging | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29169 | 29169 | 29169 | 29169 | 29169 | 29169 | 19446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44725 | Outstanding Works / Final Snagging | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8334 | 8334 | 8334 | 8334 | 8334 | 8334 | 5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D44725 | Outstanding Works / Final Snagging | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54402 | Groundwork's, foundations and BWIC | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25348.93 | 11488.93 | 11488.93 | 11488.93 | 11488.93 | 11488.93 | 7659.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54402 | Groundwork's, foundations and BWIC | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 4031.53 | 2687.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54402 | Groundwork's, foundations and BWIC | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 3767.53 | 2511.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54402 | Groundwork's, foundations and BWIC | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 16612.65 | 11075.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54404 | Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5131.72 | 7697.58 | 7697.58 | 7697.58 | 7697.58 | 7697.58 | 5131.72 | 2565.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54404 | Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17151.27 | 25726.9 | 25726.9 | 25726.9 | 25726.9 | 25726.9 | 17151.27 | 8575.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54404 | Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1682.83 | 2524.25 | 2524.25 | 2524.25 | 2524.25 | 2524.25 | 1682.83 | 841.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54404 | Drainage | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25997.26 | 38995.88 | 38995.88 | 38995.88 | 38995.88 | 38995.88 | 25997.26 | 12998.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | MAT | Materials | BUDGET | Approved Early Budget | 801.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54406 | Temporary surfaces | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14122.84 | 21184.26 | 28245.68 | 35307.1 | 21184.26 | 14122.84 | 7061.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54408 | Feature Paving | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34444.8 | 51667.2 | 68889.6 | 68889.6 | 60278.4 | 34444.8 | 17222.4 | 8611.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54410 | Street Furniture | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54410 | Street Furniture | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54410 | Street Furniture | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9044.25 | 18088.5 | 36177 | 54265.5 | 72354 | 72354 | 54265.5 | 36177 | 9044.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54412 | Soft Landscaping | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54412 | Soft Landscaping | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7633.74 | 15267.48 | 17812.06 | 20356.64 | 20356.64 | 10178.32 | 5089.16 | 5089.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54414 | General Signage, Totems and Way finding | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507.65 | 6761.47 | 9015.29 | 13522.94 | 9015.29 | 2253.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54416 | Power and Comms | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54418 | Arch 42 works | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5361.5 | 8042.25 | 8042.25 | 8042.25 | 8042.25 | 8042.25 | 5361.5 | 2680.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54418 | Arch 42 works | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.38 | 2822.07 | 2822.07 | 2822.07 | 2822.07 | 2822.07 | 1881.38 | 940.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54418 | Arch 42 works | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1758.18 | 2637.27 | 2637.27 | 2637.27 | 2637.27 | 2637.27 | 1758.18 | 879.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54418 | Arch 42 works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10253.88 | 15380.82 | 15380.82 | 15380.82 | 15380.82 | 15380.82 | 10253.88 | 5126.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D54420 | Cleaning to External Works | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64504 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7316.48 | 7316.48 | 7316.48 | 7316.48 | 7316.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64506 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 19923.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64508 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64508 | Station Ventilation | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 44298.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D64508 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 54470935.39 | 1706277.85 | 2123303.23 | 2351294.02 | 2054306.61 | 1502780.8 | 2686793.15 | 3418926.61 | 3636939.82 | 3697974.8 | 3704449.2 | 3571431.74 | 4799028.85 | 4650840.02 | 4164534.3 | 4889091.48 | 4653372.82 | 4082253.29 | 2123544.33 | 2875734.57 | 2881075.15 | 1868494.01 | 1592274.27 | 1377522.01 | 864237.55 | 674357.41 | 485546.73 | 355524.41 | 248117.58 | 180712.87 | 171450.15 | 144910.43 | 114766.28 | 93735.82 | 88945.14 | 86952.79 | 81572.52 | 12856.01 | 8161.7 | 8161.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | STAFF | 4575922.27 | 162080 | 165695 | 167505 | 170945 | 170945 | 172695 | 172695 | 132723.08 | 179471.73 | 168120.64 | 168120.64 | 168120.64 | 169735.63 | 169735.63 | 160091.83 | 157254.06 | 153193.5 | 153193.5 | 143457.41 | 143457.41 | 184226.08 | 178550.54 | 160139.63 | 150588.11 | 129500.93 | 105368.34 | 53479.3 | 47803.76 | 47803.76 | 47803.76 | 31884.55 | 22240.74 | 15180.92 | 15180.92 | 15180.92 | 11120.37 | 11120.37 | 7059.82 | 7059.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 8970601.62 | 488772.14 | 646766.74 | 589006.18 | 482458.81 | 359715.29 | 584027.19 | 563498.9 | 873501.55 | 876157.06 | 839110.6 | 592308.8 | 976600.88 | 925550.73 | 618467.06 | 636735.52 | 574741.28 | 405033.06 | 262420.21 | 254069.66 | 198593.76 | 163155.04 | 187815.43 | 154068.82 | 153748.82 | 137008.48 | 132124.6 | 122274.6 | 94696.4 | 63129.2 | 63129.2 | 58329.2 | 54440 | 54440 | 51080 | 51080 | 51080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 3883257.47 | 178626.74 | 219159.97 | 186390.45 | 169898.28 | 126073.33 | 189310.69 | 164894.46 | 765054.12 | 277743.85 | 186421.06 | 120627.84 | 134119.31 | 110473.7 | 92001.42 | 76248.64 | 74958.97 | 62922.44 | 54155.98 | 54948.42 | 52589.19 | 38505.72 | 39654.83 | 35053.68 | 26300.56 | 23289.75 | 22781.32 | 18090.12 | 15394.02 | 10537.34 | 8640.21 | 8047.41 | 7345.16 | 7345.16 | 6868.27 | 6868.27 | 6331.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 14307794.64 | 589139.19 | 859757.72 | 878645.21 | 538944.02 | 243726.62 | 578761.66 | 807204.42 | 297192.54 | 616232.31 | 558606.4 | 375501.96 | 677933.32 | 658894.54 | 433585.99 | 621739.01 | 450253.68 | 250528.97 | 112414.9 | 116769.32 | 65483.06 | 36500.85 | 37710.9 | 25539.77 | 28671.6 | 28155.59 | 26088.45 | 23186.18 | 18319.73 | 9269.13 | 8255.26 | 5833.75 | 4801 | 4801 | 3847.21 | 3847.21 | 3753.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 20539771.32 | 208061.29 | 126305.11 | 415630.24 | 598754.39 | 536237.08 | 1086877.9 | 1628788.32 | 1744097.99 | 1684327.36 | 1890829.36 | 2255602.32 | 2776224.74 | 2713853.96 | 2783574.93 | 3338564.22 | 3342080.74 | 3159911.24 | 1496493.98 | 2263103.24 | 2378444.74 | 1404456.89 | 1112533.59 | 972970.34 | 481467.17 | 336232.61 | 182780.52 | 123311.32 | 60992.28 | 39062.05 | 32710.33 | 32439.03 | 19082.43 | 6213.67 | 6213.67 | 4221.32 | 4166.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 1523047.09 | 50721.1 | 77178.3 | 85676.55 | 64647.05 | 35018.95 | 44056.18 | 47500.8 | -279974.13 | 31794.41 | 27447.77 | 27228.99 | 27228.99 | 33352.57 | 33352.57 | 23195.56 | 23195.56 | 23195.56 | 19809.89 | 19809.89 | 19809.89 | 19809.89 | 15055.27 | 11669.59 | 6871.88 | 6871.88 | 6871.88 | 6835.97 | 3450.3 | 3450.3 | 3450.3 | 3400.03 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 3385.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 670540.98 | 28877.39 | 28440.39 | 28440.39 | 28659.06 | 31064.53 | 31064.53 | 34344.71 | 104344.67 | 32248.08 | 33913.37 | 32041.19 | 38800.97 | 38978.89 | 33816.7 | 32516.7 | 30888.53 | 27468.52 | 25055.87 | 23576.63 | 22697.1 | 21839.54 | 20953.71 | 18080.18 | 16589.41 | 13298.17 | 9531.62 | 8346.92 | 7461.09 | 7461.09 | 7461.09 | 4976.46 | 3471.28 | 2369.4 | 2369.4 | 2369.4 | 1735.64 | 1735.64 | 1101.88 | 1101.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 54470935.39 | 1706277.85 | 2123303.23 | 2351294.02 | 2054306.61 | 1502780.8 | 2686793.15 | 3418926.61 | 3636939.82 | 3697974.8 | 3704449.2 | 3571431.74 | 4799028.85 | 4650840.02 | 4164534.3 | 4889091.48 | 4653372.82 | 4082253.29 | 2123544.33 | 2875734.57 | 2881075.15 | 1868494.01 | 1592274.27 | 1377522.01 | 864237.55 | 674357.41 | 485546.73 | 355524.41 | 248117.58 | 180712.87 | 171450.15 | 144910.43 | 114766.28 | 93735.82 | 88945.14 | 86952.79 | 81572.52 | 12856.01 | 8161.7 | 8161.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128503187.41
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## E
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
E08500 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 773699.04 | 32546.1 | 32546.1 | 16273.05 | 0 | 0 | 0 | 0 | -29687.76 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15000 | General Management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 50352.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15000 | General Management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | -50352.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15002 | Tunnels Prelims - Running Tunnels (TBM) | LAB | Labour | BUDGET | Approved Early Budget | 121449.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15002 | Tunnels Prelims - Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | -18227.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15002 | Tunnels Prelims - Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15002 | Tunnels Prelims - Running Tunnels (TBM) | STAFF | Staff | BUDGET | Approved Early Budget | 5226601.71 | 3713.79 | 3713.79 | 0 | 0 | 0 | 0 | 0 | -64970.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 355109.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71607.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | -2159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1722.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | STAFF | Staff | BUDGET | Approved Early Budget | 5718999.9 | 176601.07 | 169173.5 | 75925.76 | 0 | 0 | 0 | 0 | -9437.77 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 24883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15004 | SCL Prelims Tunnels | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15010 | Northbound Running Tunnels Plant | MAT | Materials | BUDGET | Approved Early Budget | 298221.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15010 | Northbound Running Tunnels Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 72206.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35910.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15010 | Northbound Running Tunnels Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8483986.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34021.03 | 0 | 0 | 0 | 0 | -1216059.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15010 | Northbound Running Tunnels Plant | STAFF | Staff | BUDGET | Approved Early Budget | 24945.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1889.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15010 | Northbound Running Tunnels Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2143768.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | LAB | Labour | BUDGET | Approved Early Budget | 58.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | MAT | Materials | BUDGET | Approved Early Budget | 1255210.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 41027.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 26014.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15011 | Northbound Running Tunnels Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 535487.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1217.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | LAB | Labour | BUDGET | Approved Early Budget | 2394453.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 89111.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15012 | Northbound Running Tunnels Labour (Assembly and Disassembly) | STAFF | Staff | BUDGET | Approved Early Budget | 139787.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15013 | Southbound Running Tunnels Plant | MAT | Materials | BUDGET | Approved Early Budget | 310154.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15013 | Southbound Running Tunnels Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 42629.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35910.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15013 | Southbound Running Tunnels Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8545746.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34020.92 | 0 | 0 | 0 | 0 | 0 | -1216059.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15013 | Southbound Running Tunnels Plant | STAFF | Staff | BUDGET | Approved Early Budget | 24945.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1889.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15013 | Southbound Running Tunnels Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2116900.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15014 | Southbound Running Tunnels Materials | MAT | Materials | BUDGET | Approved Early Budget | 1140446.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15014 | Southbound Running Tunnels Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 48367.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15014 | Southbound Running Tunnels Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 166407.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15014 | Southbound Running Tunnels Materials | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33333.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15014 | Southbound Running Tunnels Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 545238.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1217.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | LAB | Labour | BUDGET | Approved Early Budget | 2348574.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | MAT | Materials | BUDGET | Approved Early Budget | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 114328.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15015 | Southbound Running Tunnels Labour (Assembly and Disassembly) | STAFF | Staff | BUDGET | Approved Early Budget | 139787.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15020 | Site Facilities & Logistics | MAT | Materials | BUDGET | Approved Early Budget | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15020 | Site Facilities & Logistics | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1641.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15022 | Running Tunnels (TBM) | LAB | Labour | BUDGET | Approved Early Budget | 26311.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15022 | Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | 173673.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15022 | Running Tunnels (TBM) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 234.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15022 | Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 70589.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18120.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15022 | Running Tunnels (TBM) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4898434.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10972.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 827543.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | 1515776.06 | 32195.09 | 26448.23 | 18857.67 | 0 | 0 | 0 | 0 | -7400.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | 465162.56 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 25427.14 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 339519.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15082.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 364305.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15024 | SCL Tunnels | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 1201.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15031 | SCL PPE | MAT | Materials | BUDGET | Approved Early Budget | 12129.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15031 | SCL PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1420.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15031 | SCL PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 195013.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15032 | TBM PPE | MAT | Materials | BUDGET | Approved Early Budget | 41648.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15032 | TBM PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2365.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15032 | TBM PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 110751.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15042 | Running Tunnels (TBM) | MAT | Materials | BUDGET | Approved Early Budget | 246.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15042 | Running Tunnels (TBM) | MISC | Miscellaneous | BUDGET | Approved Early Budget | -87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15042 | Running Tunnels (TBM) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15042 | Running Tunnels (TBM) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15044 | SCL Tunnels | LAB | Labour | BUDGET | Approved Early Budget | 178.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15044 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | 1111.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15044 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 20458.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E25110 | SCL Tunnels | MAT | Materials | BUDGET | Approved Early Budget | -88.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E25110 | SCL Tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | -62999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E25110 | SCL Tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 63286.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35010 | Construction of CP1 | LAB | Labour | BUDGET | Approved Early Budget | 1275837.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3604.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35010 | Construction of CP1 | MAT | Materials | BUDGET | Approved Early Budget | 347664.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35010 | Construction of CP1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | 164956.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35010 | Construction of CP1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 42417.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35010 | Construction of CP1 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 449.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35020 | Construction of CP2 | LAB | Labour | BUDGET | Approved Early Budget | 834759.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35020 | Construction of CP2 | MAT | Materials | BUDGET | Approved Early Budget | 239688.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35020 | Construction of CP2 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 37813.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35020 | Construction of CP2 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 394.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35030 | Construction of CP3 | LAB | Labour | BUDGET | Approved Early Budget | 1155491.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35030 | Construction of CP3 | MAT | Materials | BUDGET | Approved Early Budget | 257062.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65355.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35030 | Construction of CP3 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 39405.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18448.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35030 | Construction of CP3 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 394.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 331.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35060 | Above ground & Enabling Works (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1635417.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35070 | Excavation and Primary lining (TBM Launch Galleries) | MAT | Materials | BUDGET | Approved Early Budget | 685.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35070 | Excavation and Primary lining (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35070 | Excavation and Primary lining (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1120381.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35080 | Waterproofing (TBM Launch Galleries) | LAB | Labour | BUDGET | Approved Early Budget | 11186.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35080 | Waterproofing (TBM Launch Galleries) | MAT | Materials | BUDGET | Approved Early Budget | 12.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35080 | Waterproofing (TBM Launch Galleries) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 65.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35080 | Waterproofing (TBM Launch Galleries) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 195948.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35090 | Secondary lining TBM Launch Galleries | LAB | Labour | BUDGET | Approved Early Budget | 492031.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3136.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35090 | Secondary lining TBM Launch Galleries | MAT | Materials | BUDGET | Approved Early Budget | 313486.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -62603.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35090 | Secondary lining TBM Launch Galleries | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 18427.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35090 | Secondary lining TBM Launch Galleries | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 959686.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35100 | KP Secondary lining | LAB | Labour | BUDGET | Approved Early Budget | 327398.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35100 | KP Secondary lining | MAT | Materials | BUDGET | Approved Early Budget | 169796.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35100 | KP Secondary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 6423.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35100 | KP Secondary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 308800.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | LAB | Labour | BUDGET | Approved Early Budget | 241436.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | MAT | Materials | BUDGET | Approved Early Budget | 105564.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11919.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 84271.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35130 | KG Above ground & Enabling Works KG to tie-in point 180m | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | LAB | Labour | BUDGET | Approved Early Budget | 2212084.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11996.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | MAT | Materials | BUDGET | Approved Early Budget | 838316.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14780.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 48881.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35140 | KG Excavation and Primary lining (inc Adit gallery for grout treatment) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 95897.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18460.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35150 | KG Waterproofing (excl 1st stage concrete and drainage) | LAB | Labour | BUDGET | Approved Early Budget | 5192.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35150 | KG Waterproofing (excl 1st stage concrete and drainage) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 219228.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35160 | KG Northbound Secondary lining | LAB | Labour | BUDGET | Approved Early Budget | 521048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35160 | KG Northbound Secondary lining | MAT | Materials | BUDGET | Approved Early Budget | 327562.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35160 | KG Northbound Secondary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5015.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35160 | KG Northbound Secondary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 494958.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35170 | KP Above ground & Enabling Works KP | LAB | Labour | BUDGET | Approved Early Budget | 221950.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35170 | KP Above ground & Enabling Works KP | MAT | Materials | BUDGET | Approved Early Budget | 138062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35170 | KP Above ground & Enabling Works KP | MISC | Miscellaneous | BUDGET | Approved Early Budget | 864.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35170 | KP Above ground & Enabling Works KP | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 79280.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | LAB | Labour | BUDGET | Approved Early Budget | 1670352.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21347.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | MAT | Materials | BUDGET | Approved Early Budget | 375120.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 15379.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35180 | KP Excavation and Primary lining (inc Adit gallery for grout treatment) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 8557.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35190 | KP Waterproofing (excl 1st stage concrete and drainage) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35190 | KP Waterproofing (excl 1st stage concrete and drainage) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 89837.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35210 | Above ground & Enabling Works Overrun | LAB | Labour | BUDGET | Approved Early Budget | 491418.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68200.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35210 | Above ground & Enabling Works Overrun | MAT | Materials | BUDGET | Approved Early Budget | 31021.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35210 | Above ground & Enabling Works Overrun | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 808.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35210 | Above ground & Enabling Works Overrun | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 37189.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | LAB | Labour | BUDGET | Approved Early Budget | 195625.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | MAT | Materials | BUDGET | Approved Early Budget | 100976.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35290 | Overrun Excavation and Primary lining including CP4 & CP5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5856.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9117.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35309 | Overrun Tunnels Waterproofing including CP4 & CP5 | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 100315.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | LAB | Labour | BUDGET | Approved Early Budget | 119431.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26338.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | MAT | Materials | BUDGET | Approved Early Budget | 77790.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35310 | Overrun Tunnels Secondary lining including CP4 & CP5 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 992.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | LAB | Labour | BUDGET | Approved Early Budget | 181404.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | MAT | Materials | BUDGET | Approved Early Budget | 4659188.64 | 12855.84 | 12855.84 | 0 | 0 | 0 | 0 | 0 | -25711.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35370 | Northbound Running Supply of PC Segment | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 59362.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55458.47 | 5000 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35380 | Northbound Running Power Consumption | LAB | Labour | BUDGET | Approved Early Budget | 2101.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35380 | Northbound Running Power Consumption | MISC | Miscellaneous | BUDGET | Approved Early Budget | 336401.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35380 | Northbound Running Power Consumption | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35390 | Northbound Running Fuel Consumption | MAT | Materials | BUDGET | Approved Early Budget | 31544.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35410 | Northbound Running Grout Materials | LAB | Labour | BUDGET | Approved Early Budget | 11034.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11034.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35410 | Northbound Running Grout Materials | MAT | Materials | BUDGET | Approved Early Budget | 402771.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35410 | Northbound Running Grout Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 8694.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35410 | Northbound Running Grout Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -4281.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35415 | Northbound General Plant Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35431 | Tunnel Labour below ground | LAB | Labour | BUDGET | Approved Early Budget | 3178768.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2906.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35431 | Tunnel Labour below ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 284116.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35432 | Tunnel Labour Above Ground | LAB | Labour | BUDGET | Approved Early Budget | 2615256.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1306.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35450 | Southbound Running Supply of PC Segments | MAT | Materials | BUDGET | Approved Early Budget | 4676741.57 | 12855.84 | 12855.84 | 0 | 0 | 0 | 0 | 0 | -25711.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35450 | Southbound Running Supply of PC Segments | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35450 | Southbound Running Supply of PC Segments | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 59362.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55458.47 | 5000 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35460 | Southbound Running Power Consumption | LAB | Labour | BUDGET | Approved Early Budget | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35460 | Southbound Running Power Consumption | MISC | Miscellaneous | BUDGET | Approved Early Budget | 341425.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35460 | Southbound Running Power Consumption | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35470 | Southbound Running Fuel Consumption | MAT | Materials | BUDGET | Approved Early Budget | 16033.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35480 | Southbound Running Supply of SGI Rings | LAB | Labour | BUDGET | Approved Early Budget | 190160.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -873.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35480 | Southbound Running Supply of SGI Rings | MAT | Materials | BUDGET | Approved Early Budget | 426409.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35480 | Southbound Running Supply of SGI Rings | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3508.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35480 | Southbound Running Supply of SGI Rings | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 829.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35490 | Northbound Running Supply of SGI RINGS | MAT | Materials | BUDGET | Approved Early Budget | 428150.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35490 | Northbound Running Supply of SGI RINGS | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35490 | Northbound Running Supply of SGI RINGS | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1072.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35511 | Tunnel Labour Below Ground | LAB | Labour | BUDGET | Approved Early Budget | 3212004.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2906.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35511 | Tunnel Labour Below Ground | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 284116.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35512 | Tunnel Labour Above Ground | LAB | Labour | BUDGET | Approved Early Budget | 2562091.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1306.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35537 | TBM | MAT | Materials | BUDGET | Approved Early Budget | -28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35537 | TBM | MISC | Miscellaneous | BUDGET | Approved Early Budget | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35537 | TBM | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 370410.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35547 | Conveyor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 44147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35557 | Locomotives | MAT | Materials | BUDGET | Approved Early Budget | 4381.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35557 | Locomotives | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35557 | Locomotives | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10525.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35567 | Other | LAB | Labour | BUDGET | Approved Early Budget | 19.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35567 | Other | MAT | Materials | BUDGET | Approved Early Budget | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35567 | Other | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 10028.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35567 | Other | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35570 | Southbound Running Grout Materials | MAT | Materials | BUDGET | Approved Early Budget | 402354.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35570 | Southbound Running Grout Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5942.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35570 | Southbound Running Grout Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -1263.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35577 | TBM | MAT | Materials | BUDGET | Approved Early Budget | -24475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35577 | TBM | MISC | Miscellaneous | BUDGET | Approved Early Budget | 24475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35577 | TBM | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 370410.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35587 | Conveyor | MISC | Miscellaneous | BUDGET | Approved Early Budget | 57397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35597 | Locomotives | MAT | Materials | BUDGET | Approved Early Budget | 1780.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35597 | Locomotives | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2601.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35597 | Locomotives | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 20232.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35607 | Other | LAB | Labour | BUDGET | Approved Early Budget | 19.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35607 | Other | MAT | Materials | BUDGET | Approved Early Budget | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35607 | Other | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16227.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35607 | Other | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 3212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35610 | North and South bound Ground treatment | MAT | Materials | BUDGET | Approved Early Budget | 491.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35620 | KG SCL pilot (26m) Excavation and Primary lining | LAB | Labour | BUDGET | Approved Early Budget | 783075.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35620 | KG SCL pilot (26m) Excavation and Primary lining | MAT | Materials | BUDGET | Approved Early Budget | 214252.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35620 | KG SCL pilot (26m) Excavation and Primary lining | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1202.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35620 | KG SCL pilot (26m) Excavation and Primary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 77265.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35620 | KG SCL pilot (26m) Excavation and Primary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 68953.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | LAB | Labour | BUDGET | Approved Early Budget | 3681565.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28458.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | MAT | Materials | BUDGET | Approved Early Budget | 1061736.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 138997.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 54504.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6162.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | STAFF | Staff | BUDGET | Approved Early Budget | 19888.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4613.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35630 | KG SGI Rings Supply and Installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 46809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 69786.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -38084.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 91016.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | STAFF | Staff | BUDGET | Approved Early Budget | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35636 | KG SGI Rings Purchased Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35637 | KG SGI Rings Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 6788.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35637 | KG SGI Rings Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35637 | KG SGI Rings Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 294496.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35638 | KG SGI Rings Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 43605.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35638 | KG SGI Rings Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 2796.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35638 | KG SGI Rings Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 72660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35639 | KG SGI Rings Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 6825.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35639 | KG SGI Rings Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9312.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35650 | KP Dewatering | MISC | Miscellaneous | BUDGET | Approved Early Budget | 102229.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10383.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35660 | KP SCL pilot (26m) Excavation and Primary lining | LAB | Labour | BUDGET | Approved Early Budget | 717765.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35660 | KP SCL pilot (26m) Excavation and Primary lining | MAT | Materials | BUDGET | Approved Early Budget | 209297.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35660 | KP SCL pilot (26m) Excavation and Primary lining | MISC | Miscellaneous | BUDGET | Approved Early Budget | 6121.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35660 | KP SCL pilot (26m) Excavation and Primary lining | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5790.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35660 | KP SCL pilot (26m) Excavation and Primary lining | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 14942.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | LAB | Labour | BUDGET | Approved Early Budget | 3950232.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | MAT | Materials | BUDGET | Approved Early Budget | 778028.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 112587.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22084.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | STAFF | Staff | BUDGET | Approved Early Budget | 19444.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4168.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35670 | KP SGI Rings Supply and Installation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 23952.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3339.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 63402.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -47654.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 126964.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | STAFF | Staff | BUDGET | Approved Early Budget | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35676 | KP SGI Rings Purchased Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6814.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35677 | KP SGI Rings Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 5315.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35677 | KP SGI Rings Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35677 | KP SGI Rings Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 207420.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35678 | KP SGI Rings Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 36186.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35678 | KP SGI Rings Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3267.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35678 | KP SGI Rings Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 78404.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35679 | KP SGI Rings Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 9058.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35679 | KP SGI Rings Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1568.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35679 | KP SGI Rings Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2800.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | LAB | Labour | BUDGET | Approved Early Budget | 3411361.94 | 814410.52 | 255968.56 | 122430.14 | 0 | 0 | 0 | 0 | -55848.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | MAT | Materials | BUDGET | Approved Early Budget | 591792.17 | 41918.17 | 44246.13 | 22170.67 | 0 | 0 | 0 | 0 | -2796.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5338.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 61611.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26079.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | STAFF | Staff | BUDGET | Approved Early Budget | 16316.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35680 | Tunnelling incl. junctions to existing platform tunnels | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 221640.77 | 146432.27 | 123653.92 | 30913.48 | 0 | 0 | 0 | 0 | -318193.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35686 | KStation CP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 2029.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35686 | KStation CP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23961.79 | 47165.89 | 34382.77 | 36951.12 | 0 | 0 | 0 | 0 | -115963.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35687 | KStation CP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1551.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35687 | KStation CP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 57795.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290046.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35687 | KStation CP Hire Plant | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35687 | KStation CP Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 497150 | 16270.25 | 6508.1 | 1627.03 | 0 | 0 | 0 | 0 | 191675.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35688 | KStation CP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 1882.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35688 | KStation CP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 974.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35689 | KStation CP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 65.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35690 | Southbound General Plant Materials | LAB | Labour | BUDGET | Approved Early Budget | 3805.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35690 | Southbound General Plant Materials | MAT | Materials | BUDGET | Approved Early Budget | 654009.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35690 | Southbound General Plant Materials | MISC | Miscellaneous | BUDGET | Approved Early Budget | 105397.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35690 | Southbound General Plant Materials | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 920943.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35690 | Southbound General Plant Materials | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 82098.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35705 | Running CP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 2875.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35705 | Running CP Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 10985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35705 | Running CP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 13465.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35706 | Running CP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 992.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35706 | Running CP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 329450.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145262.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35707 | Running CP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 564.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35707 | Running CP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 860.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35708 | Running CP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 5754.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35708 | Running CP Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 535.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35715 | Launch Galleries Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 578.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35715 | Launch Galleries Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2227.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35716 | Launch Galleries Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 832.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35716 | Launch Galleries Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 230561.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27741.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35716 | Launch Galleries Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 385556.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35717 | Launch Galleries Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 1218.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35717 | Launch Galleries Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35718 | Launch Galleries Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 803.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35720 | KG plant | MAT | Materials | BUDGET | Approved Early Budget | 12446.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35720 | KG plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -33213.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35720 | KG plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14079.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35725 | KG Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 81918.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35725 | KG Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 43723.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35725 | KG Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 560070.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35726 | KG Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1058.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35726 | KG Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 21800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35726 | KG Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 296523.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26665.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35726 | KG Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 20909.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35727 | KG Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 43120.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35727 | KG Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5539.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35727 | KG Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 115801.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35728 | KG Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 10649.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35728 | KG Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 727.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35728 | KG Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 348.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35730 | KP Plant | LAB | Labour | BUDGET | Approved Early Budget | 5914.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35730 | KP Plant | MAT | Materials | BUDGET | Approved Early Budget | 217.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35730 | KP Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | -21983.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35730 | KP Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 39692.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35735 | KP Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 45894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35735 | KP Purchased Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 22711.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35735 | KP Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 357272.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35736 | KP Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 1804.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35736 | KP Hire Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 21800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35736 | KP Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 293854.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26665.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35736 | KP Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 13777.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35737 | KP Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 33185.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35737 | KP Spare Parts | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35737 | KP Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 94144.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35738 | KP Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 7507.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35738 | KP Fuel & Lubricants | MISC | Miscellaneous | BUDGET | Approved Early Budget | 727.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35738 | KP Fuel & Lubricants | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4586.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35765 | Overrun tunnels Purchased Plant | MAT | Materials | BUDGET | Approved Early Budget | 1356.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35765 | Overrun tunnels Purchased Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 5129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35766 | Overrun tunnels Hire Plant | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35766 | Overrun tunnels Hire Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 31401.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60923.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35766 | Overrun tunnels Hire Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35767 | Overrun tunnels Spare Parts | MAT | Materials | BUDGET | Approved Early Budget | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35767 | Overrun tunnels Spare Parts | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 9075.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35768 | Overrun tunnels Fuel & Lubricants | MAT | Materials | BUDGET | Approved Early Budget | 5756.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35800 | Northbound Running Consumables | MAT | Materials | BUDGET | Approved Early Budget | 805964.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35800 | Northbound Running Consumables | MISC | Miscellaneous | BUDGET | Approved Early Budget | 49718.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35800 | Northbound Running Consumables | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 348331.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35800 | Northbound Running Consumables | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 104639.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35890 | Southbound Running Consumables | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35890 | Southbound Running Consumables | MAT | Materials | BUDGET | Approved Early Budget | 814143.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35890 | Southbound Running Consumables | MISC | Miscellaneous | BUDGET | Approved Early Budget | 64873.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35890 | Southbound Running Consumables | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 319329.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E35890 | Southbound Running Consumables | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 104639.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45318 | Fit Out | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45318 | Fit Out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | LAB | Labour | BUDGET | Approved Early Budget | 1061.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41153.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | MAT | Materials | BUDGET | Approved Early Budget | 21678.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -231.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | MISC | Miscellaneous | BUDGET | Approved Early Budget | 14699.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2344.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45352 | Tunnel Fit Out - M&E | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1034478.43 | 522006.48 | 134228.09 | 184925.42 | 462701.75 | 449836.1 | 395757.93 | 416993.44 | 659472.61 | 250365.23 | 330191.82 | 1041718.92 | 909152.35 | 787017.66 | 599969.43 | 239733.78 | 192309.52 | 79826.59 | 0 | 0 | 101597.48 | 14513.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45354 | SCL Tunnel Fit Out | MAT | Materials | BUDGET | Approved Early Budget | 2075.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45374 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 472.52 | 0 | 6355.72 | 542.69 | 542.69 | 542.69 | 0 | 0 | -6668.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45381 | M&E Material (CP) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45385 | Kennington Station cross passages Fit Out | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 131000 | 35000 | 9000 | 9000 | 9000 | -175759 | 25000 | 25000 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45385 | Kennington Station cross passages Fit Out | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45385 | Kennington Station cross passages Fit Out | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 16059.73 | 16059.65 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45385 | Kennington Station cross passages Fit Out | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5390.2 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45385 | Kennington Station cross passages Fit Out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 339000 | 173000 | 94000 | 46000 | 62000 | -190848.94 | 126091.2 | 160602.65 | 119538.05 | 97927.88 | 56235.27 | 60656.46 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45910 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 479.3 | 229.48 | 0 | 550.46 | 550.46 | 550.46 | 550.46 | 27217.83 | -18376.1 | 0 | 0 | 0 | 0 | 1075.97 | 10829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E45920 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 258112.9 | 0 | 0 | 0 | 0 | 255876.51 | 311907.53 | 848759.12 | -68188.4 | 0 | 169587.26 | 425838.59 | 1179421.19 | 1894327.09 | 2273633.1 | 1930509.86 | 1197813.93 | 881188.7 | 374089.54 | 523725.36 | 282645.43 | 409939.79 | 74817.91 | 63200.38 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E65505 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 43450.26 | 217251.3 | 217251.3 | 217251.3 | 217251.3 | 217251.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E65542 | SPJ Tunnel Fit Out - T&C | MAT | Materials | BUDGET | Approved Early Budget | 3468.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E65568 | T&C Material (CP) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 123530534.88 | 1871700.79 | 862936.59 | 981167.49 | 671794.9 | 809805.76 | 763215.92 | 1363970.39 | 581636.29 | 431929.25 | 706664.35 | 1662628.44 | 2262034.3 | 1610188.87 | 1816620.87 | 2304776.52 | 1433573.71 | 1004465.55 | 417539.8 | 567175.62 | 601494.21 | 641705.02 | 292069.21 | 280451.68 | 237001.42 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | E | STAFF | 11293995.71 | 180314.86 | 172887.29 | 75925.76 | 0 | 0 | 0 | 0 | -33330.16 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 40407146.67 | 814410.52 | 255968.56 | 253430.14 | 35000 | 9000 | 9000 | 9000 | -190123.67 | 25000 | 25000 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 25165875.26 | 47165.89 | 34382.77 | 36951.12 | 0 | 0 | 0 | 0 | 310724.51 | 5390.2 | 2000 | 2000 | 2000 | -1214059.73 | -1214059.65 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 24714241.87 | 99824.94 | 96406.04 | 41028.34 | 0 | 0 | 0 | 0 | -101.49 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 18893585.69 | 684938.48 | 270745.83 | 557559.08 | 636794.9 | 800805.76 | 754215.92 | 1354970.39 | 402151.68 | 386456.43 | 664581.73 | 1630545.82 | 2229951.68 | 2782106.25 | 2988538.25 | 2263693.9 | 1433573.71 | 1004465.55 | 417539.8 | 567175.62 | 601494.21 | 641705.02 | 292069.21 | 280451.68 | 237001.42 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 2277959.54 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 122003.18 | 6000 | 6000 | 6000 | 6000 | 18059.73 | 18059.65 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 777730.14 | 32546.1 | 32546.1 | 16273.05 | 0 | 0 | 0 | 0 | -29687.76 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 3682.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 123530534.88 | 1871700.79 | 862936.59 | 981167.49 | 671794.9 | 809805.76 | 763215.92 | 1363970.39 | 581636.29 | 431929.25 | 706664.35 | 1662628.44 | 2262034.3 | 1610188.87 | 1816620.87 | 2304776.52 | 1433573.71 | 1004465.55 | 417539.8 | 567175.62 | 601494.21 | 641705.02 | 292069.21 | 280451.68 | 237001.42 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 19750.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147884832.91
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## F
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
F08600 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 167960.56 | 1491 | 8397.25 | 9014.13 | 9746.94 | 9571.94 | 9659.44 | 9484.44 | 5118.14 | 14294.46 | 14774.76 | 15777.26 | 16213.26 | 16213.26 | 16508.26 | 16184.26 | 16191.76 | 16540.76 | 14771.67 | 14891.67 | 13539.17 | 13039.17 | 13375.32 | 10765.82 | 10765.82 | 9939.23 | 8150.73 | 7650.73 | 7400.73 | 7225.73 | 7225.73 | 7225.73 | 7225.73 | 6656.69 | 6656.69 | 5756.69 | 5496.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F08610 | MEP Working Area Overhead | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181.84 | 1761.96 | 3568.54 | 7647.89 | 9384.7 | 2823.47 | 3585.32 | 1531.93 | 3796.94 | 4156.19 | 4643.93 | 3713.31 | 2173.5 | 887.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16002 | K.Shafts Prelims Kennington - PHASE 1 | LAB | Labour | BUDGET | Approved Early Budget | 270704.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16002 | K.Shafts Prelims Kennington - PHASE 1 | MAT | Materials | BUDGET | Approved Early Budget | 38797.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16002 | K.Shafts Prelims Kennington - PHASE 1 | MISC | Miscellaneous | BUDGET | Approved Early Budget | -140.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16002 | K.Shafts Prelims Kennington - PHASE 1 | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 444.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16002 | K.Shafts Prelims Kennington - PHASE 1 | STAFF | Staff | BUDGET | Approved Early Budget | 1349152.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16004 | K.Shafts Prelims Kennington - PHASE II | MISC | Miscellaneous | BUDGET | Approved Early Budget | -23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16004 | K.Shafts Prelims Kennington - PHASE II | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16004 | K.Shafts Prelims Kennington - PHASE II | STAFF | Staff | BUDGET | Approved Early Budget | 299170.82 | 55424.7 | 111116.11 | 55306.69 | 59880 | 79310 | 79987.5 | 80352.5 | 68107.22 | 67726.87 | 61700 | 61700 | 61700 | 61700 | 61700 | 72060 | 50010 | 47810 | 47810 | 47810 | 43410 | 43410 | 41210 | 23285 | 23285 | 20210 | 12560 | 12560 | 12560 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16020 | K.Shafts Prelims Site Facilities & Logistics | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16020 | K.Shafts Prelims Site Facilities & Logistics | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | LAB | Labour | BUDGET | Approved Early Budget | -56683.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5320 | 5320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | MAT | Materials | BUDGET | Approved Early Budget | 99510.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | MISC | Miscellaneous | BUDGET | Approved Early Budget | 400067.55 | 22325 | 15947 | 22325 | 22325 | 22325 | 19250 | 18500 | -110042.63 | 13324.99 | 14074.99 | 13324.99 | 13324.99 | 13324.99 | 8412.5 | 7662.5 | 7662.5 | 7662.5 | 8412.5 | 7662.5 | 7662.5 | 7662.5 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 53798.13 | 0 | 0 | 0 | 5248 | 2624 | 5248 | 2624 | -15744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5248 | 5248 | 5248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16022 | Temporary Services | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 292035.89 | 3828 | 4794.41 | 6368.1 | 12274.57 | 6334.82 | 13307.33 | 4877 | 76043.97 | 5040 | 5040 | 8971.87 | 14555.6 | 14555.6 | 15315.6 | 14555.6 | 11383.73 | 5800 | 5040 | 5040 | 4870 | 3040 | 3040 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | LAB | Labour | BUDGET | Approved Early Budget | 260993.49 | 0 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 8015.13 | 5828.98 | 14252.54 | 14284.73 | 14284.73 | 14284.73 | 14284.73 | 14284.73 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 9475.47 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 8701.51 | 21853.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | MAT | Materials | BUDGET | Approved Early Budget | 135636.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.98 | 222 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 406.25 | 0 | 0 | 2096.5 | 0 | 0 | 1048.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 800869.39 | 0 | 925 | 75 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 23998.31 | 97 | 661.25 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 470.73 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 606.6 | 303.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 4301.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12414.96 | 6436.3 | 8406.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16024 | Temporary Accommodation | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2987.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16026 | IT Equipment & running costs | MISC | Miscellaneous | BUDGET | Approved Early Budget | 63371.23 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | 2771.78 | -12770.35 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16026 | IT Equipment & running costs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 213.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12708.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16026 | IT Equipment & running costs | STAFF | Staff | BUDGET | Approved Early Budget | 2760.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2771.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16026 | IT Equipment & running costs | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 2711.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | LAB | Labour | BUDGET | Approved Early Budget | 145754.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | MAT | Materials | BUDGET | Approved Early Budget | 762616.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23991.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 130284.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 35898.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24189.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 182631.92 | 11555.08 | 29876.18 | -21905.02 | 2055.08 | 3211.08 | 3939.08 | 1411.08 | -12415.38 | 2171 | 2171 | 2171 | 2171 | 2171 | 2152 | 2152 | 2152 | 11256 | 2152 | 2152 | 2627 | 2652 | 2652 | 2152 | 125 | 125 | 125 | 125 | 125 | 17.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16028 | Environmental Control | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16030 | H&S Quality Environmental | MAT | Materials | BUDGET | Approved Early Budget | 4800.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16030 | H&S Quality Environmental | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1144.19 | 3084.33 | 4539.99 | 3140 | 2806 | 2806 | 2806 | 1485.33 | 2541.2 | 1858.85 | 1858.85 | 1858.85 | 2408.85 | 550 | 550 | 550 | 550 | 0 | 0 | 6903 | 2408.85 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16030 | H&S Quality Environmental | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 15801.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4059.9 | 176.6 | 176.6 | 176.6 | 176.6 | 176.6 | 176.6 | 130.2 | 130.2 | 130.2 | 130.2 | 176.6 | 176.6 | 176.6 | 130.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16030 | H&S Quality Environmental | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 23031.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683.6 | 1683.6 | 1683.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4368 | 3290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16030 | H&S Quality Environmental | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 909.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16031 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 445.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 24951.44 | 2450 | 6356.84 | 1982.93 | 1122.31 | 1982.93 | 1440.81 | 1982.93 | 12937.52 | 5619.9 | 1982.93 | 1982.93 | 1982.93 | 1982.93 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 1084.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16032 | Liaison and Coordination with others | LAB | Labour | BUDGET | Approved Early Budget | 22370.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16032 | Liaison and Coordination with others | MAT | Materials | BUDGET | Approved Early Budget | 13534.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16032 | Liaison and Coordination with others | MISC | Miscellaneous | BUDGET | Approved Early Budget | 75822.63 | 5248 | 78 | 672 | 500 | 750 | 0 | 0 | -2123.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16032 | Liaison and Coordination with others | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 18334.12 | 3362 | 0 | 0 | 416 | 0 | 0 | 416 | 15173.41 | 0 | 1889 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | LAB | Labour | BUDGET | Approved Early Budget | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | MAT | Materials | BUDGET | Approved Early Budget | 12651.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6823.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1776.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 14342.5 | 5116 | 21307.95 | 2976.37 | 1512.79 | 2976.37 | 2976.37 | 2976.37 | 31539.84 | 7476.84 | 3511.6 | 4790.92 | 3593.19 | 3593.19 | 4789.87 | 6625.11 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4786.73 | 4188.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16034 | Waste Management & Disposal | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 910.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | LAB | Labour | BUDGET | Approved Early Budget | 244922.54 | 3666.6 | 7179.9 | 9809.9 | 9993.9 | 9993.9 | 25760.7 | 27167.7 | -47049.35 | 29978.34 | 29978.34 | 29978.34 | 29978.34 | 27164.34 | 23472.02 | 16292.12 | 15413.79 | 15413.79 | 15413.79 | 12603.15 | 16408.35 | 16408.35 | 16408.35 | 15457.05 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 12603.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | MAT | Materials | BUDGET | Approved Early Budget | 380481.36 | 87343.28 | 97568.56 | 71365.09 | 25885.2 | 11040.81 | 0 | 0 | -417903.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 187687.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12227.09 | 16081.85 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 71474.93 | 2646 | 2646 | 2646 | 2646 | 3646 | 2646 | 2646 | 593015.48 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 719.44 | 508.72 | 508.72 | 1508.72 | 508.72 | 508.72 | 3154.72 | 3154.72 | 3154.72 | 5292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16036 | Logistics (Including Temporary Work/Access/ & Site Hoardings/Barriers) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 135767.76 | -1205.56 | 4920.87 | 331.44 | 331.44 | 331.44 | 331.44 | 331.44 | -5372.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35689.21 | 35689.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16038 | Security & Access Control | LAB | Labour | BUDGET | Approved Early Budget | 893972.6 | 42131 | 26869.53 | 26119.53 | 26119.53 | 18826.5 | 26357.1 | 26357.1 | 56014.25 | 27107.1 | 26357.1 | 26357.1 | 26607.1 | 26357.1 | 18826.5 | 12045.9 | 11295.9 | 11295.9 | 11295.9 | 19154.7 | 11295.9 | 12045.9 | 11795.9 | 11295.9 | 11295.9 | 12795.9 | 11295.9 | 11295.9 | 11795.9 | 7530.6 | 7530.6 | 7530.6 | 7530.6 | 3765.3 | 3765.3 | 3765.3 | 3765.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16038 | Security & Access Control | MAT | Materials | BUDGET | Approved Early Budget | 22309.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16038 | Security & Access Control | MISC | Miscellaneous | BUDGET | Approved Early Budget | 19012.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16038 | Security & Access Control | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 3503.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16038 | Security & Access Control | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 65205 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | -130 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16042 | Materials Handling Plant | LAB | Labour | BUDGET | Approved Early Budget | 13956.5 | 0 | 3024 | 3024 | 3024 | 1512 | 3024 | 3024 | -16632 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 1512 | 3024 | 3024 | 3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16042 | Materials Handling Plant | MAT | Materials | BUDGET | Approved Early Budget | 1267.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16042 | Materials Handling Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 11705.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16042 | Materials Handling Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 19289.54 | 0 | 0 | 1386 | 1386 | 753 | 1386 | 1386 | -2755.3 | 1326 | 1386 | 1386 | 753 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1386 | 1299.2 | 839.2 | 839.2 | 839.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16042 | Materials Handling Plant | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16044 | Cranage | LAB | Labour | BUDGET | Approved Early Budget | 16269.84 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | -29489.73 | 9550.8 | 9550.8 | 9550.8 | 9550.8 | 4775.4 | 0 | 0 | 0 | 0 | 0 | 4775.4 | 4775.4 | 4775.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16044 | Cranage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16044 | Cranage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 58486.26 | 21539.81 | 21666.23 | 16818.01 | 18997.2 | 10195.62 | 20206.2 | 18839.7 | 141615.17 | 18500 | 6312.88 | 5689.88 | 2463.07 | 1517.81 | 0 | 0 | 0 | 0 | 0 | 2463.07 | 2463.07 | 2463.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16046 | Passenger/Goods Hoists | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5888.89 | -5546.89 | 13732.33 | 18322.83 | 5347.63 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 1547.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16048 | General Plant | LAB | Labour | BUDGET | Approved Early Budget | 12325.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16048 | General Plant | MAT | Materials | BUDGET | Approved Early Budget | 23958.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25081.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16048 | General Plant | MISC | Miscellaneous | BUDGET | Approved Early Budget | 6550.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16048 | General Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 132426.13 | 8768.68 | 8440.87 | 6817.15 | 6498.34 | 2676 | 3437 | 3237 | 60474.02 | 16403.58 | 3955 | 3055 | 2335 | 960 | 960 | 960 | 960 | 960 | 960 | 7023.36 | 7023.36 | 5173 | 4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16050 | Small Plant & PPE | MAT | Materials | BUDGET | Approved Early Budget | 8808.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7666.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16050 | Small Plant & PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16050 | Small Plant & PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 84939.62 | 2363.2 | 4467.36 | 1796.04 | 1806 | 1675 | 2447.2 | 2447.2 | 21590.97 | 7427.6 | 3011.2 | 3011.2 | 3064 | 984 | 0 | 0 | 0 | 0 | 0 | 4989.6 | 4989.6 | 3453.6 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16052 | Scaffolding | LAB | Labour | BUDGET | Approved Early Budget | 17196.77 | 9960.3 | 9960.3 | 9960.3 | 9960.3 | 4980.15 | 9960.3 | 7470.23 | 24641.87 | 4980.15 | 4980.15 | 4980.15 | 4980.15 | 4980.15 | 2490.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16052 | Scaffolding | MAT | Materials | BUDGET | Approved Early Budget | 7667.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8945.18 | 0 | 0 | 0 | 1942.8 | 1942.8 | 1942.8 | 3885.6 | 3885.6 | 1942.8 | 1942.8 | 1942.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16052 | Scaffolding | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 387 | 3478.96 | 1665.5 | 1390 | 695 | 1390 | 2403.96 | 13807.19 | 3437.32 | 3437.32 | 3437.32 | 695 | 695 | 347.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F16052 | Scaffolding | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 21898.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26100 | Utilities | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26100 | Utilities | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26100 | Utilities | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26110 | Kennington Park | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26110 | Kennington Park | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26111 | KP-Trials Pits & Utilities Surveys | LAB | Labour | BUDGET | Approved Early Budget | 4432.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8428.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26111 | KP-Trials Pits & Utilities Surveys | MAT | Materials | BUDGET | Approved Early Budget | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26111 | KP-Trials Pits & Utilities Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 1423.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8428.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26111 | KP-Trials Pits & Utilities Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7946.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26112 | KP - Water Works (TW) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 127506.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43628.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26112 | KP - Water Works (TW) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17122.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26113 | KP-Gas works | MISC | Miscellaneous | BUDGET | Approved Early Budget | 929026.82 | 0 | 0 | 0 | 18970.25 | 0 | 0 | 0 | -18970.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184929.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26114 | KP - Cabling Works (UKPN-Comms) | MISC | Miscellaneous | BUDGET | Approved Early Budget | -18724.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26114 | KP - Cabling Works (UKPN-Comms) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 16695.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26114 | KP - Cabling Works (UKPN-Comms) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26115 | KP-Permanent Connections (UKPN-Water) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 58800.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9568.02 | 9568.02 | 0 | 0 | 0 | 0 | 9568.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26115 | KP-Permanent Connections (UKPN-Water) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26116 | KP-Surveys for UXO | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26120 | Kennington Green | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26120 | Kennington Green | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26121 | KG-Trials Pits & Utilities Surveys | LAB | Labour | BUDGET | Approved Early Budget | 37163.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7060.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26121 | KG-Trials Pits & Utilities Surveys | MAT | Materials | BUDGET | Approved Early Budget | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26121 | KG-Trials Pits & Utilities Surveys | MISC | Miscellaneous | BUDGET | Approved Early Budget | 18235.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26121 | KG-Trials Pits & Utilities Surveys | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1996.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26122 | KG - Water Works (TW) | MAT | Materials | BUDGET | Approved Early Budget | 17545.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26122 | KG - Water Works (TW) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 574749.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26122 | KG - Water Works (TW) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 17706.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26123 | KG-Gas works (SGN-NG) | MAT | Materials | BUDGET | Approved Early Budget | 6552.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26123 | KG-Gas works (SGN-NG) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 251341.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26123 | KG-Gas works (SGN-NG) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2411.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26124 | KG - Cabling Works (UKPN-Comms) | MAT | Materials | BUDGET | Approved Early Budget | 1579.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26124 | KG - Cabling Works (UKPN-Comms) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 915217.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26124 | KG - Cabling Works (UKPN-Comms) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -16695.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26124 | KG - Cabling Works (UKPN-Comms) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26125 | KG-Permanent Connections (UKPN-Water) | MAT | Materials | BUDGET | Approved Early Budget | 1071.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26125 | KG-Permanent Connections (UKPN-Water) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 65235.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9519.24 | 9519.24 | 0 | 0 | 0 | 0 | 0 | 9519.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26125 | KG-Permanent Connections (UKPN-Water) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 80.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26125 | KG-Permanent Connections (UKPN-Water) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F26126 | KG-Surveys for UXO | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36212 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 8760.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13137.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36212 | Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 19622.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36212 | Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 332.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36212 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2759.3 | 4973 | 4872 | 0 | 0 | 0 | 0 | 0 | -12345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36212 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 23343.79 | 22195 | 15347 | 0 | 0 | 0 | 0 | 0 | 25268.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 502.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -319.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 252831.79 | 4620 | 4620 | 8830 | 0 | 0 | 0 | 0 | 14635.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 52341.33 | 10597.13 | 5298.57 | 0 | 0 | 0 | 0 | 0 | -24395.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36213 | Excavation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 193901.64 | 103418.44 | 27009.96 | 4023.59 | 0 | 0 | 0 | 0 | 13779.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3700 | 0 | 1233.33 | 1233.33 | 1233.33 | 0 | 0 | 0 | 0 | 0 | 0 | 34028.55 | 38258.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36214 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 67059.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36216 | Piling ( Including Ring Beam) | LAB | Labour | BUDGET | Approved Early Budget | 148429.98 | 5563.43 | 10724.85 | 402 | 0 | 0 | 0 | 0 | 1573.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36216 | Piling ( Including Ring Beam) | MAT | Materials | BUDGET | Approved Early Budget | 356651.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13195.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36216 | Piling ( Including Ring Beam) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 5519.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36216 | Piling ( Including Ring Beam) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 104956.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36216 | Piling ( Including Ring Beam) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1426299 | 1934.12 | 23484 | 15000 | 15000 | 0 | 0 | 0 | 259.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36217 | Slabs (Base intermediate) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 27812.26 | 25089.51 | 33664.76 | 46890.2 | 28855.51 | 24046.26 | 50497.14 | 225007.01 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36217 | Slabs (Base intermediate) | MAT | Materials | BUDGET | Approved Early Budget | 14748.44 | 15264.38 | 64424.53 | 91950.37 | 67999.47 | 93212.58 | 34337.57 | 30444.66 | 95841.05 | 20805.79 | 11273.4 | 28702.45 | 28702.45 | 2682.05 | 0 | 0 | 0 | 0 | 175 | 17728.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36217 | Slabs (Base intermediate) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -123600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36217 | Slabs (Base intermediate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 526.29 | 1072.43 | 0 | 4289.71 | 4289.71 | 4289.71 | 4289.71 | 4289.71 | -8414.47 | 0 | 0 | 4660.85 | 4660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36217 | Slabs (Base intermediate) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36218 | Walls (Including Internal walls and finishes) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 9205.26 | 11200.42 | 16401 | 22956.39 | 15304.26 | 24231.73 | 15304.26 | 143021.43 | 52900 | 52900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36218 | Walls (Including Internal walls and finishes) | MAT | Materials | BUDGET | Approved Early Budget | 91273.91 | 11566.4 | 39377.86 | 7687.64 | 21487.64 | 68990.26 | 75393.67 | 61121.39 | -36.6 | 30151.99 | 13364.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36218 | Walls (Including Internal walls and finishes) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 2853.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7297.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36219 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 4766.01 | 0 | 6310.79 | 2864.75 | 16277.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36219 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 10976.89 | 37571.12 | 17533.93 | -4129.9 | 7416.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36219 | Staircases | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 11129 | 11129 | 0 | 0 | 0 | -22258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | LAB | Labour | BUDGET | Approved Early Budget | 13977.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16810.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | MAT | Materials | BUDGET | Approved Early Budget | 7061.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | MISC | Miscellaneous | BUDGET | Approved Early Budget | 12487.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 32540.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11442.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8865.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36222 | Breaking out Existing Foundations and Obstructions | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5368.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5368.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36223 | Excavation | LAB | Labour | BUDGET | Approved Early Budget | 65554.69 | -199 | 199 | 0 | 0 | 0 | 0 | 0 | 10184.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36223 | Excavation | MAT | Materials | BUDGET | Approved Early Budget | 2355.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -542.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36223 | Excavation | MISC | Miscellaneous | BUDGET | Approved Early Budget | 53440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36223 | Excavation | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 28283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | MAT | Materials | BUDGET | Approved Early Budget | 338970 | 4930 | 280 | 0 | 0 | 0 | 0 | 0 | 7995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15288.43 | 15568.43 | 13158.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36224 | Disposal | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 67059.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36226 | Piling ( Including Ring Beam) | LAB | Labour | BUDGET | Approved Early Budget | 200057.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74767.82 | 0 | 6900 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36226 | Piling ( Including Ring Beam) | MAT | Materials | BUDGET | Approved Early Budget | 469999.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36226 | Piling ( Including Ring Beam) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 10992.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36226 | Piling ( Including Ring Beam) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | -95350.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36226 | Piling ( Including Ring Beam) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 1880949.34 | 13732 | -957.06 | 17225.06 | 0 | 0 | 0 | 0 | -61688.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36227 | Slabs (Base intermediate) | LAB | Labour | BUDGET | Approved Early Budget | 105867.83 | 46796.58 | 39003.43 | 51963.38 | 41087.33 | 20543.66 | 42295.78 | 0 | 57850.05 | 3877 | 3877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36227 | Slabs (Base intermediate) | MAT | Materials | BUDGET | Approved Early Budget | 118526.32 | 67580.31 | 90186.77 | 30307.49 | 77527.18 | 49252.77 | 16205.23 | 23906.63 | 31213.15 | 10450 | 32904.38 | 32904.38 | 3120.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10392.24 | 10392.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36227 | Slabs (Base intermediate) | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11575.05 | 1866.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36227 | Slabs (Base intermediate) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 7605.01 | 4289.71 | 8579.41 | 2144.85 | 2144.85 | 4289.71 | 2144.85 | 3977.06 | 75653.25 | 0 | 4660.85 | 4660.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36227 | Slabs (Base intermediate) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36228 | Walls | LAB | Labour | BUDGET | Approved Early Budget | 37439.07 | 17155.62 | 45317.86 | 7645.55 | 1220.59 | 0 | 0 | 0 | 271773.97 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36228 | Walls | MAT | Materials | BUDGET | Approved Early Budget | 146131.55 | 38252.46 | 25901.4 | 49919.71 | 58973.47 | 55524.71 | 30844.47 | 17957.42 | -32246.11 | 17957.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36228 | Walls | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4134.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30655.71 | 15282.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36229 | Staircases | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33324 | -59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36229 | Staircases | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58921.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36229 | Staircases | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 11361.5 | 33993.17 | 19399.75 | 15913.15 | 14241.83 | -94909.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36259 | K.Shafts Main Works Columns | LAB | Labour | BUDGET | Approved Early Budget | 0 | -2128 | 2505.62 | 1888.08 | 1699.27 | 755.23 | 849.63 | 0 | 61946.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36259 | K.Shafts Main Works Columns | MAT | Materials | BUDGET | Approved Early Budget | 18064.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20678.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36259 | K.Shafts Main Works Columns | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 6530.25 | 37948.7 | 18472.49 | 3168.22 | 10165.55 | 0 | -76285.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36261 | Head House Structure (including External Roofing and Cladding) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36261 | Head House Structure (including External Roofing and Cladding) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170756.69 | -170756.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36270 | K.Shafts Main Works Columns | LAB | Labour | BUDGET | Approved Early Budget | 15026.16 | 1636.33 | 0 | 1455.39 | 3044.52 | 1132.85 | 1132.85 | 0 | 41941.57 | 314.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36270 | K.Shafts Main Works Columns | MAT | Materials | BUDGET | Approved Early Budget | 17981.05 | 10629.23 | 17048.11 | 19777.39 | 15811.17 | 6066.69 | 18984.96 | 0 | -40404.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36270 | K.Shafts Main Works Columns | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1510.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1510.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36272 | K.Shafts Main Works Head House Structure (including External Roofing and Cladding) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4734.43 | 21612.72 | -26347.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F36272 | K.Shafts Main Works Head House Structure (including External Roofing and Cladding) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 82576.62 | 246120.7 | 338620.69 | -667318.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46304 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 25152.13 | 0 | 0 | 0 | 0 | 0 | 0 | 117942.3 | 0 | 0 | 0 | 0 | 37892.45 | 134345.97 | 34447.69 | 13779.07 | 241133.8 | 48226.76 | 27558.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46306 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2076.27 | 0 | 0 | 583.7 | 999.68 | 959.43 | 938.5 | 1221.08 | 7348.52 | 0 | 0 | 0 | 0 | 24387.52 | 14467.17 | 26454.26 | 56996.52 | 44488.62 | 12094.56 | 21547.82 | 8266.96 | 880.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46308 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 6345.64 | 2459.69 | 4579.38 | 6741.81 | 6741.81 | 6741.81 | 6741.81 | 9397.95 | 20950.24 | 0 | 0 | 0 | 0 | 0 | 10162.63 | 80509.04 | 94342.95 | 67740.99 | 22205.31 | 0 | 0 | 0 | 0 | 0 | 0 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 778.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46310 | Station Ventilation | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12959.1 | 0 | 0 | 3782.73 | 5455.87 | 65834.12 | 12803.1 | 67798.23 | 46265.74 | 35499.5 | 11639.18 | 29388.93 | 8729.39 | 0 | 3782.73 | 1745.88 | 581.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46310 | Station Ventilation | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89230.69 | 232587.54 | 170365.48 | 84890.42 | 37038.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46312 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 15596.98 | 0 | 0 | 0 | 0 | 0 | 0 | 10106.19 | 0 | 0 | 0 | 0 | 24012.66 | 96050.65 | 0 | 0 | 0 | 0 | 68261.99 | 108285.1 | 28238.89 | 25417.4 | 9887.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46315 | M&E Labour | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24773.06 | 86824.82 | 162120.63 | 129737 | 66568.07 | 60098.49 | 32514.64 | 48116.91 | 13339.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46316 | M&E Plant | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112.65 | 0 | 0 | 0 | 1228.68 | 4306.29 | 8040.76 | 6434.62 | 3301.6 | 2980.73 | 1612.64 | 2386.47 | 661.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46317 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 3860.97 | 4029.32 | -2014.8 | 0 | 0 | 0 | 12126.71 | 42501.79 | 79360 | 91788.12 | 47096.5 | 42519.31 | 23003.91 | 34042.41 | 9437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46318 | M&E Subcontractor | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80472.02 | 23961.98 | 18783.38 | 175.55 | 3686.46 | 3510.91 | 351.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46322 | Internal walls and finishes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27293.86 | 27293.86 | 27293.86 | 13133.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46322 | Internal walls and finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.33 | 41610.5 | 10045.23 | 96678.47 | 91882.25 | 46186.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46322 | Internal walls and finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17427.79 | 44687.5 | 114545.3 | 126819.39 | 60085.54 | 72777.09 | 91816.23 | 119729.74 | 199812.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46324 | Headhouse structure | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46324 | Headhouse structure | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153362.6 | 100641.98 | 160034.29 | 160034.29 | 114633.46 | 101145.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46332 | Internal walls and finishes | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25989.63 | 25989.63 | 25989.63 | 14176.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46332 | Internal walls and finishes | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81709.2 | 8763.73 | 154914.01 | 100200.71 | 100200.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46332 | Internal walls and finishes | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13245.65 | 70954.74 | 110036.39 | 135658.33 | 95483.37 | 65689.49 | 118416.83 | 170469.42 | 87392.31 | 41138.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46334 | Headhouse structure | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46334 | Headhouse structure | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153362.6 | 100911.54 | 100776.76 | 190563.86 | 145028.26 | 144352.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46354 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 108029.59 | 25152.13 | 0 | 0 | 0 | 0 | 0 | 0 | 45558.28 | 0 | 0 | 0 | 0 | 0 | 0 | 85717.29 | 70132.33 | 0 | 0 | 0 | 58443.61 | 136368.42 | 140264.66 | 7792.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46356 | Fire Suppression and Fire Detection | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2076.27 | 0 | 0 | 615.3 | 1053.8 | 1011.36 | 989.3 | 1287.18 | 7972.57 | 0 | 0 | 0 | 1011.14 | 8748.63 | 3701.34 | 18254.35 | 30872.56 | 5720.26 | 0 | 14637.13 | 32721.55 | 39116.46 | 29190.13 | 18001.98 | 6729.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46358 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 5870.22 | 3648.24 | 2863.46 | 7287.82 | 7287.82 | 7287.82 | 7287.82 | 10159.08 | 19007.86 | 0 | 0 | 0 | 1862.32 | 774.68 | 13789.26 | 15958.36 | 8574.13 | 13584.75 | 774.68 | 50973.78 | 23550.2 | 47549.71 | 60750.22 | 28910.97 | 2850.81 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 716.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46360 | Tunnel Vent | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57091.64 | 136842.9 | 95418.27 | 5142.67 | 256.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46360 | Tunnel Vent | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5647.69 | 8145.7 | 98291.49 | 35171.87 | 140473.45 | 92268.46 | 53001.38 | 17377.5 | 44110.12 | 66341.1 | 24976.96 | 9215.83 | 2606.63 | 868.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46362 | Lifts | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 15596.98 | 0 | 0 | 0 | 0 | 0 | 0 | 10249.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42604.97 | 85209.94 | 76696.19 | 80953.07 | 76696.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46365 | M&E Labour (KG) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8241.74 | 28915.36 | 10060.47 | 49174.81 | 136179.91 | 13602.34 | 42635.44 | 7341.38 | 61293.64 | 109566.7 | 114317.83 | 122614.98 | 83110.01 | 31858.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46366 | M&E Plant (KG) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112.65 | 0 | 0 | 415.98 | 1459.43 | 507.78 | 2481.97 | 6873.32 | 686.54 | 2151.91 | 370.54 | 3093.63 | 5530.09 | 5769.89 | 6188.67 | 4194.76 | 1607.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46367 | M&E Material (KG) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2153.96 | 10051.81 | -4335.85 | 0 | 0 | 3731.29 | 13090.88 | 4554.68 | 22262.96 | 79122.37 | 7903.14 | 24771.77 | 4265.44 | 35612.43 | 63659.74 | 66420.2 | 71240.96 | 48288.04 | 18510.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46368 | M&E Subcontractor (KG) | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F46368 | M&E Subcontractor (KG) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 54974.03 | 0 | 0 | 6116.85 | 10094.33 | 0 | 20699.63 | 12478.85 | 15849.79 | 0 | 0 | 0 | 23129.76 | 138368.6 | 0 | 15419.84 | 0 | 5806.42 | 18908.01 | 32757.59 | 3317.95 | 14516.05 | 9124.37 | 4147.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56420 | K.Shafts External Works Kennington Park | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7635.6 | 30542.4 | 30542.4 | 7635.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56420 | K.Shafts External Works Kennington Park | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64876.03 | 127126.87 | 125758.12 | 61911.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56420 | K.Shafts External Works Kennington Park | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032.6 | 4130.4 | 4130.4 | 1032.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56420 | K.Shafts External Works Kennington Park | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56440 | K.Shafts External Works Kennington Green | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7635.6 | 30542.4 | 30542.4 | 7635.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56440 | K.Shafts External Works Kennington Green | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64876.03 | 127126.87 | 125758.12 | 61911.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56440 | K.Shafts External Works Kennington Green | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032.6 | 4130.4 | 4130.4 | 1032.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F56440 | K.Shafts External Works Kennington Green | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F66502 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 7782.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F66552 | BMS Scada | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 7160.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 17796533.45 | 815407.24 | 890326.6 | 698999.12 | 735743.05 | 704267.72 | 888438.43 | 1071453.37 | 1113086.4 | 787805.41 | 902646.01 | 1081014.05 | 1134587.82 | 1575774.47 | 1383405.49 | 1595540.21 | 1050678.52 | 1177104.38 | 577339.87 | 949011.07 | 1146480.61 | 1092724.68 | 834713.3 | 392052.9 | 233275.24 | 106644.83 | 98136.83 | 59261.92 | 61791.92 | 52812.82 | 52496.62 | 51746.62 | 51746.62 | 47412.28 | 60577.24 | 51454.2 | 135175.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | F | STAFF | 1651083.69 | 55424.7 | 111116.11 | 55306.69 | 59880 | 79310 | 79987.5 | 80352.5 | 70878.9 | 67726.87 | 61700 | 61700 | 61700 | 61700 | 61700 | 72060 | 50010 | 47810 | 47810 | 47810 | 43410 | 43410 | 41210 | 23285 | 23285 | 20210 | 12560 | 12560 | 12560 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 10360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 2503604.74 | 193346.18 | 213987.35 | 179899.82 | 183561.96 | 124236 | 175224.28 | 153697.15 | 978190.68 | 236953.2 | 177841.75 | 154300.35 | 195397.03 | 226002.46 | 286526.23 | 306754.4 | 119379.57 | 141943.09 | 77553.18 | 199988.55 | 234289.96 | 234880.69 | 175565.9 | 118564.47 | 64459.4 | 34100.56 | 32600.56 | 32600.56 | 33100.56 | 28835.26 | 28835.26 | 28835.26 | 28835.26 | 25069.96 | 25069.96 | 25069.96 | 38221.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 808626.32 | 63912.96 | 84296.48 | 41463.66 | 46257.8 | 35714.94 | 46828.74 | 50901.46 | 887162.52 | 87270.91 | 45245.93 | 39403.88 | 24590.36 | 18288.21 | 21793.05 | 26367.1 | 14998.2 | 16142.7 | 13993.24 | 55097.25 | 44272.98 | 43110.82 | 25709.63 | 12837.07 | 7739.19 | 839.2 | 839.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16803.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 3342108.72 | 338984.5 | 361797.19 | 275031.28 | 267684.13 | 295064.71 | 224086.38 | 186657.88 | -130038.6 | 137378.28 | 222501.9 | 266000.03 | 256522.17 | 220793.98 | 253351.76 | 338012.59 | 110293.65 | 104990.07 | 41026.33 | 129247.5 | 92218.87 | 66420.2 | 75023.69 | 50440.17 | 19092.38 | 0 | 2096.5 | 0 | 0 | 1048.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 4348941.93 | 123811.79 | 78371.49 | 87675.26 | 108720.19 | 131022.35 | 326434.31 | 565198.87 | -443571.8 | 223693.77 | 359977.18 | 523796.2 | 560740.87 | 987121.83 | 707481.04 | 816564.66 | 728269.37 | 696378.86 | 371241.02 | 282749.51 | 370340.28 | 400782.7 | 371710.64 | 170155.62 | 102214.43 | 37724.59 | 37308.59 | 1619.38 | 3899.38 | 1512.33 | 1494.38 | 1494.38 | 1494.38 | 1494.38 | 13909.34 | 6436.3 | 10686.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 4965893.91 | 38436.11 | 32360.73 | 50608.28 | 59892.03 | 29347.78 | 26217.78 | 25161.07 | -251882.44 | 20487.92 | 20604.49 | 19854.49 | 17662.17 | 42086.19 | 28397.26 | 10212.5 | 8712.5 | 149713.58 | 9412.5 | 215429.65 | 344253.16 | 286437.17 | 128404.81 | 3831.25 | 4831.25 | 3831.25 | 4581.25 | 4831.25 | 4831.25 | 3831.25 | 4581.25 | 3831.25 | 3831.25 | 3831.25 | 4581.25 | 3831.25 | 53607.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 176274.14 | 1491 | 8397.25 | 9014.13 | 9746.94 | 9571.94 | 9659.44 | 9484.44 | 2347.14 | 14294.46 | 14774.76 | 15959.1 | 17975.22 | 19781.8 | 24156.15 | 25568.96 | 19015.23 | 20126.08 | 16303.6 | 18688.61 | 17695.36 | 17683.1 | 17088.63 | 12939.32 | 11653.59 | 9939.23 | 8150.73 | 7650.73 | 7400.73 | 7225.73 | 7225.73 | 7225.73 | 7225.73 | 6656.69 | 6656.69 | 5756.69 | 5496.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 17796533.45 | 815407.24 | 890326.6 | 698999.12 | 735743.05 | 704267.72 | 888438.43 | 1071453.37 | 1113086.4 | 787805.41 | 902646.01 | 1081014.05 | 1134587.82 | 1575774.47 | 1383405.49 | 1595540.21 | 1050678.52 | 1177104.38 | 577339.87 | 949011.07 | 1146480.61 | 1092724.68 | 834713.3 | 392052.9 | 233275.24 | 106644.83 | 98136.83 | 59261.92 | 61791.92 | 52812.82 | 52496.62 | 51746.62 | 51746.62 | 47412.28 | 60577.24 | 51454.2 | 135175.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41457666.83
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667

## G
Account_ID | Description | Element_ID | Title | Field_Name | Data_Label | 18/19 05 (5) | 18/19 06 (6) | 18/19 07 (7) | 18/19 08 (8) | 18/19 09 (9) | 18/19 10 (10) | 18/19 11 (11) | 18/19 12 (12) | 18/19 13 (13) | 19/20 01 (14) | 19/20 02 (15) | 19/20 03 (16) | 19/20 04 (17) | 19/20 05 (18) | 19/20 06 (19) | 19/20 07 (20) | 19/20 08 (21) | 19/20 09 (22) | 19/20 10 (23) | 19/20 11 (24) | 19/20 12 (25) | 19/20 13 (26) | 20/21 01 (27) | 20/21 02 (28) | 20/21 03 (29) | 20/21 04 (30) | 20/21 05 (31) | 20/21 06 (32) | 20/21 07 (33) | 20/21 08 (34) | 20/21 09 (35) | 20/21 10 (36) | 20/21 11 (37) | 20/21 12 (38) | 20/21 13 (39) | 21/22 01 (40) | 21/22 02 (41) | 21/22 03 (42) | 21/22 04 (43) | 21/22 05 (44) | 21/22 06 (45) | 21/22 07 (46) | 21/22 08 (47) | 21/22 09 (48) | 21/22 10 (49) | 21/22 11 (50) | 21/22 12 (51) | 21/22 13 (52)
G08700 | Working Area Overhead Cost Code | WAO | Working Area Overhea | BUDGET | Approved Early Budget | 27302.67 | 1214.85 | 8914.07 | 6108.24 | 5981.13 | 5514.89 | 5357.25 | 5468.1 | 78252.4 | 11419.42 | 11069.67 | 8910.2 | 5907.66 | 5490.04 | 3931.4 | 135.25 | 62.13 | 62.13 | 62.13 | 4.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17000 | R.Systems Prelims General management & Supervision | LAB | Labour | BUDGET | Approved Early Budget | 227350.2 | 38481.31 | 59681.31 | 59681.31 | 46941.18 | 37783.85 | 37783.85 | 37783.85 | 73107.38 | 62958.84 | 62958.84 | 29399.08 | 12975.79 | 12975.79 | 6024.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17000 | R.Systems Prelims General management & Supervision | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17000 | R.Systems Prelims General management & Supervision | MISC | Miscellaneous | BUDGET | Approved Early Budget | 38.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17000 | R.Systems Prelims General management & Supervision | STAFF | Staff | BUDGET | Approved Early Budget | 1114860.91 | 87348.23 | 119522.59 | 95022.59 | 79653.89 | 131096.01 | 131096.01 | 131096.01 | -31604.89 | 69602.43 | 69602.43 | 60413.63 | 50519.67 | 42113.63 | 23433.17 | 1399.43 | 1399.43 | 1399.43 | 1149.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17031 | PPE | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190.4 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 933.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17031 | PPE | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17031 | PPE | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 13048.78 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | 4634.49 | -4369.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17040 | Plant and Equipment | MAT | Materials | BUDGET | Approved Early Budget | 4312.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G17040 | Plant and Equipment | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 362693.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37210 | Trackbed construction | MAT | Materials | BUDGET | Approved Early Budget | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37210 | Trackbed construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37211 | Cleaning invert and crack repairs | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11910.75 | 0 | 15124.93 | 27224.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37211 | Cleaning invert and crack repairs | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 0 | 1783.27 | 3209.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37212 | Crainage blocks from BCO and lay down in the tunnels | LAB | Labour | BUDGET | Approved Early Budget | 55530.8 | 20220.9 | 48524.15 | 15408.43 | 9749.2 | 10995.86 | 10995.86 | 5783.14 | -112583.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37212 | Crainage blocks from BCO and lay down in the tunnels | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 37754.2 | 7654.52 | 16609.09 | 9377.72 | 9688.89 | 14903.26 | 14903.26 | 8434.11 | 29197.56 | 4087.24 | 302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37214 | Flash Welding and Distribution running rails | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 8134.05 | 32536.2 | 8134.05 | 0 | 0 | 0 | -34558.09 | 0 | 0 | 6833.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37214 | Flash Welding and Distribution running rails | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37214 | Flash Welding and Distribution running rails | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37214 | Flash Welding and Distribution running rails | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 38440.81 | 153763.25 | 45137.52 | 0 | 0 | 0 | -25014.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37215 | Second Stage Trackbed Drainage | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46310.02 | 29063.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37215 | Second Stage Trackbed Drainage | MAT | Materials | BUDGET | Approved Early Budget | 0 | 10415.5 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | 10801.26 | -75223.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37215 | Second Stage Trackbed Drainage | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | 1342.79 | -2855.18 | 1326.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37216 | Track assembly and 2nd stage concrete NB | LAB | Labour | BUDGET | Approved Early Budget | 296797.29 | 144557.73 | 115058.47 | 291694.51 | 200480.82 | 7918.58 | 7918.58 | 128692.27 | -60708.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37216 | Track assembly and 2nd stage concrete NB | MAT | Materials | BUDGET | Approved Early Budget | 1400.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37216 | Track assembly and 2nd stage concrete NB | MISC | Miscellaneous | BUDGET | Approved Early Budget | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -204.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37216 | Track assembly and 2nd stage concrete NB | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 4051.41 | 25510.19 | 20304.44 | 51475.5 | 35378.97 | 1397.4 | 1397.4 | 22710.4 | -84042.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37216 | Track assembly and 2nd stage concrete NB | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2399.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37217 | Track assembly and 2nd stage concrete SB | LAB | Labour | BUDGET | Approved Early Budget | 232102.23 | 0 | 205771.94 | 8142.27 | 86481.96 | 282331.18 | 282331.18 | 106066.88 | 231073.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37217 | Track assembly and 2nd stage concrete SB | MAT | Materials | BUDGET | Approved Early Budget | 952.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3239.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37217 | Track assembly and 2nd stage concrete SB | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 36312.69 | 1436.87 | 15261.52 | 49823.15 | 49823.15 | 18717.68 | -72383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37217 | Track assembly and 2nd stage concrete SB | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2399.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37218 | Thermit Welding NB&SB (only FLO labour and plant) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 550.2 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | 7702.82 | -11502.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37218 | Thermit Welding NB&SB (only FLO labour and plant) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 209.63 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | 2934.84 | -14565.32 | 665.75 | 1509.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | LAB | Labour | BUDGET | Approved Early Budget | 0 | 2856.74 | 3664.28 | 5102.48 | 4547.55 | 4168.8 | 4168.8 | 3536.72 | -28045.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | MAT | Materials | BUDGET | Approved Early Budget | 209950.12 | 44500.86 | 65856.12 | 102902.79 | 92898.44 | 84853.94 | 84853.94 | 69948.17 | 112141.51 | 325.58 | 23.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | -10479.42 | 1005.75 | 1005.75 | 1005.75 | 1005.75 | 215.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 46822.41 | 18722.99 | 18633.58 | 18633.58 | 13309.64 | 12422.31 | 12422.31 | 12422.31 | -70536.48 | 5986.15 | 3678.46 | 2909.23 | 2909.23 | 1573.33 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 993.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37219 | Materials, Special plant and other Equipment for trackbed construction | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67891.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37220 | Running rail and baseplates | MAT | Materials | BUDGET | Approved Early Budget | 347.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37221 | Buffer Stops | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6514.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37221 | Buffer Stops | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747.62 | -747.62 | 0 | 0 | 21745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37221 | Buffer Stops | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35288.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37222 | Materials, Special plant and other Equipment for running rails and base plates | LAB | Labour | BUDGET | Approved Early Budget | 103280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4531.76 | 1982.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37222 | Materials, Special plant and other Equipment for running rails and base plates | MAT | Materials | BUDGET | Approved Early Budget | 513661.99 | 187415.64 | 252143.14 | 455570.88 | 30411.92 | 40200.78 | 99575.78 | 80825.78 | 15803.54 | 3417.25 | 53835.76 | 12668.63 | 2896.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37222 | Materials, Special plant and other Equipment for running rails and base plates | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29102.11 | 29102.11 | 12472.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37222 | Materials, Special plant and other Equipment for running rails and base plates | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 216351 | 12055.56 | 12055.56 | 12055.56 | 12055.56 | 12055.56 | 35443 | 12055.56 | -65124.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37222 | Materials, Special plant and other Equipment for running rails and base plates | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 52880 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | 10956.09 | -28627.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37231 | Materials 3rd and 4th Rail | MAT | Materials | BUDGET | Approved Early Budget | 84942.59 | 0 | 0 | 0 | 0 | 0 | 195542.04 | 1244336.33 | -97588.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37231 | Materials 3rd and 4th Rail | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 1029.05 | 0 | 0 | 0 | 0 | 0 | 20430.03 | 0 | -13700.14 | 6729.89 | 3124.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37232 | Installation 3rd and 4th Rail | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 10369.45 | 15554.17 | 32383.41 | 100748.4 | -87032.82 | 478900.11 | 105639.83 | 36164.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37232 | Installation 3rd and 4th Rail | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18553.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37232 | Installation 3rd and 4th Rail | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 2900 | 16046.81 | 193485.26 | 56691.73 | 13736.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37232 | Installation 3rd and 4th Rail | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 5610.95 | 8416.42 | 49177 | 54515.34 | -85634.96 | 48913.4 | 14232.68 | 3419.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37232 | Installation 3rd and 4th Rail | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 22014.71 | 374250.09 | -372954.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37240 | Maintenance walkway, handrails etc. | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37240 | Maintenance walkway, handrails etc. | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37240 | Maintenance walkway, handrails etc. | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4087.24 | 302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37241 | Tunnel temporary services and general maintenance | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3490.14 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 3034.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | STAFF | Staff | BUDGET | Approved Early Budget | 491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37250 | R.Systems Main Works Junction work track (Battersea Crossover only) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37251 | Materials Crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5601.71 | 6110.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37251 | Materials Crossover box | MAT | Materials | BUDGET | Approved Early Budget | 0 | 0 | 1027755.82 | 0 | 0 | 0 | 0 | 0 | -6746.2 | 123181.89 | 51208.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37251 | Materials Crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3799.3 | 17730.09 | 17785.57 | 11113.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37251 | Materials Crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095.65 | 5113.04 | 2837.19 | 704.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37252 | Installation Crossover box | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88474.96 | 173904.74 | 144598.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37252 | Installation Crossover box | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22339.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37252 | Installation Crossover box | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 23049 | 0 | 0 | 0 | 0 | 0 | 16967.43 | 41172.4 | 19413.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37252 | Installation Crossover box | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37252 | Installation Crossover box | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 15827.54 | 8181.65 | 1332.63 | 1332.63 | 2040.63 | 1332.63 | -30047.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37261 | FLO Pre&Post works SPJ | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179573.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37261 | FLO Pre&Post works SPJ | MAT | Materials | BUDGET | Approved Early Budget | 3669.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37261 | FLO Pre&Post works SPJ | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37261 | FLO Pre&Post works SPJ | STAFF | Staff | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37261 | FLO Pre&Post works SPJ | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 7062.03 | 7062.03 | 7062.03 | 7062.03 | 7062.03 | 62764 | 7062.03 | -105136.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | LAB | Labour | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 10075 | -10850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15686.31 | 4278.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | MAT | Materials | BUDGET | Approved Early Budget | 507824.02 | 0 | 0 | 0 | 0 | 0 | 6577.8 | 18571.43 | -20910.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23192.05 | 6325.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86052.21 | 23468.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3365.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37262 | Materials SPJ | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 38000 | 0 | 5149.23 | 28320.77 | -71470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | LAB | Labour | BUDGET | Approved Early Budget | 353413.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | MAT | Materials | BUDGET | Approved Early Budget | 43608.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6659.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 22233.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | STAFF | Staff | BUDGET | Approved Early Budget | 68383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68383.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37263 | Installation SPJ (Subcontract) | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 2335258.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137914.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37271 | FSC Northbound | LAB | Labour | BUDGET | Approved Early Budget | 693212.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11229.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37271 | FSC Northbound | MAT | Materials | BUDGET | Approved Early Budget | 797291.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37271 | FSC Northbound | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3267.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -102.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37271 | FSC Northbound | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 201120.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7115.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37272 | FSC Southbound | LAB | Labour | BUDGET | Approved Early Budget | 493391.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37272 | FSC Southbound | MAT | Materials | BUDGET | Approved Early Budget | 833725.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14695.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37272 | FSC Southbound | MISC | Miscellaneous | BUDGET | Approved Early Budget | 3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37272 | FSC Southbound | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 206597.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20000.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37273 | SCL tunnels NB | LAB | Labour | BUDGET | Approved Early Budget | 8414.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37281 | Cross passages 1, 2 & 3 fit out | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58962.26 | 66037.74 | 66037.74 | 58962.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G37282 | Tunnel signage | MISC | Miscellaneous | BUDGET | Approved Early Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21226.42 | 23773.58 | 23773.58 | 21226.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G47302 | Traction Sub | MAT | Materials | BUDGET | Approved Early Budget | 3168.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G47302 | Traction Sub | PLANT | Plant & Equipment | BUDGET | Approved Early Budget | 829.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G47302 | Traction Sub | SUBCON | Subcontractors | BUDGET | Approved Early Budget | 371548.19 | 162823.61 | 0 | 0 | 40983.84 | 368854.56 | 255105 | 147795 | 93455.65 | 927.86 | 0 | 0 | 513833.14 | 713833.14 | 715431.14 | 515431.14 | 359874.35 | 0 | 0 | 0 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G47307 | M&E Material | MAT | Materials | BUDGET | Approved Early Budget | 4499.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 10569035.6 | 790366.87 | 2143525.98 | 1374361.16 | 839676.44 | 1136890.68 | 1471684.52 | 2674400.92 | -439779.83 | 1314243.94 | 758467.76 | 386341.48 | 687227.51 | 861775.91 | 755414.96 | 523560.6 | 367930.69 | 8056.34 | 7603.42 | 5462.3 | 12124.53 | 12124.53 | 12124.53 | 12124.53 | 137055.1 | 40363.18 | 6291.19 | 6291.19 | 6291.19 | 6291.19 | 6075.29 | 5082.19 | 5082.19 | 4248.86 | 3034.9 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | G | STAFF | 1183735.63 | 87348.23 | 119522.59 | 95022.59 | 79653.89 | 131096.01 | 131096.01 | 131096.01 | -94876.81 | 69602.43 | 69602.43 | 60413.63 | 50519.67 | 42113.63 | 23433.17 | 1399.43 | 1399.43 | 1399.43 | 1149.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | LAB | 2463492 | 206666.88 | 448537.02 | 420268.02 | 374407.03 | 366455.26 | 384059.5 | 400389.08 | 278144.7 | 744827.29 | 333923.41 | 116778.96 | 14958.43 | 12975.79 | 6024.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15686.31 | 4278.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | PLANT | 1112736.96 | 70130.17 | 135876.48 | 101891.35 | 100217.65 | 107930.22 | 192508.27 | 137767.52 | -368511.78 | 113994.85 | 46881.52 | 10242.91 | 2909.23 | 1573.33 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 1209 | 993.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MAT | 3010204.77 | 242332 | 1356556.34 | 569274.93 | 134111.62 | 135855.98 | 397350.82 | 1425230.59 | -38553.02 | 128061.64 | 106204.58 | 35550.55 | 4033.45 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 1136.92 | 933.9 | 0 | 0 | 0 | 0 | 0 | 23192.05 | 6325.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | SUBCON | 2764486.16 | 180841.73 | 72286.47 | 179963.02 | 143472.11 | 388205.31 | 358029.66 | 569716.61 | -332397.72 | 5015.1 | 59265.02 | 66037.74 | 579870.88 | 772795.4 | 715431.14 | 515431.14 | 359874.35 | 0 | 0 | 0 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 6666.67 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MISC | 7077.41 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 1833.01 | 3283.01 | 4733.01 | 38162.4 | 241323.21 | 131521.13 | 88407.49 | 29028.19 | 25690.8 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 90301.07 | 27717.65 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 4248.86 | 3034.9 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WAO | 27302.67 | 1214.85 | 8914.07 | 6108.24 | 5981.13 | 5514.89 | 5357.25 | 5468.1 | 78252.4 | 11419.42 | 11069.67 | 8910.2 | 5907.66 | 5490.04 | 3931.4 | 135.25 | 62.13 | 62.13 | 62.13 | 4.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Subtotal | 10569035.6 | 790366.87 | 2143525.98 | 1374361.16 | 839676.44 | 1136890.68 | 1471684.52 | 2674400.92 | -439779.83 | 1314243.94 | 758467.76 | 386341.48 | 687227.51 | 861775.91 | 755414.96 | 523560.6 | 367930.69 | 8056.34 | 7603.42 | 5462.3 | 12124.53 | 12124.53 | 12124.53 | 12124.53 | 137055.1 | 40363.18 | 6291.19 | 6291.19 | 6291.19 | 6291.19 | 6075.29 | 5082.19 | 5082.19 | 4248.86 | 3034.9 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26620851.84
[5 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692374468.6667